EXCELLENCE IN PUBLIC SECTOR AUDITING

REPORT OF THE AUDITOR GENERAL OF THE

REPUBLIC OF FIJI

Audit Report on Performance Audit – Volume 1

December 2014

EXCELLENCE IN PUBLIC SECTOR AUDITING

REPORT OF THE AUDITOR GENERAL

OF THE REPUBLIC OF FIJI

Audit Report on Performance Audits – Volume 1

December 2014

Performance Audit Reports

1.	Management of National Employment Centre

2.	Contractual Engagements by Municipal Councils

3.	Management	of	Multilateral	Environmental

Agreements

4.	Management of Rural Electrification Program

5.	Public Debt Management

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Management of

National

Employment Centre

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	1

A PERFORMANCE AUDIT REPORT OF THE OFFICE OF

THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	1

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

The NEC Policy is an outcome of the Government’s vision to achieve full employment and boost productivity for

all its citizens. Government’s commitment is reflected in the enactment of the NEC Decree 2009 and the

subsequent Regulations of 2010 that provide the framework for NEC.

Relevant institutions such as the NEC and Employment Creation Services have been established to implement

government’s national policy pertaining to employment creation matters in both the formal and informal sectors.

This audit is necessary to ascertain the extent and effectiveness of the NEC and the Employment Creation

Services in implementing government’s vision.

Table of Contents

1.0	EXECUTIVE SUMMARY..........................................................................................................4

2.0	INTRODUCTION.......................................................................................................................6

2.1	Overview...........................................................................................................................6

2.2	Reasons for the audit ...........................................................................................................7

3.0	AUDIT OBJECTIVES, SCOPE & METHODOLOGY ................................................................8

3.1	Audit objectives and scope ....................................................................................................8

3.2	Audit methodology...............................................................................................................8

4.0	KEY ARRANGEMENTS FOR NEC EXISTENCE AND OPERATION ......................................9

4.1	Governing legislation and regulation ......................................................................................10

4.2	Stakeholders involved with NEC ...........................................................................................12

4.2.1	National Employment Centre Board............................................................................................13

4.2.2	National Employment Centre Secretariat and Employment Creation Services agencies ...........15

4.2.3	Strategic partners ........................................................................................................................20

4.2.4	Employment providers.................................................................................................................21

4.3	Quality management and governance systems ........................................................................23

5.0	MANAGING KEY ACTIVITIES OF NEC .................................................................................27

5.1	Registration of the unemployed ............................................................................................27

5.2	Professional counselling services .........................................................................................29

5.3	Data management and use .................................................................................................31

5.4	Public awareness campaign ................................................................................................32

5.5	Life Skills Training (LST) – NEC Secretariat ............................................................................33

5.6	Employment Skills Training (EST).........................................................................................36

5.7	Workplace attachment- NEC Secretariat ................................................................................38

5.8	Permanent Employment .....................................................................................................39

5.9	National Employment Centre Trust Fund ................................................................................40

6.0	MONITORING AND REPORTING ACTIVITIES OF NEC ......................................................43

6.1	Performance reports ..........................................................................................................43

6.2	Annual reports ..................................................................................................................45

6.3	Monitoring clients finding employment for recovery purposes ......................................................46

7.0	CONCLUSION ........................................................................................................................48

8.0	REFERENCES ........................................................................................................................49

APPENDIX 1.1: NEC CORE BUSINESSES.....................................................................................	50

APPENDIX 1.2: FUNCTIONS OF NEC BOARD ..............................................................................	51

APPENDIX 1.3: OBJECTIVES AND GOALS OF FORMAL EMPLOYMENT SERVICES AGENCIES52

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	2

| AA | Administrative Assistant |
| --- | --- |
| ACP | Annual Corporate Plan |
| CATD | Centre for Appropriate Technology & Development |
| CFWP | Cash For Work Plus |
| CP | Cabinet Paper |
| CSO | Customer Service Officer |
| DSC | Development Sub-Committee |
| ECS | Employment Creation Services |
| ERAB | Employment Relations Advisory Board |
| EST | Employment Skills Training |
| FES | Formal Employment Services |
| FNPF | Fiji National Provident Fund |
| FORES | Foreign Employment Services |
| FRCA | Fiji Revenue and Customs Authority |
| FVS | Fiji Volunteer Services |
| IHRDP | Human Resource Development Program |
| ID | Identification |
| ILO | International Labour Organisation |
| ISO | International Organisation of Standardisation |
| LST | Life Skills Training |
| MOU | Memorandum of Understanding |
| NCSMED | National Centre for Micro Enterprise Development |
| NDMO | National Disaster Management Office |
| NEC | National Employment Centre |
| PSC | Public Service Commission |
| SES | Self-Employment Services |
| SG | Solicitor General |
| SME | Small Micro Enterprises |
| SOP | Standard Operating Procedure |
| TPAF | Training and Productivity Authority of Fiji |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1.4: STRUCTURE OF NEC INCLUDED IN CP (10) 154 ..............................................	53

APPENDIX 1.5: REVISED STRUCTURE.........................................................................................	54

APPENDIX 1.6:	EXISTING ORGANISATION STRUCTURE...................................................55

__________________________________________________________________________________________

Acronyms

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	3

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

1.0	EXECUTIVE SUMMARY

Background	The NEC was established under the National Employment Centre Decree No. 54 of 2009 to

provide social justice to unemployed persons through provision of skills and competencies, as

well as facilitate their participation towards sustainable employment.

NEC’s primary objective is to boost employment creation and improving productivity nation-

wide through a better governance framework and its core function is to consolidate all

employment creation agencies into a “one-stop” quality service for all unemployed. The

institutional transformation of all employment creation agencies through NEC is to be

undertaken by adopting international best practices and standards as reflected in the Decree.

Coverage	The audit is conducted with the objective of assessing the effectiveness of the actions taken

by key agencies to ensure the provision of quality employment services to the unemployed

and the creation of decent and environmentally sustainable employment.

The audit looks into three main areas including the key arrangements for NEC existence and

operation, management of NEC key activities and reporting and monitoring of NEC activities.

Key findings Key arrangements for NEC existence and operation

	Seven Regulations have been developed as required by the NEC Decree 2009 which was

subsequently reviewed in 2011. However, the Regulations are still awaiting vetting from

the SG’s Office before gazetting.

	The NEC Board since 2011 has not been having the required number of meetings as

prescribed under the NEC Decree 2009.

	The establishment of Self Employment Services (SES) is still awaiting implementation of

Cabinet Decision 85 of 13th March 2012.

	The required number of staffing for NEC endorsed by Cabinet has not eventuated. The

limited number of staff for NEC currently under the Ministry of Labour has greatly

affected its operations in the centres.

	NEC has not been effective in engaging strategic partners.

	Practical application of section 44 of the Decree is somewhat difficult.

	Training package for competency based and value based skill is not broken down into

modules to adequately cover ISO 9001 and ISO 26000.

Managing key activities of NEC

	Identification cards are not issued to the unemployed persons who have been registered

with NEC.

	No evidence existed to indicate that a criterion is in place governing engagement of

consultants providing professional counselling services.

	The NEC database has limited ability to generate some essential and required reports.

	NEC was not able to meet their 2012 awareness target and conduct awareness for

tertiary institutions.

	The Centre has not been able to conduct the LST regularly throughout all the centres. The

unavailability of a suitable venue has been a major hindrance.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	4

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	The current system of identifying the suitable employment skill training is not effective

as there are stills more NEC clients not being absorbed into the permanent workforce.

Monitoring and Reporting activities of NEC

	The Centre has not prepared quarterly or bi annual performance reports as required

under the given legislation.

	Audit was not able to ascertain whether reports from the two agencies providing

services not managed by NEC were prepared and submitted quarterly, bi-annually and

annually by the responsible agencies.

	Review of the NEC Board papers prepared for the Board’s recent meeting found errors in

the performance update of certain activities of the NEC.

	Apart from NEC the other ECS agencies do not submit their annual report to NEC

Secretariat that will enable them to integrate it as an integrated report of all the ECS.

	The mechanism in place to monitor absorption of clients into permanent employment is

not quite effective.

Overall conclusion	In view of the limited funding and staffing the audit acknowledges the great work done

by the Ministry of Labour so far on the establishment and operations of the NEC. The NEC

Board has also played a critical role over the years on the establishment and

implementation of the NEC.

Cabinet’s commitment on the program is also evident through the endorsement of

Cabinet Papers on the NEC submitted by the Ministry.

However, the success and sustainability of the program is heavily reliant on the

finalisation of the draft Regulations and the co-operation and commitment of other

agencies that are part of the initiative.

General Recommendation The Ministry of Labour should continue to follow up with the various agencies to ensure

the full implementation of the Cabinet Decisions and requirements of the NEC Decree

2009 in respect to the set up and operations of NEC.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	5

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.0 INTRODUCTION

This section of the report provides a brief overview of the National Employment Centre

and the reasons for conducting the audit.

2.1 Overview

2.1.1	After extensive and intensive consultations the Development Sub-Committee (DSC) in its

meetings on 5th November 2008 and 20th May 2009, in addition to discussions with stakeholders

in the Employment Relations Advisory Board (ERAB) in its meeting on the 12th of May 2009, an

enabling NEC policy framework was agreed as the best way forward to cost-effectively address

the unemployment problem in the country.1 This visionary policy concept was approved by

Cabinet on the 4th of June 2009 as per Cabinet Decision No. 59.

2.1.2	In approving the NEC policy framework, Cabinet also approved that all Government‟s

employment creation agencies in the formal and informal sectors (i.e formal employment

creation and job creation through self-employment and small micro enterprises) are to be part of

the NEC framework by law under the Labour Ministry to facilitate a “one stop” quality services

for all unemployed persons in the urban and rural sectors.2

2.1.3	The decision by Cabinet to approve the establishment of NEC was mooted by the following

factors identified in CP (09) 45 of 28th May 2009 as reasons in the poor delivery of government‟s

employment creation services:

	too many government agencies administering employment creation activities (a total of 10);

	too many separate and fragmented employment creation policy framework;

	lethargic responses to employment creation needs due to bureaucratic arrangements and

procedures;

	piecemeal evolution of different employment creation policies over the years without review;

	service delivery mechanisms within national Government agencies incompatible to quickly

respond to very aggressive labour market employment demand in context of local and

economic crisis;

	absence of any national integrated policy framework for employment creation;

	absence of any national “one stop” agency that is cost-effective outside the Civil Service;

	absence of quality management systems to improve the delivery of employment creations

services;

	lack of professionally qualified and trained personnel to manage and undertake employment

creation services;

	absence of a National Qualification framework to benchmark employment skills to

recognised international standards and boost productivity;

	poor governance framework;

	lack of political will in the past to satisfactorily reformed employment creation policies and

services in cost-effective and cost-efficient manner.

1 Paragraph 2.1- CP(10) 154 of 4th June 2010

2 Paragraph 2.2- CP (09) 237 of 30th October 2009

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	6

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.1.4	The Cabinet Paper identified the adverse consequences of continuing with the current inefficient

and fragmented employment creation policies and administrations without any review and

reform. The key consequences included the following:

	increasing unemployment and poverty;

	drain on taxpayers and retard Civil Service Reform and Labour Reform;

	escalating national security risks and increase crimes;

	decreasing overseas employment and remittances;

	decreasing enrolment of students in tertiary institutions;

	decreasing exports and depleting foreign reserves;

	adverse impacts on those employed due to traditional extended families support for the ever

increasing unemployed within families;

	low job satisfaction and low productivity amongst employed workers;

	decreasing FIRCA tax revenue, FNPF contributions and TPAF levies;

	decreasing literacy, employment skills and productivity;

	increasing number of squatter settlements due to house shortages;

	breakdown of families and increasing child poverty, malnutrition and delinquencies; and

	failure to deliver the goals of the Peoples Charter.

2.1.5	The NEC was officially launched by the Minister for Labour, Industrial Relations and

Employment on Friday 4th June, 2010 at the Holiday Inn, Suva.

2.2 Reasons for the audit

2.2.1	The NEC Policy is an outcome of the Government‟s vision to achieve full employment and boost

productivity for all its citizens. Government‟s commitment is reflected in the enactment of the

NEC Decree 2009 that provides the framework for NEC.

2.2.2	Relevant institutions such as the NEC and Employment Creation Services have been

established to implement government‟s national policy pertaining to employment creation

matters in both the formal and informal sectors.

The National Employment Centre regarded as the agency for providing quality „one-stop‟

employment creation services to enhance the employability of all unemployed persons

throughout the Fiji Islands is responsible for facilitating, coordinating and monitoring the

provisions of quality counselling services, life skills training, employment skills training and

entrepreneurship skills training to promote decent and environmentally sound employment,

creation of small businesses and volunteer service to boost productivity amongst unemployed

persons.

2.2.3	This audit is necessary to ascertain the extent and effectiveness of the NEC and the

Employment Creation Services in implementing government‟s vision

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	7

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

3.0 AUDIT	OBJECTIVES,	SCOPE	&

METHODOLOGY

This section of the report describes the objective and scope for this audit. It also

discusses the methodology utilised to gather information for the audit.

3.1 Audit objectives and scope

3.1.1	The objective of the audit is to assess the effectiveness of the actions taken by key agencies to

ensure the provision of quality employment services to the unemployed and the creation of

decent and environmentally sustainable employment by examining:

	the key arrangements for NEC existence and operation;

	the managing of key activities for NEC; and

	the reporting and monitoring of NEC activities.

3.1.2	The audit focused mainly on the Ministry of Labour and Industrial Relations. The remaining

agencies included in the NEC Decree 2009 to be involved in the management of NEC were not

covered in detail as the regulations governing their involvement have yet to be formalised.

3.2 Audit methodology

3.2.1	The audit was conducted using the following evidence gathering techniques.

	Documentary review

Relevant documents relating to NEC were reviewed. The key documents reviewed included

NEC 2009 Decree, Cabinet Memorandums and Decisions, NEC Board meeting minutes

and papers, Standard Operating Procedures, Regulations, Performance Reports and

Organisational Plans.

	Interviews

Interviews were conducted with the following officers of NEC:

	Director

	Senior Administrative Officer

	Executive Officers

	Administrative Officers

	Other

Information and reaffirmations sought and provided through emails and faxes.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	8

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.0 KEY	ARRANGEMENTS	FOR	NEC

EXISTENCE AND OPERATION

This section of the report looks into the key arrangements in place that establishes the

existence and operation of NEC. They entail the legislative requirements, stakeholders’

involvement and the quality management and governance arrangements.

4.0.1	The National Employment Centre primary objective is to boost employment creation and

improving productivity nation-wide through a better governance framework. Its core function is

to consolidate all employment creation agencies into a “one-stop” quality service for all

unemployed.

4.0.2	The establishment of the NEC was approved to be undertaken in three phases. The three

phases outlined below formed part of CP (09) 45 of 28th May 2009 which was approved by

Cabinet as per Cabinet Decision No 59 of 2nd June 2009.

Figure 4.1: The 3 phases of NEC establishment

Consolidation of the reporting

functions of all current

employment creation services

within Government Ministries and

• First phase

Departments under the NEC

Secretariat

Consolidation of all current

employment creation services

in Government specifically

designed to deliver the 7 core

• Second phase

businesses. Appendix 1.1

outline the 7 core businesses.

Designing and implementation of

quality management operating systems

and processes to cost-effectovely

deliver the seven core businesses of the

NEC . Target for NEC's quality

• Third

phase

management systems to be

benchmarked and certified to

international standards.

4.0.3	The following observations were gathered on the arrangements in place with regards to the

existence and operations of NEC.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	9

| Regulation | Brief description |
| --- | --- |
| National Employment Centre (Administration) Regulations 2010 | The Regulation specifies the management and operations of the National Employment Centre. |
| National Employment Centre (Trust Fund) Regulations 2010 | The Regulation specifies the management and operations of the National Employment Centre Trust Fund. |
| National Employment Centre (Formal Employment Service) Regulations 2010 | The Regulation specifies the management and operations of the Formal Employment Service. |
| National Employment Centre (Self Employment Service) Regulations 2010 | The Regulation specifies the management and operations of the Self Employment Service. |
| National Employment Centre (Fiji Volunteer Service) Regulations 2010 | The Regulation specifies the management and operations of the Fiji Volunteer Service. |
| National Employment Centre (Foreign Employment Service) Regulations 2010 | The Regulation specifies the management and operations of the Foreign Employment Service. |
| National Employment Centre (Code of Ethics) Regulations 2010 | The Regulation specifies the Code of Ethics for the National Employment Centre Board, NEC Secretariat, officers of the Employment creation services, any trainee, attaché or volunteer or person employed on a contract of service or contract for service by NEC. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.1 Governing legislation and regulation

4.1.1	As per Cabinet Decision 303/2009, Cabinet approved the establishment of the National

Employment Centre through the enactment of the National Employment Centre Decree No.54.3

4.1.2	Under section 103 of the Decree, the Minister for Labor, Industrial Relations and Employment is

empowered to make regulations giving effect to any provisions of the Decree. The requirement

of regulations is also provided for under sections 89(4), 66(3), 56(3), 59(4), 77(3) and 80(5) of

the Decree.

4.1.3	Our audit found that seven regulations have been developed as required in the Decree above.

The seven regulations were submitted for Cabinet‟s endorsement on the 4th of June 2010 as CP

(10) 1604, CP (10) 1615, CP (10) 1626, CP (10) 1637, CP (10) 1648, CP (10) 1659 and CP (10)

16610. The 7 Regulations were endorsed by Cabinet on 7th June 2010 as per Cabinet Decision

Numbers 204, 205, 206, 207, 208, 209 and 2010. The following table identifies the Regulations

and a brief description of their contents.

Table 4.1: NEC Regulations

4.1.4	Our review of the Cabinet Papers that were submitted by the Ministry on 4th June 2010 found

that three recommendations were made for Cabinet to take note of. The three recommendations

are listed below:

	The salient features of the various Regulations;

3 Paragraph 2.1 - CP (10) 162 of 4th June 2010

4 NEC (Formal Employment Service) Regulations 2010

5 NEC (Self Employment Service) Regulations 2010

6 NEC (Administration) Regulations 2010

7 NEC (Trust Fund) Regulations 2010

8 NEC (Foreign Employment Service) Regulations 2010

9 NEC (Fiji Volunteer) Regulations 2010

10 NEC (Code of Ethics) Regulations 2010

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	10

| NECB Paper Number | Description |
| --- | --- |
| 03/11 | National Employment Centre Administration (Amendment) Regulations 2011 |
| 04/11 | National Employment Centre Formal Employment Service (Amendment) Regulations 2011 |
| 05/11 | National Employment Centre Self Employment Services (Amendment) Regulations 2011 |
| 06/11 | National Employment Centre Foreign Employment Service (Amendment) Regulations 2011 |
| 07/11 | National Employment Centre Fiji Volunteer Service (Amendment) Regulations 2011 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	That the said Regulations have been vetted by the Attorney General‟s Office and to be

gazetted by the Minister for Labour, Industrial Relations and Employment on the powers

vested on him under the NEC Decree 2009; and

	The arrangement between the Attorney-General‟s Office and the Minister of Labour to

inform Cabinet of the said Regulations.

4.1.5	Discussion with the officer responsible revealed that since the establishment of NEC in 2010

these regulations have yet to be gazetted. As at the date11 of the audit no response has been

provided by the Solicitor General‟s (SG‟s) Office despite various follow up made by NEC.

Discussion with the responsible officer also noted that another review of the regulations was

made in 2012 and sent to SG‟s Office for vetting and as to date no response has been provided

by the SG‟s Office. Our review of the NEC Board meeting minutes found the following with

regards to the proposed amendment of the regulations:

	The following papers were submitted to the NEC Board in its meeting on the 29th of

September 2011 on the amendments for each of the regulations.

Table 4.2: Details of Papers deliberated by the NEC Board on 29th of September 2011

The Board was invited to endorse the proposed amendments to the regulations and

endorse the amended version of the regulations.

	NEC Board Paper 01/12 of 17th December 2012 indicated that NEC has incorporated

changes to the Regulations and that the Regulations were in the Solicitor General‟s Office

for vetting.12

4.1.6	Audit followed up with the responsible officer at Solicitor General‟s Office; however no response

was provided from the officer.

4.1.7	Due to the above irregularity the Ministry is using the Decree as the main legislation governing

NEC.

4.1.8	There is a risk that the effective management of NEC is hindered by the lack of appropriate

regulations that gives effect to the provisions of the Decree.

11 As at 22nd May 2014

12 Paragraphs 3.3 to 3.8 of NECB Paper 01/12

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	11

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2 Stakeholders involved with NEC

4.2.1	The National Employment Centre Decree 2009 identifies the various stakeholders/agencies

involved in the management of NEC. The involvements of these stakeholders/agencies play a

critical role in the successful implementation of key requirements under the Decree. The

following diagram summarizes the various stakeholders/agencies identified by the Decree and

their link in managing the operation of NEC.

Figure 4.2:Stakeholders of NEC

NEC Board

(Part 4 Section 17)

NEC Secretariat

(Part 5 Section 24)

Employment Creation Services agencies

Formal Employment

Service

Department of Youth

and Sports

(Part 8 Section 56)

Self-Employment Service

Ministry of National Planning

Ministry of Indigenous Affairs

Ministry of Industry

(Part 9 Section 66)

Fiji Volunteer Service

Public Service

Commission

( Part 10 Section 77)

Foreign Employment

Service

Ministry of Labour

( Part 11 Section 86)

Training institutions

and agencies

(Part 7 Section 47)

Employment providers

(Section 44)

Strategic partners

Fiji Disciplined

Forces

(Part 7 Section 48)

Reputable

International

agencies

(Part 7 Section 49)

4.2.2	The following paragraph discusses observations gathered on the various stakeholders.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	12

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.1 National Employment Centre Board

4.2.1.1 Part 4 of the National Employment Centre Decree 2009 establishes the National Employment

Centre Board.

4.2.1.2 The National Employment Centre Board is to be responsible to the Minister for the

implementation of national policies pertaining to employment creation matters in both the formal

and informal sectors through the National Employment Centre Secretariat and the Employment

Creation Services. 13

4.2.1.3 The functions and powers of the Board are set out under Section 18 of the NEC Decree 2009.

Appendix 1.2 provides details of the functions and powers of the Board.

The following observations were made in respect to the National Employment Centre Board.

Composition of the Board

4.2.1.4 The National Employment Centre Board shall consist of the following members:

(a) Permanent Secretaries responsible for Finance, National Planning, Public Service

Commission, Education, Social Welfare, Business and Commerce and Agriculture and

Lands;

(b) General Manager Native Land Trust Board;

(c) four Divisional Commissioners;

(d) representatives of youths;

(e) representatives of employers;

(f) representatives of workers;

(g) representatives of vocational training institutions;

(h) representatives of civil society organisations; and

(i) other persons. 14

4.2.1.5 According to Part 4 section 17 of the NEC Decree 2009, the Minister appoints the members of

the Board, and in appointing such members the Minister must appoint such persons who, in the

opinion of the Minister, have experience and expertise in the areas covered by the functions of

the Board or in employment creation, small and micro enterprises, vocational training,

entrepreneurship, youth development, industrial, commercial, legal, business or administrative

matters.

4.2.1.6 Section 20 (1) of the NEC Decree states that a member of the Board holds Office for a period

not exceeding 2 years as specified in the instrument of the member‟s appointment but is eligible

for re-appointment.

4.2.1.7 The Invitation to becoming a board member is facilitated through invitation letters sent by the

Minister to the various bodies for their confirmation of membership and appointment of

respective nominees. Once the confirmation is received the board members are then finalised

and gazetted through legal notice.

13 NEC Decree 2009 Part 4 s.16

14 NEC Decree 2009 Part 4 s.17

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	13

| National Employment Centre Board Members |  |  |
| --- | --- | --- |
| Organization | 2010-2012 | 2012-2014 |
| Chairperson |  |  |
| Ps Ministry of Labour | Mr. Taito Waqa | Mr. Taito Waqa |
| Government representatives |  |  |
| PS PSC | Mr. Parmesh Chand | Mr. Parmesh Chand |
| PS Ministry of Finance | Mr. Filimoni Waqabaca | Mr. Filimoni Waqabaca |
| PS Ministry of National Planning | Mr. Pita Wise | Mr. Pita Wise |
| PS Ministry of Education | Dr Brij Lal | Dr Brij Lal |
| Ps Ministry of Social Welfare | Mr. Govind Sami | Mr. Govind Sami |
| Ps Ministry of Agriculture | Mr. Mason Smith | Mr. Ropate Ligairi |
| PS Ministry of Industry & Trade | Mr. Shaheen Ali | Mr. Shaheen Ali |
| Ps Ministry of Lands | Mr. Filimoni Kau | Mr. Filimoni Kau |
| Employers representatives: |  |  |
|  | Ms. Judy VEE-JOY | Mr. Kamlesh Chand |
|  | MS Pawan Sharma | Mr. Noel Tofinga |
| Workers Representatives |  |  |
|  | Ms. Teresa Ali | Ms. Teresa Ali |
|  | Ms. Asena Naulivou | Mr. Nitin Goundar |
| Youth Representatives |  |  |
|  | Mr. Timoci Kacanavesi | Mr. Usaia Cirikiwai |
|  | Ms. Elizabeth Bucknell | Jone Nawaikula |
| Representatives of Vocational Training institutions |  |  |
|  | Mr. Jone Usumate | Mr. Tito Esala |
|  | Mr. Tito Esala | Mr. Kamlesh Prakash |
|  | Mr. Josua Mataika | Dr Kesaia Seniloli |
|  | Dr. Rohit Kishore |  |
| Representatives of Civil Society Organization |  |  |
|  | Mr. Hassan Khan | Mr. Mohammed Hassan Khan |
|  | Mr. Leonard Benjamin Anthony |  |
| The General Manager Native Land Trust Board |  |  |
|  | Mr. Alipate Qetaki | Mr. Alipate Qetaki |
| Four divisional commissioners |  |  |
| Commissioner Central Division |  |  |
| Commissioner Eastern Division |  |  |
| Commissioner Western Division |  |  |
| Commissioner Northern Division |  |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.1.8 The first Board members of NEC were appointed in 2010 to run for a period of two years from

2010 to 2012. The second Board members were appointed in 2012 for the period 2012-2014.

Refer to the table below for the list of the Board members between the period 2010 to 2012

and 2012 to 2014.

Table 4.3: List of Board Members for the period 2010-2012 and 2012-2014

4.2.1.9   The appointment of the NEC Board members for 2010 to 2012 and 2012 to 2014 were

gazetted on the 14th of April 2010 and 9th of November 2012 respectively.

4.2.1.10 Audit gathered that a new set of invitation has been sent to representatives by the Minister for

membership for the period 1 January 2014 to December 2015 which also includes the existing

tenure of current Board members. No explanations were provided by the Ministry on the

anomaly.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	14

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.1.11 There is a risk that the Ministry may not secure the full commitment of the invited members for

the Committee due to the one year appointment as compared to the required term of two

years.

Meeting of the Board

4.1.2.12 The Chairperson must call at least one meeting of the Board every 6 months for the

performance of its functions and the exercise of its powers.15

4.1.2.13 The 1st meeting of the National Employment Centre Board was held on the 21st of May 2010.

Our review of the relevant documents since the date found that the Board has had the

following number of meetings:

Table 4.4: Number of meetings conducted by NEC Board from 2010-2014

Year	Actual number of meetings

2010	2

2011	1

2012	0

2013	1

2014	1 ( to date)

4.1.2.14 The above table indicates that the Board since 2011 have not been having the required

number of meetings as prescribed under the NEC Decree 2009. Discussions with the officer in

charge on the issue found that in 2012 the Board meeting was scheduled for the 17th

December however due to the hurricane warning that was issued to the whole of Fiji the

meeting was cancelled.

4.1.2.15 Non conduct of the meeting as required may result in the delay of any submission that should

be deliberated by the Board.

4.2.2	National Employment Centre Secretariat and Employment Creation

Services agencies

4.2.2.1 The National Employment Centre Secretariat and Employment Creation Services agencies

entail key stakeholders of NEC outlined in the NEC Decree 2009.

4.2.2.2 Employment Creation Services are defined under the NEC Decree 2009 as the Formal

Employment Service, the Self Employment Service, the Fiji Volunteer Service and the Foreign

Employment Service constituted and gazetted under the Decree. The objectives and goals of

the various Employment Creation Services are included under Appendix 1.3.

Establishment of the National Employment Centre Secretariat

4.2.2.3 The object of this Part is to establish the National Employment Centre Secretariat under the

jurisdiction of the Ministry to be responsible to the Board for the facilitation, coordination and

monitoring of national policies pertaining to employment creation matters implemented by the

Employment Creation Services to boost employment opportunities and productivity.16

15 NEC Decree 2009 Part 4 s. 21(1)

16 NEC Decree 2009 Part 5 s. 23

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	15

| Employment Creation Services | Responsible agencies | Relevant section of the Decree |
| --- | --- | --- |
| Formal Employment Service | Department of Youth (National Youth Service Scheme) | Section 56(2) |
| Self-Employment Service | Ministry of National Planning (Integrated Human Resource Development Programme for Employment Promotion) Ministry of Indigenous Affairs (Centre for Appropriate Technology and Development) Ministry of Industry (National Centre for Micro Enterprises Development) | Section 66(2) |
| Fiji Volunteer Service | Public Service Commission (Human Resource Management Division) | Section 77(2) |
| Foreign Employment Service | Ministry of Labour ( Foreign Employment Unit) | Section 86(2) |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.2.4 The Minister shall, by notice in the Gazette establish the National Employment Centre

Secretariat.17 The National Employment Centre Secretariat shall be responsible to the Board for

the overall consolidation, coordination, facilitation and monitoring of the employment creation

policies of Government implemented by the Formal Employment Service, the Self-Employment

Service, the Fiji Volunteer Service and the Foreign Employment Service established or

designated under this Decree.18

4.2.2.5 The National Employment Centre Secretariat was established as the Secretariat of NEC on the

30th off December 2009 through legal notice number 108. The NEC Secretariat functions are

currently administered by the Ministry of Labour, Industrial Relations and Employment.

Establishment and Designation of the Employment Creation Services

4.2.2.6 In approving the NEC policy framework, Cabinet also approved that all Government‟s

employment creation agencies in the formal and informal sectors (i.e formal employment

creation and job creation through self-employment and small micro enterprises) are to be part of

the NEC framework by law under the Labour Ministry to facilitate a “one stop” quality services

for all unemployed persons both in the urban and rural sectors.19

4.2.2.7 The NEC Decree 2009 identifies the employment creation agencies to be responsible for the

administration of the four Employment Creation Services. The Decree further requires that the

Minister by notice in the Gazette designate and establish the Employment Creation Services

operating under various agencies.

Table 4.5: Agencies responsible for the administration of the 4 Employment Creation Services

4.2.2.8 As per the requirement under the NEC Decree the establishment and the designation of the four

employment service were conferred by legal notice on the 30th of December 2009.

4.2.2.9 Our audit gathered that the “FES and the FORES functions are currently administered by the

Ministry of Labour, Industrial Relations and Employment. The FVS is administered by the Public

17 NEC Decree 2009 Part 5 s. 24 (1)

18 NEC Decree 2009 Part 5 s. 24 (2)

19 CP(09) 237 of 30th October 2009 – paragraph 2.2

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	16

Includes National Centre for Small Micro Enterprise Development, Centre of Appropriate Technology and Development, Ministry of Youth and Sports,

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Service Commission (PSC) and the SES is administered by the various different ministries20

which contribute to the development and monitoring and small micro enterprises (SMEs). The

SES is awaiting the implementation of the Cabinet Decision 85 [13/3/2012].”21The Cabinet

Decision in this respect required the following:

	the declaration of the Integrated Human Resource Development Programme for

Employment Promotion (IHRDP) operating under or hosted by the Ministry of Strategic

Planning, National Development and Statistics, the Centre for Appropriate Technology and

Development (CATD), operating under the Ministry of iTaukei Affairs and the National

Centre for Small and Micro-Enterprises Development (NCSMED) operating under the

Ministry of Industry and Trade as Self-Employment Services as per Legal Notice No.112 of

2009.

	The immediate transfer of the Integrated Human Resources Development Programme

(IHRDP) and its relevant resources from the Ministry of Strategic Planning, National

Development and Statistics to the NEC in consultation with the Ministry of Finance, the

Public Service Commission, the Solicitor General‟s Office and the Ministry of Strategic

Planning, National Development and Statistics.

4.2.2.10 Audit also gathered after discussion with responsible officer at the Ministry of Labour that the

current involvement of PSC on FVS is somewhat limited. Audit gathered that PSC had

indicated to NEC that they will only manage volunteers under the retirees‟ category. As such

NEC is facilitating all the qualified graduates and unqualified undergraduate volunteers with

their limited budget.

4.2.2.11 The above findings indicate that the existing challenges faced by NEC may be attributed to the

lack of support from other relevant government agencies.

Staffing of NEC Secretariat and ECS agencies

4.2.2.12 Officers to be employed under the National Employment Centre Secretariat, the Formal

Employment Service, the Self-Employment Service, the Fiji Volunteer Service and the Foreign

Employment Service shall be appointed by the Minister on a performance based contracts.22

4.2.2.13 The Minister shall appoint an appropriate number of officers on performance-based contracts

to effectively manage and operate the National Employment Centre offices throughout the Fiji

Islands and its Secretariat.23.

4.2.2.14 Cabinet Memorandum CP (10) 154 indicated that a total of 85 staffs are required for the NEC

Secretariat and the Employment Creation Services agencies.

4.2.2.15 The organisation structure of NEC which integrate the human resource requirements was also

included in the Cabinet Memorandum CP (10) 154 of 4th June 2010 and was endorsed by

Cabinet on the 7th of June 2010 as per Cabinet Decision No. 200. Refer to Appendix 1.4 for

details of the organisation structure.

20

Ministry of Social Welfare and Poverty Alleviation, Ministry of Agriculture, Department of Forestry, Department of Fisheries and Integrated Human Resources

Development Programme

21 Paragraph 2.4 NEC Board Paper 02/14 of 5th June 2014

22 NEC (Amendment) Decree 2011 Part 5 s. 25 (1)

23 NEC Decree 2009 Part 5 s. 25 (2)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	17

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Our audit however gathered that the required number of staffing for NEC endorsed by Cabinet

has not eventuated. Our review of the NEC Board minutes gathered the following:

	Submission for the NEC project staff was submitted to PSC on Monday 15th of June 2010

and PSC informed that the submission will be based on the approval of funding from the

Ministry of Finance.24

	Eighty-seven position description or the NEC staff were completed and submitted to PSC

on the 15th of June 2010.25 The 87 NEC post advertisements were completed and

submitted to PSC on the 15th of June 2010 for their approval.26

	The Public Service Commission at its meeting on the 28th of June 2010 has not recognised

the request to create 85 project positions for the National Employment Centre. PSC in its

letter to the Ministry dated 28 June 2010 did not approve the 85 project positions. The

Commission agreed that the Ministry use its current staffing strength for the rest of 2010 to

facilitate the operation of NEC. 27

	Given PSC‟s decision to hold the 85 project staff positions a revised streamline and lean

NEC structure has been developed with 40 project staff positions. The new NEC structure

has been reduced by 55% with the main key positions to kick-start implementation. A

revised structure was developed included as Appendix 1.5. On the revised structure, the

only positions already in the NEC are the 12 volunteer data operators. For NEC to be

implemented the Board will have to decide whether to advertise the other positions as well

as the office space required to accommodate these positions.28

	In 2010, the Public Service Commission approved the massive secondment of 45 Ministry

of Labour staff to commission the NEC roll-out from the 9th of August to the 31st of

December, 2010. On 1st January 2011, 35 staff reverted to their own departments while

only 10 continued to roll out NEC. In addition 25 volunteers have been engaged.29

 In March, 2011 NEC submitted a comprehensive proposal to PSC for 28 line positions. PSC

formally relayed their decision against the NEC 2011 staff proposal in their letter dated 5th

July 2011. Instead PSC stated that the Ministry of Labour consider the option of

redeployment of the only 2 support staff from the Employment Relations Tribunal to NEC.

To date, NEC has no line staff.30

 NEC in February received 16 line positions which has been approved by the Public Service

Commission. However, this is a reduction of 9 positions NEC initially requested for.31

4.2.2.16 Audit gathered that the 16 staffs approved by PSC are stationed in seven centres including

Suva, Lautoka, Nadi, Sigatoka, Ba, Savusavu and Labasa. Refer to the following table for

details.

24 Paragraph 2.9- NECB Paper 18/10 of 9th July 2010

25 Paragraph 2.10- NECB Paper 18/10 of 9th July 2010

26 Paragraph 2.11- NECB Paper 18/10 of 9th July 2010

27 Paragraph 2.19- NECB Paper 18/10 of 9th July 2010

28 Paragraph 2.20- NECB Paper 18/10 of 9th July 2010

29 Paragraphs 5.1-5.2- NECB Paper 01/11 of 29th September 2011

30 Paragraph 5.3- NECB Paper 01/11 of 29th September 2011

31 Paragraph 5.2- NECB paper 3/12 of 17th December 2012

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	18

| Position | Number of staffs | Centre |
| --- | --- | --- |
| Director | 1 | HQ |
| Senior Administrative Officer | 1 | HQ |
| Administrative Officers | 3 | Suva Lautoka and Labasa |
| Executive Officers | 3 | Suva |
|  | 1 | Nadi |
|  | 1 | Savusavu |
| Data Operators | 3 | Suva |
|  | 1 | Lautoka |
|  | 1 | Ba |
|  | 1 | Labasa |
| Total | 16 |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 4.6: Details of the existing 16 staffs

Appendix 1.6 details the existing structure of NEC with the above number of staffs.

The staffs signed their contract after approval from the Minister in early October 2012.

4.2.2.17 Audit however gathered that the current staffing provision does not cater for the staffing of the

Foreign Employment Service (FORES). It only caters for NEC Secretariat and the Formal

Employment Services. The commissioning of the FORES is undertaken by seconded staff from

the Policy section of the Ministry.

The staffing of the other Departments of NEC including the Self- Employment Services and the

Fiji Volunteer Services as initially proposed to Cabinet has not eventuated. NEC has taken

over part of the FVS whilst SES is still managed by various government agencies.

4.2.2.18 Audit found that the limited number of staff for NEC currently under the Ministry of Labour has

greatly affected its operations in the centres. Examples of the centres are discussed below:

Example 1: Western Division

The Centre has two data operators to enter the data for the four district office with one Employment

Officer and one Manager to oversee the Division.

Example 2: Central Eastern

The Centre has 3 Data Operators to enter data of 12,806 clients with 2 employment officers and one

Manager to supervise Central Eastern and simultaneously oversee the overall NEC operation which is

being carried out by the Senior Administrative Officer.

4.2.2.19 Audit found that a Board Paper submitted to the NEC Board in its recent meeting32 made

recommendations for the Board to endorse the funding of re-grading and recruitment of

graduate volunteers to effectively implement the NEC Decree 2009.

4.2.2.20 The limitation in staffing for NEC is detrimental to the efficiency and effectiveness of the

Centre‟s operation.

32 5th June 2014

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	19

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.3 Strategic partners

4.2.3.1 The National Employment Centre shall secure strategic partnerships with vocational training or

other training institutions or training consultants for the purposes of reviewing current offerings

for life skills training, employment skills, entrepreneurship skills and foreign employment training

and delivering modern and progressive life skills and employment skills training packages to the

Employment Creation Services as competitive costs on user pay basis.33

4.2.3.2 The National Employment Centre shall secure strategic partnerships with the disciplined forces

to deliver relevant life skills training offerings to the Employment Creation Services.34

4.2.3.3 The National Employment Centre shall secure strategic partnerships with appropriate

international training institutions and development agencies for the purposes of acquiring

experts and training consultants to build the capacity and capability of the National Employment

Centre and the Employment Creation Services.35

The following summarises the engagement of the various strategic partners by NEC.

Training institutions and agencies

4.2.3.4 The last engagement with the training institutions was in 2012 with a number of institutions for

the provision of employment skills training. The list of institution was not provided by the Ministry

during the examination. From 2013 until mid-2014 no training institution was engaged as there

were delays in the tender process.

Discipline Forces

4.2.3.5 According to NEC Secretariat they have not engaged the Discipline forces. No explanations

were provided for the non-engagement.

Reputable International agencies

4.2.3.6 Audit noted that there is no process required for the engagement of any international agencies

or organisations as long as Fiji is a member country and if they are willing to assist either

technically or financially, NEC would be willing to establish partnership with them.

Discussion with the officer in charge revealed that NEC has had only one international agency

that has partnered with NEC. NEC was able to engage International Labour Organisation (ILO)

because of its membership within the organisation.

4.2.3.7 The partnership with ILO has enabled Fiji to seek its assistance both technically and financially

from the organisation. With the funds given to NEC by ILO the Centre was able to implement

the Cash for Work Plus Project (CFWP+).

4.2.3.8 According to NEC Secretariat the Cash-for-Work is a short-term intervention used by the

humanitarian assistance organizations such as (ILO) to provide temporary employment in public

projects (such as repairing roads, clearing debris or re-building infrastructure) to the most

vulnerable segments of a population. The assistance provided through ILO is mostly common in

33 NEC Decree 2009 Part 7 s 47

34 NEC Decree 2009 Part 7 s 48

35 NEC Decree 2009 Part 7 s 49

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	20

NEC Decree 2009 Part 9 s 69(1)

NEC Decree 2009 Part 10 s 89(1)

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

food insecure, disaster-affected or post-conflict environments. The CFWP+ project were in two

folds;

	Manpower Assistance provided through NEC Volunteers

	Implementation of Business Venture(s) for Families Affected

Under the manpower assistance NEC provided NEC volunteers, and ILO to supplied sets of

basic carpentry tools for the NEC skilled unemployed persons to provide manpower assistance

in constructing new homes and rehabilitate affected families caused by the natural disasters.

The project was also intended for the volunteers to gain the technical skill where they are able

kick start their own business for self-employment.

Under the business venture program NEC also provided the Volunteers and ILO supplied the

NEC volunteers with pineapple plantlets, copra drier shed and tools where they are able to plant

and harvest and start their own farming business.

4.2.3.9 For the manpower assistance provided, a Memorandum of Understanding (MOU) was signed

on the 12th April 2013 between the respective Ministries; the Ministry of Labour, IR &

Employment & Ministry of Provincial Development and Natural Disaster Management

(Commissioner Northern Office).

4.2.3.10The lack of engagement with strategic partners may result in the Centre‟s inability to secure

potential assistance that can be offered through the partnership.

4.2.4 Employment providers

4.2.4.1 An employer who employs more than 50 workers must engage suitably qualified unemployed

persons as attachés or volunteers on a ratio of at least 5% of the total number of workers

employed by the employer. 36

4.2.4.2 A Formal Employment Service designated and established under section 56 must arrange with

employers or employers‟ organisations to provide quality workplace attachments for

unemployed persons enrolled under the Service.37 A Self Employment Service designated and

established under section 66 must arrange with employers‟ organisations or small business

employers to provide quality business attachments or business incubator services for

unemployed persons and retirees enrolled under the Service.38

The Fiji Volunteer Service designated and established under section 77 may arrange with

employers‟ organisations or employers or civil society organisations or regional agencies or

international agencies or other bodies to provide appropriate volunteer assignments for

unemployed persons and retirees under the Service.39 The Foreign Employment Service

designated and established under section 86 must arrange and implement quality re-departure

training to effectively orientate persons successfully recruited to commence foreign employment

contracts.40

36 NEC Decree 2009 Part 7 s.44

37 NEC Decree 2009 Part 8 s 59(1)

38

39 NEC Decree 2009 Part 10 s 80(1)

40

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	21

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.4.3 Our audit gathered that whilst the requirement under the Decree is mandatory for employers

employing more than 50 workers to engage volunteers and attaché, practicality of its application

is somewhat difficult.

Discussion with officers in charge at NEC Secretariat revealed that the current approach taken

by the Secretariat is that they identify the employers who employ more than 5 percent first

before they can liaise with them via email or phone to check if they are interested in taking in

volunteers and attaché‟. Refer to Figure 4.3 below for the process that is undertaken by NEC.

Figure 4.3: NEC partnership engagement process

1	2

3

awareness                     	MOUcirculated

Start

1

Identify

organisation that

want to sign MOU

NEC

N

4	5	6	7

Signing of MOU

Store the

copy of

MOU (S)

Extract

name from

database

Exit

1] Organizations are identified that would have the potential to sign MOU with NEC.

[2] Consult with relevant organization to formalize partnership between parties. Conduct NEC awareness to the relevant

stakeholder.

[3] MOU is circulated to relevant stakeholder for their verification and endorsed. If employer agrees to sign proceed to step

4.If not, the process is terminated and proceed to step 7. Signing of MOU within 7 working days from date of identification.

[4] Once signed, one copy is dispatched to the employer, one to HQ (AA) and one to be kept in district office.

[5] Update weekly report(refer to weekly report procedure)

4.2.4.4 The NEC Secretariat has drafted a SOP as a guide for the NEC staff prior to any engagement of

the employment providers. According to the NEC SOP prior to any engagement of any NEC

employer they are required to sign memorandum of understanding to ensure establishment of

agreements and arrangements.

4.2.4.5 The partnership arrangements are made via agreements and are signed by the Partnership

involved between the government through NEC and the employment providers.

4.2.4.6 Audit gathered that since NEC‟s inception in 2010 it has managed to sign 389 MOUs with the

employment providers. Refer to the following table for details.

Table 4.7: Number of MOUs signed with employment providers

Year	Number of MOU

2010	0

2011	139

2012	87

2013	133

2014	30

Total	389

4.2.4.7 The number of MOU signed by employers is encouraging and indicates willingness from various

employers to support the programme.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	22

| Section of Decree | Employment Creation Services |
| --- | --- |
| 62 | Formal Employment Services |
| 72 | Self-Employment Services |
| 82 | Fiji Volunteer Service |
| 92 | Foreign Employment Services |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.4.8 There is every potential for the number to considerably increase provided if the requirement of

the Decree is complied with.

4.3 Quality management and governance systems

4.3.1	The operating systems and procedures of the National Employment Centre must comply with

and be certified to the ISO 9001 quality management standards.41 Subject to subsection 1 the

National Employment Centre Secretariat must design, develop and implement a quality

competency- based skills training package for its staffs to ensure that they are competent to

manage the ISO certified systems and processes to the required customer service quality

standards.42

4.3.2	The governance systems of the National Employment Centre must comply with the Fiji Business

Excellence standards and the social responsibility guidelines specified under the ISO 26000

standards.43 The National Employment Centre Secretariat must design, develop and implement

a value-based skills training package for its entire staff to ensure that the internalise the Fiji

Business Excellence and social responsibility values and exhibit social responsibility behaviours

in accordance with the spirit of business excellence and ISO 26000 standards.44

4.3.3	The NEC Decree 2009 also provides the above requirements for the four Employment Creation

Services. The specific sections of the Decree are outlined below:

Table 4.8: Sections of the NEC Decree covering quality management and governance system

4.3.4	Audit found that the NEC (Administrative) Regulation awaiting formalisation provide

requirements on quality management and governance systems. The regulation specifies the

officer responsible to ensure that quality management standards are complied with and that

adequate governance system arrangements are in place.

In addition the regulations developed for the various Employment Creation Services also outline

requirements pertaining to quality management and governance system in respect to the

management of various Services.

4.3.5	Our review gathered that all regulations and the Ministry of Labour‟s Standard Operating

Procedures (SOP) have integrated the requirements of both ISO 9001 quality standards, ISO

26000 standards and the Fiji Business Excellence standards.

4.3.6	In addition, the audit also found that the quality based and value based skills training package

have been designed, developed and are currently being implemented. Discussion with

concerned officer gathered that all officers under NEC have completed training for both quality

based and value based skills.

41 NEC Decree s 26(1)

42 NEC Decree s 26(2)

43 NEC Decree s 26(3)

44 NEC Decree s 26(4)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	23

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

However, our review of the training package developed for the standards found that the

package is not broken down into modules considering the magnitude of the requirements in the

standards.

4.3.7	A review of NEC management systems and process are done all year around while a

collectively formal review is done annually.

4.3.8	There is a risk that the training may not be adding the expected value to staffs as the training

package developed may not integrate the full requirements of the standards. In addition, the

effective application of the quality management and governance system may be hindered by the

delay in the formalisation of the relevant regulations.

RECOMMENDATIONS

Ministry of Labour (National Employment Centre and NEC Board)

NEC

NEC should:

	ensure that the term of appointment for NEC Board members outlined in the NEC Decree is complied with.

	use the powers provided under the 2013 Constitution through the Ministry‟s Permanent Secretary to recruit

volunteers/attachés‟ for NEC once funds are available through savings from other votes or funds received

through the NEC Trust account.

	work towards securing better relationship with its strategic partners.

	through its awareness program make every effort to inform employers of their obligation under the NEC

Decree to employ volunteers and attaché‟s under NEC.

	ensure that the quality based and value based skills training package are broken down into modules such

that the requirements of the ISO standards are thoroughly covered.

NEC Board

	The Board should ensure that the number of meetings outlined in the NEC Decree is complied with.

Solicitor General’s Office

	The SG‟s Office should ensure that the vetting of the 7 Regulations for NEC indicated in this report is

conducted and that the Regulations are gazetted to allow NEC to effectively carry out its operations. An

update should be provided by the Office to the Ministry so that the NEC Board is updated on the subject in its

meeting.

Ministry of Strategic Planning, National Development and Statistics

	The Ministry should make every effort to ensure that the requirements of Cabinet Decision No. 85 of 13th of

March 2012 are implemented.

	The Ministry should make every effort to consult Ministry of Labour and other relevant parties identified in the

Cabinet Decision for the immediate transfer of IHRDP to NEC.

Ministry of iTaukei Affairs

	The Ministry should make every effort to ensure that the requirements of Cabinet Decision No. 85 of 13th of

March 2012 are implemented.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	24

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Ministry of Industry and Trade

	The Ministry should make every effort to ensure that the requirements of Cabinet Decision No. 85 of 13th of

March 2012 are implemented.

Management Comments

Ministry of Labour (National Employment Centre & NEC Board)

	The SG’s Office had completed vetting of the seven (7) Regulations of the NEC Decree 2009 and at present,

our legal team is finalizing the Regulations for Gazetting.

	The NEC Secretariat is complying with the NEC Decree 2009 in related to the appointment of the NEC

Board.

	The NEC will conduct minimum 2 NEC Board meetings this year 2014.

	The Ministry and NEC had been recruiting NEC Volunteers and Attaches since 2010 through its budgetary

allocation and to date Ministry had recruited 149 and 100% had been absorbed into inline position or other

organization.

	The PS MLIRE is talking with other relevant agencies PS on the way forward of this Cabinet Decision 85.

	The NEC is liaising with Ministry of i’Taukei related to the Cabinet Decision No. 85. We had presented to

the NLTB Senior Management on the NEC Framework. We will meet with General Manager again this

quarter on MOU.

	The NEC had been promoting this public and private partnership since inception and will continue to

pursue this strategy because it is a legal requirement and will also depend on the resource on the ground.

	The reviewing of SOPs is a continuing process and as we roll out by implementing the PDCA model.

Solicitor General’s Office

No comments received.

Ministry of i-Taukei Affairs

No comments received.

Ministry of Industry and Trade

No comments received.

Ministry of Strategic Planning, National Development and Statistics

	We note the findings and recommendations of your Draft Management Letter that our Ministry needs to

consult with all relevant parties and comply with Cabinet Decision No. 85 of 13th March 2012. In my

opinion, these findings do not take account of developments that have taken place after the Cabinet

Decision, which would have been explained during the conduct of this performance audit. In particular that

the findings fail to properly consider:

a)	The approval of the Prime Minister on 16th April, 2012 to revisit the Cabinet Decision in question

following a review of the National employment Centre(NEC);

b)	Subsequent discussions and consultations held with the Minister for Labour, Industrial Relations &

Employment and Minister for Agriculture and Minister for Rural & Maritime Development and

National Disaster Management where it was agreed that line Ministries would continue to implement

their employment programmes and submit regular reports to the NEC; and

c)  Updates provided to the Secretary to Cabinet on this issue on 17th December 2013.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	25

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Further OAG Comments

Ministry of Labour

The issue raised on the Board meeting concerns the term of the meeting. The NEC Decree requires a term of 2

years; however, the invitations sent out for new members are with effect from 2014 (the existing term for current

members) when in fact should have been with effect from January 2015.

Ministry of Strategic Planning, National Development and Statistics

In following up on the comments and documentation provided by the MSPNDS, audit noted the following:

	The approval of the Prime Minister endorsed on 16/4 (as no year was stated, it is assumed that year is 2011 following

on from the date of submission of the Minute Brief referenced NPO 03/03/49 dated 11/4/11) is in respect to the “Review

of the Role of the National Employment Centre”, and has no relevance to Cabinet Decision No. 85 of 13/3/12, a

decision which was made 11 months later. The purpose of the Minute Brief was to provide an update on the activities of

the NEC since it commenced operation in April 2010; provide an assessment of its effectiveness of the role of the NEC

in relation to registration and training of unemployed persons as stipulated in the NEC Decree; and to provide

recommendations for the better coordination of government‟s efforts in the creation of employment opportunities. The

Prime Minister agreed with the 4 recommendations proffered, and directed that the views of the Labour Ministry be

obtained and relevant changes be made to the entity. The 4 recommendations proffered for the PM‟s consideration and

decision include:

(i)	to take note of the status of NEC particularly the number of unemployed persons who are trained and on work

attachment;

(ii)	that the Ministry of Labour to review the structure and role of NEC with a view to reducing the size of NEC

establishment and focusing on targeted demand driven training;

(iii)	that cost recovery measures to be considered to recover cost incurred on training of the registered unemployed

persons ; and

(iv) that the NEC Decree to be reviewed through the consultative process taking into account the need to provide

targeted training and experience in countries with similar arrangement.

	In its follow up with the MSPNDS, audit was not provided with relevant documentation to support consultations

undertaken by the MSPNDS with the Minister of Labour, Industrial Relations & Employment, and the Minister for Rural

and Maritime Development & National Disaster Management and reflecting consensus that line Ministries would

continue to implement their employment programmes and submit regular reports to the NEC as alluded to in the

comments provided by the MSPNDS. It was confirmed at the exit meeting with the NEC on 18/11/14 that the Ministry

does not have any documentation regarding this matter.

	In addition, no documentation was provided by the MSPNDS to support outcomes of discussions raised on the issue at

the Prime Minister‟s forum on “Project Implementation Programme for 2014” as disclosed to the Secretary of

Cabinet via memorandum referenced NPO 03/03/49 of 17/12/13.

	Audit also followed up with the Cabinet Office regarding status or outcomes of decisions with respect to

correspondences by the MSPNDS to the Prime Minister via Minute Brief referenced NPO 03/03/49 of 13/04/12

regarding “Cabinet Decision on the Transfer of Integrated Human Resource Development Programme to

National Employment Centre” and subsequent Memorandum referenced NPO 03/03/49 of 17/12/13 regarding

“Implementation of Cabinet Decision 85 of 2012”. The Cabinet Office has no records of the correspondences alluded

to being submitted for its consideration nor any subsequent Cabinet Decision provided on the matter.

Audit is also of the view that any concerns on NEC operations should have been raised to the NEC Board during the Board‟s

meeting as it is the governing authority for NEC. Also since the Cabinet Memorandum resulting in the Cabinet Decision 85

was submitted to Cabinet via the NEC Board any subsequent changes to the decision should have also been channelled

through the NEC Board for Cabinet‟s endorsement.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	26

| Process | Description |
| --- | --- |
| Start 1. Interview client 3. Insufficient document to meet registration N requirement 2. Verify Qualification N 4. Do not meet legal requirement Y 5. Client return 6. Register Client with complete documents 7. Enter Master Registration log 8. Enter Database 9. Filing End | [1] Verify if customer fits description of an unemployed person; (school leavers, unemployed apprentices, graduates, attachés, volunteer, retirees & part time workers), check on clients ages(should be 15 years and above)and ensure if client has required documents. [2] Verify if the clients qualifies to register or not. If qualifies proceed to step 6 [3] Clarify if client has all required documents, if requirements are not met, proceed to step 5 [4]If client is less than 15 years of age or is a student he/she is declined (advise kindly & politely) [5]Advice client to return with complete documents then proceed to step 6. [6] Registration-advise the client on NEC processes fill in registration form (NEC-4-RF), advice on the repayments. Advise client to follow-up on their status and inform NEC of change of contact detail. [7] Enter registration in the master registration log. Issue confirmation letter with NEC ID .Sign MOU with clients for repayment ( NEC-1-RMOU) [8] Data entry is done. [9] Create client file. File away the form. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.0 MANAGING KEY ACTIVITIES OF NEC

This section of the report looks into the management of key activities of the National

Employment Centre. In essence it discusses the day to day activities conducted by NEC

with indications of the performances of these activities since NEC’s establishment.

5.0.1	The National Employment Centre Decree 2009 outlines various requirements covering the

management of key activities of NEC on a day to day basis. These activities are undertaken by

the Centre and entail key component of the Centre‟s performance.

5.0.2	NEC also has in place its own Standard Operating Procedure (SOP) which provides a guideline

for its staffs to manage these activities.

5.1 Registration of the unemployed

5.1.1	The object of this part is to describe the conditions of engagement of the National Employment

Centre in regards to compulsory registration, privileges and rights of unemployed persons,

attaches and volunteers enrolled in the activities of any of the Employment Creation Services

and how they are conducted including the employers‟ social responsibilities.45 Any person who

is unemployed or on part-time employment and at least 15 years of age must register with the

National Employment Centre as prescribed.46

5.1.2	The NEC Standard Operating Procedure (SOP) outline the following process in registering

unemployed persons.

Table 5.1: Process of registering unregistered persons

45 NEC Decree s 38

46 NEC Decree s 39(1)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	27

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.1.3	The NEC registration of unemployed persons in the seven centres of the Ministry of Labour

started on 14th of April 2010. As at 31st March 2014 NEC has registered a total of 33,773

unemployed persons. The following table depicts the number of unemployed persons registered

for the period 2010 to 2014.

Table 5.2: Number of unemployed persons registered for the period 2010-2014

Year	Number	of	unemployed	persons

registered

2010	9,549

2011	13,283

2012	3,696

2013	6,225

2014 (March)	1,020

Total	33,773

Source: NEC Board paper 1/14

The number of unemployed persons registered from 2010 to 2013 has exceeded the ACP

target of 2,000 persons per year.

5.1.4	The following observations were noted in regards to the registration process:

	the clients who register with NEC are provided with a registration number which NEC uses

to follow-up on the progress of their registration. However, no identification card is issued to

the unemployed person who has been registered with NEC.

Discussion with the senior officers of NEC revealed that the provision of ID cards for

registered clients is provided in part 5 of the NEC Administration Regulation. However, NEC

indicated that since the NEC (Administration) Regulation has yet to be gazetted the centre

has not complied with the requirement.

	the process flow outlined in the SOP fails to capture the verification and authorization of

registration forms before being entered into the NEC database. Audit noted that the NEC

database has a mandatory field for verification and authorization which needs to be filled to

complete a registration.

Interviews with Customer Service Officers (CSOs) and Data Entry Officers revealed that the

Manager Central/Eastern had verbally authorized them to enter their names in the

verification and authorization section to furnish the requirements of the database and to

successfully enter the registration.

Audit found that the lack of verification and authorization of the registrations led to some

duplicate serial numbers being issued to NEC application form for registration. This

duplication creates confusion for the applicant and NEC CSOs because these unique serial

numbers are used by applicants to follow up on their registrations with NEC.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	28

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.1.5	The non-issuance of ID cards suggests that there exists no formal means of identification for

unemployed persons already registered with NEC which reliably serve as a reference for

identifying NEC registered clients.

5.2 Professional counselling services

5.2.1	The National Employment Centre Secretariat shall facilitate the provision of quality counselling

services to all unemployed persons registered with the National Employment Centre.47

5.2.2	The counselling services under section 46 subsection (1) shall be delivered at the highest level

of professional standards and with confidentiality where relevant to promote the spiritual, mental

and psychological, social, physical and economic well-being of the unemployed person.48

5.2.3	The National Employment Centre Secretariat shall provide quality human resource and aptitude

assessments and referral services for unemployed persons.49

5.2.4	Audit noted that the NEC Secretariat facilitates the provision of quality counselling services to all

unemployed persons registered with the National Employment Centre. This service is part of the

NEC process and it is compulsory for all the NEC clients to undergo.

5.2.5	According to NEC the main objective of the professional counselling is to help the NEC clients

understand and accept themselves as they are, to also encourage and also develop special

abilities and right attitudes within themselves that will assist them. Special attention are given to

those NEC client that are flagged on high risks category.

5.2.6	For the period 2010-2014 the NEC has engaged a total of 18,474 clients in the activity. Refer to

the following table for details.

Table 5.3: Number of clients engaged for professional counselling services by NEC for the period 2010-2014

Year	 Number of professional counselling

2010	 3,825

2011	 9,976

2012	 2,832

2013	 1,284

2014 (March)	 557

Total	 18,474

Source: NEC Board paper 1/14

The NEC SOP provides the process of arranging professional counselling. Refer Figure 5.1

below for details.

47 NEC Decree s 46(1)

48 NEC Decree s 46(2)

49 NEC Decree s 39(3)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	29

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Figure 5.1: Process of arranging professional counseling

Arrange for

venue &

stationeries

Start

1. Extract names

from Database

2. Inform individual

of the schedule

session

3. Logistic

arrangement and

training room setup

4. Verify & collate

attendance

5. Professional

Counseling/Aptitude

Assessment Begins

6. Collect TEF

7. Update

Database

8. File records

END

NEC-4-

AF

NEC-4-

TEF

1] DEO to extract client names from the database especially those that have missed out

on previous sessions. List to be verified by EO and distributed to responsible officers

(DEO/EO) for calling.

2] Clients to be contacted through telephone and other medium (radio, email, newspaper,

TV, etc) of communications.

[3] Logistics to be prepared 3 weeks before training sessions begins. DEO/EO to ensure

that training room is properly and neatly set up every morning. Also ensure that

stationeries and equipment‟s are in order (printed slides, folders, toilet paper, multimedia,

laptop, butcher papers, whiteboard & permanent makers, cello tape, scissors, blue tac

etc). The DEO/EO shall paste signage/directions in the nearby proximity to the venue to

easily locate the venue.

[4] The EO/DEO must be in the training room one hour before the training session

begins. The Clients to sign attendance register (NEC-2-LF) before the session begins.

Ensure names are spelt correctly as it appears in the birth certificate with NEC ID

numbers. Responsible officers (DEO/EO) to vet and verify attendance list.

[5] DEO/EO to ensure that the program executed is within the required timeline of 2

hours per session and to start on time. To ensure clients fill the Training Evaluation Form

(TEF) (NEC-2-TEF) at the end of the session before they leave the training room.

DEO/EOs must be the last one to leave the venue.

[6] Responsible Officer(s) to ensure the safe keeping of TEFs and that the training room

is well organised (clean and tidy) before and after the sessions.

[7]Input data (TEFs) in database and manual register after the training sessions.

[8] File documents in appropriate client folder

( NEC-1-RCF).

5.2.7	Under the NEC Decree 2009 the NEC Secretariat must engage quality counselling services and

must engage professional counsellors registered under the appropriate registration body to

conduct counselling services for the registered unemployed persons50.

5.2.8	Audit gathered that NEC Secretariat has engaged the Kuruleca consultants for its professional

counselling services since 2010. The Kuruleca Consultants according to NEC Secretariat is

recognized by the American Counselling Association. Verification of the consultant‟s

qualification as stated in the curriculum vitae confirmed that the consultant is qualified to provide

the services. However, audit could not locate any certified certificates in the Kuruleca consultant

folder to substantiate its credentials.

5.2.9	Audit also found that the NEC selection or engagement of counsellors are vetted and

scrutinized by the MLIRE Executive Managers and endorsed by the Permanent Secretary.

However no evidence existed to indicate that a criterion is in place governing engagement of

counsellors.

5.2.10 In addition, audit noted from reports submitted by the consultant that NEC needs more proper

planning in the organising and scheduling of counselling sessions. Complaints were received

from the NEC clients confirmed that phone calls were made to them the evening before the

meeting informing them about the counselling session with specified venues and time.

5.2.11 Furthermore, scrutiny of the consultant‟s report revealed that there were sessions that had

exceeded the limit of clients that should attend as per the MOU ranging from 40 to 50 NEC

clients per session.

50 NEC Decree 2009 Part 6 s.27

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	30

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.2.12 Lack of proper planning and monitoring of counselling services can result in the wastage of

government resources. In addition, the non-existence of criteria for selection of counsellors

indicates the lack of transparency in the engagement process.

Furthermore, having consultants to provide counselling outside the requirement of the

agreement may have an effect on the efficient provision of services provided by the consultant.

5.3 Data management and use

5.3.1	The National Employment Centre shall establish and maintain an efficient data management

system on the labour market including the registration of unemployed persons and the supply

and demand of labour in the labour market.51

5.3.2	The existing NEC database was developed specifically for the Centre by a Consultant from

India. The database allows NEC to capture a wide variety of information for individuals wishing

to find employment.

5.3.3	Audit noted that although the NEC database captures a wide range of data, the database has

limited ability to generate some essential and required reports. The following reports are

required by the NEC officers for data analysis purpose but cannot be generated by the NEC

database.

Table 5.4: Reports cannot be generated by the existing NEC database

Report name	 Limitation of the database	 Audit Comment

registration date by age group                	Age is present in the reports but there is

Registration by name by NEC number by

no way of selecting a particular age

group.

NEC officers need to select an age

group for the database to display all

candidates within that age group.

This report cannot be generated from

registration date by postal address by towns/districts  	There is no postal address in the reports

generated                      	Other   contact   information   like   a

the database

Registration by name by NEC number by

secondary phone contact is not

displayed in the reports. NEC officers

need the secondary phone contact

when the primary phone contact is not

reachable

registration date by living arrangement           	Living arrangements is not in any reports

Registration by name by NEC number by

NEC officer need to determine if a

candidate   has   accommodation

arrangements

Registration by name by NEC number by

registration date by driving license number by class

by status by expiry date

No. Reports does not state if clients have

a driving license or details of driving

license

Usually employers request for

candidates with driving license.

registration date by bank name by account number   	Bank name and account number is not

on any reports                   	The bank details are a necessary for

Registration by name by NEC number by

salary payment to the candidate

registration date by FNPF number by age         	FNPF number is not on any reports

registration date by TIN number               	No. TIN number is not on any reports

Registration by name by NEC number by

Registration by name by NEC number by

The FNPF number is necessary for the

candidate just in case they secure

permanent employment.

TIN number for a candidate serves as

an identification

Registration by name by NEC number by

registration date by passport number by expiry date

by country by work permit by PR date

Passport number and its details is not on

any reports

The Passport details is essential for

candidates seeking foreign

employment

in any reports                    	Some employers prefer candidate who

Registration by name by NEC number by

registration  date  by  degree  of  literacy

(read/write/spoken/English/arithmetic/Braille/Sign

language/etc.)

Degree or literacy levels is not generated

have medium to higher literacy level

thus it becomes crucial for NEC

officers to have this report

Registration by name by NEC number by

registration date by employment status

No. Employment status is not generated

in any reports

Employment status is an important

information which NEC staff need in

other to allocate them to an

51

employment opportunity

Registration by name by NEC number by  Secondary school details is not captured  Secondary school details is an

NEC Decree 2009 Part 7 s. 51(1)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	31

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

registration date by secondary by school by year –

FJC/FSLC/FSFE

in any reports                    important information which NEC staff

need in other to allocate them to an

employment opportunity

Registration by name by NEC number by

registration date by work experience by employer by

occupation by duration

Work experience is not generated into

any reports

NEC staffs need the work experience

to be in reports or current work details

so that they will not have to send their

registration date by existing employment skills      	Existing	employment	skills

generated into any reports            	Existing employment skills status is an

contact details to employers if they

have an employment

Registration by name by NEC number by	is not

important information which NEC staff

need in other to allocate them to an

employment opportunity

Registration by name by NEC number by

registration date by registration feedback by area

needing improvement

Registration by name by NEC number by

registration date by registration feedback by

recommendation to others

No. Feedback statistics does not show

any feedback on improvement

Feedback statistics does not show any

feedback on recommendation to others

This will allow NEC to gauge there

service delivery

This will allow NEC to gauge there

service delivery

registration date by NEC Registration officer       	Officer name is not generated into reports

Registration by name by NEC number by

This will allow to monitor the

productivity of an officer

Registration by name by NEC number by

registration date by NEC Verification officer

Verification  Officer  name  is  not

generated into reports

This will prove the accountability

component for the NEC officer

registration date by NEC Authorizing Manager      	Authorizing  Manager  is  not  generated

into reports                     	This   will   prove   the   accountability

Registration by name by NEC number by

component for the NEC officer

5.3.4	Audit also found that the database cannot generate a NEC Registration number automatically.

As a result NEC officers have to follow the excel based register and assign the NEC registration

number manually.

Similarly, while interviewing data entry officers, audit found that the database does not prompt

the data entry officer with a warning when a double entry for a registration number occurs. This

indicates that the database does not assign primary key function to the registration details

unlike the normal databases.

There is also difficulty to add the applicant‟s passport size photograph into the database.

5.3.5	Discussion with the senior administrative officer found that the NEC database was a tailor made

database which was designed to suit the basic functions of NEC at the time of its inception

2010. The NEC database has since not been upgraded.

5.3.6	An out dated database impairs the entities ability to achieve its intended objective. It can also

impair critical decision making for NEC officers by not providing adequate data analysis and

modelled reports.

5.4 Public awareness campaign

5.4.1	The National Employment Centre shall provide quality advice, media marketing, annual expo

shows and awareness programmes and training to employers and the general public on the

development role of the National Employment Centre, including the legal requirements and

incentives associated with enrolment of unemployed persons at the Centre and workplace

attachments with the Employment Creation Services.52

5.4.2	Audit found that public awareness is currently conducted by the Ministry to inform the public on

the role of the National employment Centre and the benefits of registering with NEC, how to

52 NEC Decree Part 7 s 54

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	32

NEC Decree 2009 Part 8 s 57(3)

NEC Decree 2009 Part 8 s 67(1)

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

register with NEC and to inform the employers on their statutory obligation as part of the NEC

Decree.

5.4.3	Public awareness is mainly focused on a number of groups including non-governmental

organisations, government departments, religious groups, private and corporate organisations,

secondary schools and tertiary institutions. Our review of the Annual Corporate Plan of the

Ministry over the past four years found that a total of 70 awareness campaigns were targeted to

be conducted by NEC yearly. No breakdown was however provided as to the number of

awareness to be conducted for each of the target groups.

5.4.4	It was gathered that the awareness campaigns are done throughout the year upon request of

any particular stakeholder group instead of NEC taking the initiative to reach out to the various

stakeholders. The Centre conducts this awareness through presentations, emails and through

phone conversations.

5.4.5	For the past four years from 2010 – 2013, NEC has conducted a total of 457 public awareness

campaigns throughout the country. NEC has managed to surpass their targeted number of

awareness for every year except for 2012 where there able to only conduct a total of fifty three

awareness.

While there were 457 awareness conducted over the four year period, audit noted that no

awareness was conducted in tertiary institution in Fiji.

5.4.6	Audit was informed that due to lack of funds and human resources, NEC was not able to meet

their 2012 awareness target and conduct awareness for tertiary institutions.

5.4.7	There is every potential for NEC to increase the awareness of its operations if the Centre is

well-resourced.

5.5 Life Skills Training (LST) – NEC Secretariat

5.5.1	A Formal Employment Service designated and established under section 56 must provide a

quality life skills training course compatible with the needs of unemployed persons and

recognised under the national qualification framework.53 A life skills training course provided

under subsection (1) must be designed and conducted as prescribed with the aim of promoting

the holistic development of unemployed persons enabling them to become disciplined and

productive workers.54 A trainer conducting any part or the whole of the employment skills

training course must be an accredited trainer.55

5.5.2	A Self-Employment Service designated and established under section 66 must provide a quality

life skills training course compatible with the needs of unemployed persons and retirees and

recognised under the national qualification framework.56 A life skills training course provided

under the subsection (1) must be designed and conducted as prescribed with the aim of

promoting the holistic development of unemployed persons and retirees enabling them to

53 NEC Decree 2009 Part 8 s 57(1)

54 NEC Decree 2009 Part 8 s 57(2)

55

56

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	33

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

become disciplined and productive workers and entrepreneurs.57 A trainer conducting any part

or the hole of the employment skills training course must be an accredited trainer.58

5.5.3	The Fiji Volunteer Service designated and established under section 77 must provide a quality

life skills training course compatible with the needs of unemployed persons and retirees and

recognised under the national qualification framework.59 A life skills training course provided

under subsection (1) must be designed and conducted as prescribed with the aim of promoting

the holistic development of unemployed persons and retirees enabling them to become

disciplined and productive volunteers.60 A trainer conducting any part or the hole of the

employment skills training course must be an accredited trainer.61

5.5.4	The Foreign Employment Service designated and established under section 86 must provide a

quality life skills training course compatible with the overseas employment needs of unemployed

persons and retirees and recognised under the national qualification framework.62 A life skills

training course provided under subsection (1) must be designed and conducted as prescribed

with the aim of promoting the holistic development of unemployed persons and retirees enabling

them to become disciplined and productive foreign employment workers.63 A trainer conducting

any part or the hole of the employment skills training course must be an accredited trainer.64

5.5.5	The Life Skills Training is a multi-component proactive curriculum addressing social,

psychological, cognitive, and attitudinal factors with the aim of promoting the holistic

development of unemployed persons enabling them to become disciplined and productive

workers.

The rationalization of this training is to allow clients to understand the universal values, good

faith and social justice principles that one should understand and apply.	The LST is a

competency value based one week program.

5.5.6	The life skill training package includes 11 units outlined as follows:

i.	the study and application of core values in real life;

ii.	NEWSTART programme

iii.	religion and cross-cultural matters;

iv.	fundamental principles and rights;

v.	prevention of or limiting the spread of HIV/AIDS and drug abuse;

vi.	first aid skills;

vii.	adolescent training;

viii.	financial literacy training;

ix.	technological literacy training; and

x.	a disciplined life style, teamwork and survival skills.

5.5.7	NEC currently conducts life skills training for FES, FORES and FVS. The following table

illustrates the process involved in arranging clients for life skills training.

57

58

59

60

61

62

63

64

NEC Decree 2009 Part 8 s 67(2)

NEC Decree 2009 Part 8 s 67(3)

NEC Decree 2009 Part 8 s 78(1)

NEC Decree 2009 Part 8 s 78(2)

NEC Decree 2009 Part 11 s 78(3)

NEC Decree 2009 Part 11 s 87(1)

NEC Decree 2009 Part 11 s 87(2)

NEC Decree 2009 Part 11 s 87(3)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	34

| Process | Description |
| --- | --- |
| Start Extract names [1] Setup room [2] NEC-4-AL Conduct LST Training Take attendance & [3] Verify [4] Forward attendance to AA/EO/Managers for Certificates [5] NEC-4- Fill & collect TEF TEF [6] Present certificates to clients [7] Collate & submit weekly report [8] END | [1] DEO/EO to extract names from Professional Counselling & Aptitude Assessment List and also include clients that have missed out on previous sessions. Call and inform clients on training venue, date and time. [2]Responsible officer to set up training room one hour prior to start of training, including organisation of stationeries and equipments (Workbook, Training Manual, Toilet paper, multimedia, laptop, butcher papers, whiteboard & permanent makers, cello tape, scissors, blue tac). [3] Before commencement of training, Trainer to announce housekeeping matters to participants. LST must be conducted within 6 hours per day (30 hours per week), excluding breaks. Certificates will only be awarded to participants attending the full 30 hours. [4] Clients to sign attendance register daily. Ensure name‟s are spelt correctly as it appears in the birth certificate with NEC ID numbers. [5] Trainer to verify & type attendance list and submit to EO/Managers for printing of certificates. [6] Ensure clients fill the TEF/MOU and collect forms at the end of the session before they leave the training room [7]Present LST certificates to clients at the end of the session. Input data (TEFs) in database and update manual register after the training session. [8] DEO to collate and submit Weekly Report (WR) to EO. [8a] DEO to update database after forwarding the WR to EO. EO to verify and submit WR to Manager. Manager to add value and submit to AA for compilation. [9] File documents in appropriate folder. |

|  | File records/ documents [9] |
| --- | --- |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 5.5: Process of arranging clients for the training

5.5.8	For the period 2010 to 2014 NEC has engaged 10,216 clients through this program. Refer to

the table 5.6 for details.

Table 5.6: Clients engaged for the LST program for the period 2010-2014

Year	Number of unemployed persons

2010	2,351

2011	5,431

2012	1,333

2013	1,014

2014 (March)	87

Total	10,216

Source: NEC Board paper 1/14

5.5.9	The qualification of this training milestone is reflected in the behavioural change of clients

absorbed into work attachments.

5.5.10 Audit noted that NEC has only managed to achieve the targeted number of 2,500 annually in

2011. Discussions with senior officers revealed that the Centre has not been able to conduct the

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	35

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

LST regularly throughout all the centres. The unavailability of a suitable venue has been a major

hindrance since NEC has to identify and book the venue in advance.

5.5.11 Audit also established that curriculum for the life skills training was developed as part of the

Labour Reform in 2010. The main objective was that a value based training be developed and

train the unemployed before employment so that the sustainability of employment is stable. The

training was aimed at providing a basic nurturing program for unemployed candidates. The Life

Skills Training package has not been reviewed since 2010.

In addition audit found that all the LST units offered are not well suited for the Foreign

Employment Services in view of the fact that clients under this Service will be engaged abroad.

5.5.12 There is a risk that the use of the out-dated training program may not achieve the intended

objective and thus will be unsuccessful in adding value.

5.6 Employment Skills Training (EST)

5.6.1	A Formal Employment Service designated and established under section 56 must provide

quality employment skills training course compatible with the needs of unemployed persons and

recognized under the national qualification framework.65 An employment skills training course

provided under subsection (1) must be designed and conducted as prescribed with the aim of

developing generic and specific employment knowledge and skills that are relevant to the

demand of the employment market to facilitate the absorption of unemployed persons into

formal employment.66 A trainer conducting any part or the whole of the employment skills

training course must be an accredited trainer.67

5.6.2	A Fiji Volunteer Service designated and established under section 77 must provide quality

employment skills training course compatible with the needs of unemployed persons and

retirees recognized under the national qualification framework.68 An employment skills training

course provided under subsection (1) must be designed and conducted as prescribed with the

aim of developing generic and specific employment knowledge and skills that are relevant to the

needs of volunteers and the demands of the project they are assigned to.69 A trainer conducting

any part or the whole of the employment skills training course must be an accredited trainer.70

5.6.3	A Foreign Employment Service designated and established under section 56 must provide

quality employment skills training course compatible with the foreign employment needs of

unemployed persons and retirees and recognized under the national qualification framework.71

An employment skills training course provided under subsection (1) must be designed and

conducted as prescribed with the aim of developing generic and specific employment

knowledge and skills that are relevant to the needs demand of unemployed persons and

retirees and the demands of the targeted foreign employment market.72 A trainer conducting

any part or the whole of the employment skills training course must be an accredited trainer.73

65

66

67

68

69

70

71

72

73

NEC Decree 2009 Part 8 s 58(1)

NEC Decree 2009 Part 8 s 58(2)

NEC Decree 2009 Part 8 s 58(3)

NEC Decree 2009 Part 10 s 59(1)

NEC Decree 2009 Part 10 s 59(2)

NEC Decree 2009 Part 10s 59(3)

NEC Decree 2009 Part 11 s 88(1)

NEC Decree 2009 Part 11 s 88(2)

NEC Decree 2009 Part 11 s 88(3)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	36

| PROCESS | DESCRIPTIONS |
| --- | --- |
| Start Confirm dates, venues & EST Trainer, sort names [1] Extract name and verify [2] Sort names in alphabetical order & place 35 in each class [3] Inform & confirm clients of EST [4] Finalize class list and sent to trainer [5] EST training begins and daily attendance registered [6] N Y EST Certificates provided to clients [7] Training provider provides EST report [8] End | 1] Confirm dates, venues & EST trainer. Extract names from Database (DB), customer services book and LST attendance list by year [2] DEO/EO verify if client have completed C/A & LST and match clients Aptitude Assessment and enlist them for EST. [3] Sort names in alphabetical order and place 35 in each class as per MOU agreement (NEC & training provider). [4] DEO/EO informs and confirms with clients for their availability. You may interview client for special purposes (genuine cases). [5] DEO/EO finalizes class listing and send to trainers . [6] EST begins and attendance list is issued to the trainer. If no LST Certificate produced, then go back to No.3. DEO/EO to ensure attendance list is filled/signed by clients in the morning & afternoon sessions. [7] Issue of certificates to clients after completion and receipt of certificate is signed by clients. [8] Training providers provides EST report to DNEC and DEO updates client database profile and client file. [9] Hard copy of client Report sent to registry. |

| Year | Number |
| --- | --- |
| 2010 | 152 |
| 2011 | 2360 |
| 2012 | 184 |
| 2013 | 0 |
| 2014 | 0 |
| Total | 2,696 |

|  | Report sent to Registry[9] |
| --- | --- |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.6.4	The Employment Skills Training is intended to develop suitable skills for clients to pursue for

employment relevant to the demand of labor market. The following table 5.7 illustrates the

process involved in the EST.

Table 5.7: Process of engaging clients for EST

5.6.5  	For the period 2010 to 2014 a total of 2,696 NEC clients have successfully completed training in

various discipline offered. The EST targets those without any formal tertiary qualifications. The

following table 5.8 illustrates the number of clients for each year.

Table 5.8: Number of clients engaged for EST from 2010-2014

Source: NEC Board paper 1/14

5.6.6	Over the period 2010 to 2013 NEC has only managed to meet its annual target of 1,000 per

year in 2011. The non-performance of the training in the remaining years is mainly attributed to

the cost of the training which has to be met by NEC. The cost per client for NEC to provide the

training is $600.00.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	37

| Employment skills |  |  |  |
| --- | --- | --- | --- |
| Accounting & Finance | Arts & Craft | Automotive heavy | Automotive integrated |
| Automotive light | Carpentry | Communication | consumer electronics |
| Electronics automotive | Electrical engineering | Engine service & repairs | Farming |
| Graphics design | Information technology | Joinery | Management |
| Manufacturing | Maritime | Motor Vehicle machine | Office administration |
| Painting | Panel Beating | Plumbing | Refrigeration & air con |
| Spray painting | Security | Tour Guide | Tourism |
| Welding and fabrication | Wet trades | others |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.6.7	Our audit gathered that NEC determines clients for Employment Skills Training by first

identifying their need for such training. This is obtained through the Registration Form filled by

the clients. Part 41 of the form outline 31 different types of employment skills that the NEC

clients are required to select. Refer to table 5.9 below for details:

Table 5.9: Employment skills listed in the NEC registration form

5.6.8	The information gathered are then collated by the NEC Secretariat staffs to identify the courses

that NEC needs to offer through the training providers. Due to the costs involved and the

limitation in funding, NEC prioritises the training to be offered mainly focusing on a skill which

will benefit a lot of clients. The training courses are then advertised to allow the identification of

the most suitable training providers which are then submitted for approval of engagements.

According to NEC the Employment Skills Training is provided by Vocational Training Institutions

and not Academic Training Institutions who are accredited providers that are recognized under

the Fiji National Qualification Framework. However, audit was not provided with the list of

training providers during the audit thus we were not able to ascertain the arrangements

pertaining to their engagement. .

5.6.9	Discussion with the officers revealed that the current system of identifying the suitable

employment skill training is not effective as there are still more NEC clients not being absorbed

into the permanent workforce.

NEC conducted a survey in 2012, interviewing most employers that are not involved in taking

NEC clients and found that NEC needs to review its strategy. Instead of identifying clients for

EST by obtaining their need as indicated in their registration form, NEC should provide EST for

areas that are of demand in the market so as to guarantee their absorption into the workforce.

5.6.10 The limitation in funding has a detrimental impact on the number of EST provided by NEC.

5.7 Workplace attachment- NEC Secretariat

5.7.1	A Formal Employment Service designated and established under section 56 must arrange with

employers or employers‟ organisations to provide quality workplace attachments of unemployed

persons enrolled under the Service.74

74

NEC Decree 2009 Part 8 s 59(1)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	38

| Employment Creation Services | Quantum 2010-2014 | Comments |
| --- | --- | --- |
| Formal Employment Services | 2,719 | Employed in the formal sector |
| Fiji Volunteer Services | 581 | Employed in the formal and informal sector |
| Self-Employment Services | 17,133 | Employed in the informal sector |
| Foreign Employment Services | 75 | Employed overseas |
| Total | 20,508 |  |

| Year | Number of clients |
| --- | --- |
| 2010 | 72 |
| 2011 | 1,012 |
| 2012 | 762 |
| 2013 | 1,256 |
| 2014 | 202 |
| Total | 3,304 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.7.2	Workplace attachment allows clients to acquire hands on experience on real-life work situations.

As discussed under Section 4.0 it‟s a legal obligation for employers who employ 50 or more

workers to recruit at least 5% of the total number of workers as attaché‟s.

5.7.3	For the period 2010 to March 2014, NEC has engaged a total of 3,304 clients processed

through this program. Refer to table 5.10 below for details.

Table 5.10: Clients engaged by NEC on attachment from 2010-2014

Source: NEC Board paper 1/14

5.7.4	It can be inferred from the above table that NEC has met its target of 200 per year for the period

2011 and 2014. This is encouraging as the success of workplace attachment is heavily reliant

on the willingness of employers to take in clients under the program.

5.7.5	Without the commitment of these employers the sustainability of the program is not assured in

the long run.

5.8 Permanent Employment

5.8.1	The ultimate aim of the National Employment Centre is to reduce the unemployment rate from

8.6% to 4.3% by 2015. A way in which this aim can be achieved is through the absorption of

NEC clients into permanent employment.

5.8.2	The total quantity of unemployed persons absorbed into permanent employment is reflected in

table 5.11 below.

Table 5.11: Total number of unemployed persons absorbed into permanent employment from 2010-2014

Source: NEC Board paper 1/14

5.8.3	For the 75 clients finding employment through the FORES, 47 skilled workers have been

deployed for overseas assignments and 28 are expected to leave by July 2014. The following

table 5.12 provide further details:

Table 5.12: Unemployed persons absorbed into permanent employment under FORES from 2010-2014

Country	 Quantum	Year	Area

United Arab Emirates	 16	2013 & 2014	Tourism

Canada		25	2014	Agriculture

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	39

NEC Decree 2009 Part 12 s 96(2)

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

New Zealand	 3	2014	Transportation

Others	 31	2010-2014

5.8.4	Government agencies administering SES have contributed to the development and monitoring

of small and micro enterprises. Refer to table 5.13 below for details:

5.13: Results of contribution of agencies to SES

Type of Assistance	 Quantum

Cluster projects	 6,711

Employment Created		17,133

Livelihoods improved	 36,499

Wealth created		$69,797,800

5.8.5	The number of permanent employment has the potential of increasing further if all related

stakeholders work together under the NEC umbrella.

5.9 National Employment Centre Trust Fund

5.9.1	The object of this Part is to establish a National Employment Centre Trust Fund to be held in

trust by the nominated representatives of the National Employment Centre Board as trustees of

the Fund. The Fund may be applied by the Minister on the advice of the Board for the purposes

of defraying the expenses of the National Employment Centre and the promotion and creation

of employment and business opportunities in the formal employment market, self-employment

market, Fiji Volunteer Service or foreign employment market including the incentivisation of

green jobs, green growth and green productivity.75

5.9.2	There shall be established in the special deposits account within the Ministry a National

Employment Centre Trust Fund.76 The Fund shall consist of-

(a) Any money provided by Cabinet or Parliament for the purposes of the Fund or required to

be paid into the Fund by or under this or any other law;

(b) Any grant or donation paid in the Fund from any local, regional or international agency or

charity;

(c) Any grant paid into the Fund from any Government;

(d) Any grant, contribution or donation paid into the Fund from any local, regional or

international corporate entity or individual;

(e) Any donation paid from the Fund from the public;

(f) Any donation paid into the Fund from any philanthropist or by bequest or fund raising

activity;

(g) Any investment return on any of the Fund‟s assets;

(h) Any prescribed user-pay services revenue acquired by the NEC or any of its ECS;

(i) Any grant, contribution or donation paid into the Fund from any local, regional or

international training institution; and

(j) Any other donation or contribution paid into the Fund.77

5.9.3	There shall be paid out of the Fund all amounts payable under section 97 of this Decree and all

other amounts required to be paid out of the Fund by or under this Decree.78 The management

75 NEC Decree 2009 Part 12 s 95

76 NEC Decree 2009 Part 12 s 96(1)

77

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	40

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

of the Fund, including the receipt of monies in the Fund, the payment of monies out of the Fund

and investment of the Fund, shall be in accordance with international accounting best practice

as prescribed.79

5.9.4	The Amendments to the NEC Decree allowed other financial institutions to donate fund to the

NEC Trust Fund. As at March 2014, the Trust Fund balance was $517,533.29.

5.9.5	Audit found that in 2011 the NEC and Fiji National University signed an MOU to donate $3.0 m

to the NEC Trust Fund Account. This Fund was distributed on a yearly basis until 2013. In 2012

NEC was given $1m and by 1st October 2013 the NEC had utilised $484,000.77.

5.9.6	Our review of the Board papers for 2014 found that NEC made a recommendation to the Board

to endorse an appointment of a Financial Sub-Committee to implement section 95 of the NEC

Decree 2009 which requires that the Trust Fund to be held in trust by the nominated

representatives of the NEC Board as trustees of the Fund.

RECOMMENDATIONS

	As a form of control NEC should issue identification cards to all customers registered under NEC.

	NEC should review the process of registering its customers outlined in the SOP to capture the

verification and authorisation of registration forms before being entered into the database.

	NEC should ensure that a proper and transparent process is followed in engaging consultants for

counselling services. In this regard it should ensure that appropriate documentations are available

to justify consultant‟s engagement as well as the criterion utilised to select them.

	NEC should improve on its scheduling and organising of counselling sessions and also ensure that

the terms and conditions of the contract with the consultants are complied with.

	NEC should re-assess the capability of its database and address the areas that pose a threat to

the effective and efficient management of its data.

	NEC should allocate its awareness targets in the ACP to cover all its intended target groups which

it believes it can reach annually with the available level of resources.

	NEC should review its training package for LST to ensure that it suits all clients under the four

ECS. In this regard training packages should be tailor made to the needs of each Service.

	In view of funding limitations NEC should review its strategy for provision of EST to ensure that the

program is successful.

Management Comments

	The initial phase NEC was issuing ID card but due to financial constraint, the decision was to stop and

only issue letter of confirmation. We will re-activate if budget is allocated.

	The new SOP under ISO 9001;2008 will include this verification and authorization of registration.

	The NEC is complying with the Office of Procurement new requirements in related to the hiring of

Consultants to provide services to the NEC.

	The consultant’s Terms of References (TOR) is clearly stated in the MOU or MOA.

	Since the commissioning of the NEC database in 2011, we have come across some teething problems. The

IT Team is working on it including the new reporting template.

	The NEC team is very aggressive is promoting the NEC Decree requirements and with new recruit

volunteers will enhance this area.

78

79

NEC Decree 2009 Part 12 s 96(3)

NEC Decree 2009 Part 12 s 96(4)

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	41

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	The introduction of ISO 9001; 2008 standard had brought in new initiatives to revamp all training package

and SOPs. The NEC operation will be efficient, effective and economical.

	The Employment Skill Training activity will be obsolete after we trained all unemployed persons with no

tertiary qualifications registered with the NEC. The free education and free/available scholarship will take

care of this cost. We will focus on up-skilling of specialized discipline only.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	42

| ECS | Legislative Provision | Ministry Responsible |
| --- | --- | --- |
| Formal Employment Service | NEC Decree 2009, Section 63(1)(2) | Ministry for Labour, Industrial Relations & Employment through the National Employment Centre |
| Self-Employment Service | NEC Decree 2009, Section 73(1)(2) | The SES is currently being administered by various ministries and agencies which include:  National Centre for Small Micro Enterprises Development (NCSMED)  Centre of appropriate Technology and Development (CATD)  Ministry of Youth and Sports  Ministry of Social Welfare and Poverty Alleviation  Ministry of Agriculture  Department of Forestry  Department of Fisheries  Integrated Human Resources Development Program |
| Fiji Volunteer Service | NEC Decree 2009, Section 83(1)(2) | Public Service Commission |
| Foreign Employment Service | NEC Decree 2009, Section 93(1)(2) | Ministry for Labour, Industrial Relations & Employment through the National Employment Centre |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.0 MONITORING	AND	REPORTING

ACTIVITIES OF NEC

This section looks into the monitoring and reporting of NEC activities. It is crucial that

proper and effective monitoring and reporting mechanisms are in place to monitor and

report activities of NEC in providing quality skills training, human resource development

and utilisation services that enhance the employability of unemployed persons, retirees and

volunteers, as only then can performance be established.

6.1 Performance reports

6.1.1	The 2009 NEC Decree requires all of the employment creation services to prepare and submit

their performance reports to the National Employment Centre Secretariat, the chairperson of the

NEC Board and the Minister.

6.1.2	The NEC Decree 2009 requires that these performance reports are to be prepared and

submitted by the various Employment Creation Services agencies to the above parties on a

quarterly, bi-annual and annual basis. Refer to table below for details:

Table 6.1: Requirements of NEC Decree 2009 on preparation of performance reports by ECS

6.1.3  	The National Employment Centre Secretariat is required to consolidate the performance reports

of all the employment creation services and submit them to the NEC Board and the Minister.

Audit gathered that NEC has developed a reporting procedure in their SOP which serves as a

guide for preparations, submission and consolidation of their required reports. Refer to table

below for details;

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	43

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Figure 6.1: Reporting procedure

Start

DEO

[1]

EO [2]

DM[3]

Director [4]

DS [5]

PS [6]

Minister [7]

[1] DEO compiles weekly report or any other

report that the Manager may require from time to

time.

[2] EO verifies report and submits to Manager.

[3] Managers validate and add value to the report

before onward transmission to the Administration

Assistant (AA).

[4] AA consolidates and analyses report (weekly,

monthly, quarterly, bi-annual and annual) before

final submission to Director.

[5] Director to update DSHQ on a monthly,

quarterly bi-annual and annual basis.

[6] Report is submitted to PS for further

deliberations.

[7] Final report is submitted to Minister for his

information and update.

[8] With PS and Minister‟s consultation,

verification and approval, the Report is presented

to Cabinet by Minister. Feedback must be

relayed back to all staff.

(The report may be disseminated to other

relevant stakeholder‟s subject PSLIRE approval).

Cabinet [8]

6.1.4	Audit gathered from the SOP that NEC submits its report to the Minster after verification and

validation from the NEC Managers and Director. This report includes all the ECS that NEC is

currently responsible for which entail FES, FORES and FVS. The report is prepared on a

monthly basis. Once the report is endorsed it is then submitted to the Secretariat for its

submission to the Board.

Our review of the Board Papers found that performance reports are also presented to the Board

on an annual basis.

Interview with responsible officers noted that the Centre has not prepared quarterly or bi annual

performance reports as required under the given legislation.

6.1.5	Audit was not able to ascertain whether reports from the two agencies providing services not

managed by NEC were prepared and submitted quarterly, bi-annually and annually by the

responsible agencies.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	44

| ECS | Legislative Provision | Ministry Responsible |
| --- | --- | --- |
| Formal Employment Service | NEC Decree 2009, Section 64(1)(2) | Ministry for Labour, Industrial Relations & Employment through the National Employment Centre |
| Self-Employment Service | NEC Decree 2009, Section 74(1)(2) | The SES is currently being administered by various ministries and agencies which include:  National Centre for Small Micro Enterprises Development (NCSMED)  Centre of appropriate Technology and Development (CATD)  Ministry of Youth and Sports  Ministry of Social Welfare and Poverty Alleviation  Ministry of Agriculture  Department of Forestry  Department of Fisheries  Integrated Human Resources Development Program |
| Fiji Volunteer Service | NEC Decree 2009, Section 84(1)(2) | Public Service Commission |
| Foreign Employment Service | NEC Decree 2009, Section 94(1)(2) | Ministry for Labour, Industrial Relations & Employment through the National Employment Centre |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.1.6	In addition, our review of the NEC Board papers prepared for the Board‟s recent meeting found

errors in the performance update of certain activities of the NEC. In particular, audit found that

Annexure 2.0 Table 6.0 attached as part of the performance report provided to the Board did

not agree with the discussion made as part of the Board Paper contents.

6.1.7	In the absence of a performance report, the Centre will not be able to evaluate how effectively

they are implementing and managing the employment creation services. In addition, errors in

the performance report included in the Board papers may result in the members of the Board

being mis-informed of the performances of NEC.

6.2 Annual reports

6.2.1	The 2009 NEC Decree requires all of the ECS to also prepare and submit their annual reports to

the National Employment Centre Secretariat, the Chairperson of the National Employment

Centre Board and the Minister including the host Minister of the Service.

6.2.2	The following table outline the specific sections of the NEC Decree 2009 in respect to the

preparation and submission of Annual Reports.

Table 6.2: Requirements of NEC Decree 2009 on preparation of annual reports by ECS

6.2.3  	Our examination noted that apart from NEC the other ECS agencies do not submit their annual

report to the Secretariat to enable the Secretariat to consolidate the reports in its annual report

for NEC.

6.2.4	The non-submission of annual reports by the various ECS agencies limits the information

provided to users of the report on the performance of NEC.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	45

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.3 Monitoring clients finding employment for recovery

purposes

6.3.1	The National Employment Centre has in place a repayment programme. The programme is

applicable to all unemployed persons who have registered under the NEC and have undertaken

professional counselling, aptitude assessment, life skills training, employment skills training and

work attachment including business attachment and have been absorbed into permanent

employment.

6.3.2	The following table outlines the conditions of repayment, responsibilities of NEC and

responsibilities of NEC trainee in respect to the repayment programme.

Table 6.3: Conditions for Repayment

1.	Maximum amount payable is 50 percent of the total costs of training fees incurred by the NEC.

2.	Repayments may be made to the NEC through direct deduction of the employee‟s wages to the Centre‟s

trust fund account number 7788265 with the Bank of the South Pacific (BSP) or by manual repayment at any

of the Centre‟s divisional office located in the Central/Eastern, Western and Northern divisions.

3.	Repayment may begin at any stage of the training upon agreement of the trainee.

4.	Repayment may be made in installments upon discussion and agreement between the trainee and the NEC.

Responsibilities: NEC

1.	The NEC shall sign an MOU for repayment with all NEC trainees during life skills training

2.	The NEC shall follow up with all individual trainees who are on work attachment for more than 6 months on

the NEC trainee‟s work, business attachment or foreign employment status for the purpose of repayment.

3.	The NEC shall discuss and agree with each trainee on the proposed method of repayment and the period of

repayment before any repayment is made.

4.	The NEC shall provide a designated revenue collector who shall be responsible for collecting and receipting

all payments received from trainees.

Responsibilities: NEC Trainee

1.	The trainee shall report any change to his or her employment status to the NEC within 7 working days

2.	The trainee shall inform the Centre of the updates to his or her contact details including residential, postal,

phone and email details

3.	The trainee shall apply good faith principles during the term of engagement with NEC

4.	The trainee shall demand for a receipt for the NEC when making repayments.

6.3.3	As can be interpreted from the table a Memorandum of Understanding is signed between NEC

and the trainee to repay 50% of the fees paid by the Centre. The MOU is required to be signed

by the trainee during the life skills training.

6.3.4	Audit gathered that the mechanism in place to monitor absorption of clients into permanent

employment is not quite effective. NEC conducts follow ups on all individual trainees for more

than six months on the NEC trainee‟s work, business attachment or foreign employment status

for the purpose of repayment. The mechanism in audit‟s opinion is highly unreliable.

6.3.5	There is a risk that large amount of monies invested by the Government through NEC may not

be recovered due to absence of an effective monitoring system.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	46

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

RECOMMENDATIONS

	The Centre should ensure that the requirements of the NEC Decree are complied with in respect

to the preparation and submission of performance reports.

	The Centre should ensure that proper checks are made to the performance audit report before

being endorsed and submitted as Board Paper for the Board‟s discussion.

	NEC should send requests to all agencies managing the Services not under their responsibility to

send their annual reports for activities relating to NEC within a specified timeline.

	NEC should put in place an effective monitoring system to establish employment of customers

under its programme. A suggested approach is for NEC to work with FRCA by submitting the

names of customers and requesting FRCA to inform them once a TIN is issued. A Memorandum

of Understanding should be pursued with FRCA if NEC wishes to pursue this option.

Management Comments

	At this point in time, the NEC Decree is not fully implemented due to the delay in gazetting of the seven

(7) Regulations, resource capacity and establishing of SES. The existing strategy is to establish the

Secretariat to roll out in phases the NEC Decree obligations. At the moment, we are reporting to PS and

our NEC ACP is inculcated in the MLIRE ACP.

	A mechanism is in place on all management level to verify and check on Board and Cabinet papers. The

new procedure is that the final copy is vetted by PS before delivered to the Honorable Minister for

external stakeholders.

	We are liaising with relevant agencies to identify responsible officer to prepare this report and submit to

the NEC.

	We had met with FRCA this year related to tax rebate. This tax incentive is in place and only applies to

employers employing new NEC recruits.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	47

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

7.0 CONCLUSION

7.1	In view of the limited funding and staffing the audit acknowledges the great work done by the

Ministry of Labour so far on the establishment and operations of the NEC. The NEC Board has

also played a critical role over the years on the establishment and implementation of the NEC.

7.2	Cabinet‟s commitment on the program is also evident through the endorsement of Cabinet

Papers on the NEC submitted by the Ministry.

7.3	However, the success and sustainability of the program is heavily reliant on the finalisation of

the draft Regulations and the co-operation and commitment of other agencies that are part of

the initiative.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	48

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

8.0 REFERENCES

1. CP (09) 237 of 30th October 2009

2. CP (09) 45 of 28th May 2009

3. CP (10) 154 of 4th June 2010

4. CP (10) 160 of 4th June 2010

5. CP (10) 161 of 4th June 2010

6. CP (10) 162 of 4th June 2010

7. CP (10) 163 of 4th June 2010

8. CP (10) 164 of 4th June 2010

9. CP (10) 165 of 4th June 2010

10. CP (10) 166 of 4th June 2010

11. CP (12) 70 of 9th March 2012

12. Cabinet Decision No.59 of 2nd June 2009

13. Cabinet Decision No.85 of 13th March 2012

14. Cabinet Decision No. 303 of 3rd November 2009

15. Cabinet Decision No. 200 of 7th June 2010

16. Cabinet Decision No. 204 of 7th June 2010

17. Cabinet Decision No. 205 of 7th June 2010

18. Cabinet Decision No. 206 of 7th June 2010

19. Cabinet Decision No. 207 of 7th June 2010

20. Cabinet Decision No. 208 of 7th June 2010

21. Cabinet Decision No. 209 of 7th June 2010

22. Cabinet Decision No. 200 of 7th June 2010

23. National Employment Centre Decree 2009

24. National Employment Centre Standard Operating Procedures

25. NECB Paper 18/10 of 9th July 2010

26. NECB Paper 01/11 of 29th September 2011

27. NECB Paper 03/11 of 29th September 2011

28. NECB Paper 04/11 of 29th September 2011

29. NECB Paper 05/11 of 29th September 2011

30. NECB Paper 06/11 of 29th September 2011

31. NECB Paper 07/11 of 29th September 2011

32. NECB Paper 1/12 of 17th December 2012

33. NECB Paper 3/12 of 17th December 2012

34. NECB paper 1/14 of 5th June 2014

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	49

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1.1: NEC CORE BUSINESSES

(i)	Integrated Human Resources Development Programme for Employment Promotion

(IHRDPEP) and its 7 sub programmes managed by the NEB secretariat under the ministry

of Labour (agreed at DSC and ERAB for the IHRDPEP employment promotion

programmes to be shifted from the Ministry of National Planning to Labour Ministry for

logistics and governance reasons.)

(ii)	Life skills and employment skills training and work attachments for absorption into

formal and informal local employment with the National Youth Service Scheme (NYSS)

(iii)	Entrepreneurial skills training and creation of small businesses locally through seed

funding and technical support services with the National Centre for small &micro

Enterprises Development (NCMED)

(iv)	Promotion of overseas employment opportunities by the NEB Secretariat via Ministry of

Foreign Affairs protocol.

(v)	Volunteer service under Fiji first National volunteer Scheme managed by the NEB

secretariat for those wishing to promote civic responsibilities to the various sectors both

in FiJI and also in the pacific region and overseas

(vi)	networking and strategic partnerships with training agencies and authorities such as

TPAF,FIT,TVET, Ministry of education and the National Qualification Authority for the

provisions of skills training and re-training or up-skilling of unemployed persons and

workers; and

(vii)	Collation and analysis of labour market ‘supply and demand’ information & data to

facilitate the effective delivery of the NEB core business, and advise on priority disciplines

for scholarship funding.

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	50

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1.2: FUNCTIONS OF NEC BOARD

 to establish the overarching National Employment Centre‟s strategic plan and corporate plan vision, mission, values, targets and strategies, rationalizing

and integrating the strategic plans and corporate plans of the Formal Employment Service, the Self-Employment Service, the Fiji Volunteer Service and

the Foreign Employment Service;

 to ensure the achievements of the Centre‟s overarching strategic plan and corporate plan targets every year, compatible with national unemployment

needs and Government‟s commitments to the Peoples Charter for Change, Peace and Progress;

 to ensure an efficient and effective National Employment Centre established under the Ministry by this Decree;

 to ensure the efficient and effective consolidation of all existing employment creation services within or under the jurisdictions of Government ministries

and departments under the National Employment Centre Secretariat umbrella, operating under the Ministry‟s jurisdiction;

 to ensure the efficient and effective operations of all the Employment Creation Services established under this Decree;

 to ensure the efficient and effective implementation of employment creation policies of Government through the various Employment Creation Services

by way of effective facilitation, coordination and monitoring roles;

 to ensure efficient and effective strategic partnerships with vocational training and other training institutions, including the disciplined forces to realize

quality competency-based skills training for all attachés, volunteers and unemployed persons;

 to ensure an efficient and effective national registration system for all the unemployed throughout the Fiji Islands;

 to ensure the provision of quality and professional counseling services to all unemployed persons;

 to ensure the establishment and sustainability of the Fiji Volunteer Service and the Foreign Employment Service through the National Employment Centre

Secretariat;

 to search and find innovative ways or secure partnerships to significantly create and boost employment opportunities for the unemployed, such as the

adoption of progressive information and communication technologies in training and development;

 to boost entrepreneurship skills training and the creation of small businesses locally through the provision of seed funding and technical support services;

 to effectively promote, facilitate and boost local and overseas employment opportunities through progressive media marketing and other effective

strategies;

 to effectively promote, facilitate and boost participation in the Fiji Volunteer Service for services locally, regionally and internationally;

 to effectively promote and facilitate quality skills training and re-training or up-skilling of unemployed persons and workers;

 to ensure the timely collation and analysis of labour market „supply and demand‟ information and data relating to employment and unemployment to

facilitate the effective delivery of the National Employment Centre and Employment Creation Services‟ core businesses;

 to provide and maintain an efficient and current national human resources database system on employment and unemployment to ensure quality policy

advice to the Minister and also to facilitate the Government‟s human resources planning, including the allocation of scholarships;

 to periodically advise the Minister on the performances of all the Employment Creation Services in terms of employment creation growth;1396

 to assume and rationalise the employment creation responsibilities of existing boards or bodies established by any of the Employment Creation Services

operating within the jurisdiction of any Government ministry or department for the purposes of organisation reform under this Decree;

 to decide on the allocation and distribution of human resources, operating and capital budgets and assets amongst the Employment Creation Services

and the National Employment Centre Secretariat in accordance with the Government policy to establish the National Employment Centre and associated

restructuring reform;

 to decide, in consultation with the Minister, on the employment creation core businesses of the Employment Creation Services during the establishment

or designation of the Formal Employment Service, the Self-Employment Service, the Fiji Volunteer Service or the Foreign Employment Service;

 to decide, based on the determination of employment creation core businesses under subsection (1)(v), the rationalisation of organisation structures and

positions in these Services, their numbers, grades, salary levels, contractual terms and conditions of employment and performance management systems

to be adopted that are compatible with the market demands of the various employment and business markets to ensure that these Services are market-

driven, cost-efficient and cost-effective;

 to inquire into and report to the Minister on matters relating to employment creation referred to it by the Minister;

 to provide the Minister with bi-annual reports on the progress in implementing the employment creation policies of Government under this Decree; and

 to advise the Minister on any other employment creation matter as well as matters provided for by this Decree and any other written law;

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	51

| Formal Employment Service | Relevant section of the Decree | Objectives | Goals |
| --- | --- | --- | --- |
| Formal Employment Service | Part 8 sections 55 and 56 | To provide quality human resource development service to unemployed persons to facilitate their absorption into the formal employment market and boost productivity including green productivity. |  To provide quality human resource development service to unemployed persons to facilitate their absorption into the formal employment market and boost productivity including green productivity. |
| Self-Employment Service | Part 9 section 65 and 66 | To provide quality human resource development service to unemployed persons and retirees to help them start and sustain their own small or micro enterprises, local economic development programmes or social enterprises as empowered entrepreneurs to boost employment creation and productivity including green productivity and green jobs. |  Provide quality business skills training and advise for unemployed persons and retirees to facilitate their active participation in the formal, informal, urban and rural employment markets through the creation and sustaining of their own small and micro enterprises of other forms of self-employment. |
| Fiji Volunteer Service | Part 10 section 75 and 76 | To promote a strong sense of service and civic pride amongst the people of the Fiji Islands |  To engage unemployed persons and retirees who wish to serve society in the spirit of volunteering in any local, regional or international undertakings, including green growth projects.  Develop a strong sense of civic pride and alleviate social problems in the nation. |
| Foreign Employment Service | Part 11 section 85 and 86 | To provide quality human resource development service to unemployed person and retirees to facilitate their absorption into decent and environmentally responsible overseas employment to boost employment creation and productivity. | To provide quality foreign employment services which involve orientation training to the unskilled, semi-skilled or skilled employed persons and retirees to facilitate their recruitment into the foreign employment market. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX	1.3:	OBJECTIVES	AND	GOALS	OF	FORMAL

EMPLOYMENT SERVICES AGENCIES

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	52

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1.4: STRUCTURE OF NEC INCLUDED IN CP (10) 154

NEC BOARD

CEO

US02

Director NEC secretariat

US04

US04

Director FVS     US04        Director FES Director FORES

US04       Director SES

US04

Division SS01                	NEC Manager Northern

NEC Manager Central

Division SS01

NEC Manager Easter

Division SS01

NEC Manager Western

Division SS01

Employment officers x4

SS03

Employment officers x4

SS03

Employment officers x4

SS03

Employment officers x4

SS03

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	53

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1.5: REVISED STRUCTURE

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	54

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1.6:	EXISTING ORGANISATION STRUCTURE

MANAGEMENT OF NATIONAL EMPLOYMENT CENTRE	55

CONTRACTUAL ENGAGEMENTS

BY MUNICIPAL COUNCILS

A Performance Audit Report of the Office

of the Auditor General of the Republic of

Fiji

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

The audit looks into contractual engagements by Municipal Councils in Fiji. The audit focused on three

areas which include:

	Policy framework governing contractual engagements;

	Key elements of contractual engagements; and

	Managing contractors’ performance.

The audit covered seven of the thirteen municipal councils in Fiji located within the Central and the Western

Divisions.

Table of Contents

1.0 EXECUTIVE SUMMARY..........................................................................................................	3

2.0 INTRODUCTION ......................................................................................................................	5

2.1	Background.......................................................................................................... 5

2.2	Legislation governing municipal councils operations ....................................................... 6

2.3	Reasons for undertaking the audit.............................................................................. 6

3.0 AUDIT OBJECTIVES SCOPE AND METHODOLOGY ............................................................	7

3.1	Audit objectives ..................................................................................................... 7

3.2	Audit scope .......................................................................................................... 7

3.3	Audit methodology ................................................................................................. 7

4.0 POLICY FRAMEWORK GOVERNING CONTRACTUAL ENGAGEMENTS..10

4.1	Existence of effective policy framework ..................................................................... 10

4.2	Existence of contract planning................................................................................. 11

4.3	Risk assessment ................................................................................................. 13

5.0 KEY ELEMENTS OF CONTRACTUAL ENGAGEMENTS..................................	17

5.1	Human resources involvement in contractual works ...................................................... 17

5.1.1	Technical expertise in the identification of contracted works................................................................ 17

5.1.2	Contract management skills and knowledge.................................................................................... 18

5.2	Tendering of contractual works................................................................................ 19

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	1

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.2.1	Responsibility of evaluating and approving tenders........................................................................... 19

5.2.2	Evaluation and documentation of tender ........................................................................................ 20

5.2.3	Contractual agreement .............................................................................................................. 22

5.3	Records Management........................................................................................... 27

5.3.1	Maintenance of file on contractual works ........................................................................................ 27

5.3.2	Existence of contracts inventory and register................................................................................... 28

5.4	Payments of contractors ........................................................................................ 28

5.4.1	Controls in payments of contractors .............................................................................................. 29

5.4.2	Deposit payments made by Suva City Council to Construction Builders ................................................. 30

6.0 MANAGING CONTRACTORS PERFORMANCE...................................................................	39

6.1	Monitoring system................................................................................................ 39

6.2	Monitoring of contracted works by an external party...................................................... 40

6.3	Evaluation of contract performance .......................................................................... 41

6.4	Monitoring, reporting and evaluation of performance requirements included in the contract

agreement .................................................................................................................... 	42

6.5	Managing complaints on contractors work .................................................................. 44

7.0 CONCLUSION .......................................................................................................................	49

8.0 REFERENCE .........................................................................................................................	50

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	2

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

1.0	EXECUTIVE SUMMARY

Background	Some of the Municipal Councils service deliveries to the rate payers are performed by

contractors mainly due to the lack of resources within the Councils. These contractors

enter into contractual agreement with respective Councils with the common aim to

provide quality service to raise living standards amongst the rate payers and the

general community.

Coverage	The audit on Management of contracts in Municipal Councils focused on three main areas

including policy framework governing contractual engagements, key activities of

contractors’ engagements and managing contractors’ performance.

The audit covered seven of the thirteen municipal councils in Fiji.

Overall conclusion None of the Councils visited have developed a policy governing the management of

contractual engagements. Most the Councils visited were following tender procedures

outlined in the Manual of Accounts for Municipal Councils in Fiji which was endorsed in

1992. Detailed planning of outsourced services were lacking in six of the Councils

visited. Further to this risk assessment of contractual activities were not conducted by all

the Councils visited.

Generally records maintained on activities relating to contractual engagements needs to

be improved. It is pivotal that contract files contain information relating to tender

evaluations, contractual agreement, correspondences between the Council and the

contractor and other key activities of the engagement. Equally important is the

compilation of contracts inventory and contracts register to evidence the contracts

undertaken by the Councils over the years.

There is also a need to separate parties currently involved in the evaluation and

approval of tender proposals to ensure transparency in the tender process. The criteria

for tender evaluation is also lacking in most of the Councils. Contractual agreements

being entered into by most of the Councils needs to be reviewed to incorporate other key

items highlighted in this report. A few of the Councils also need to have their

agreements vetted by a solicitor. Stringent controls also need to be put in place to

ensure payments made to contractors are within the requirements of the contract

agreement.

Some evidence of monitoring of contractual engagement was noted to have been

conducted by most of the Councils; however there have been lack of proper

documentations to indicate the results of monitoring works. This anomaly was mainly

attributed to the absence of a monitoring policy in place and non-specification of

monitoring requirements in the contractual agreements. The evaluation of the

contractors’ performance and preparation of a contract performance report was not

conducted by all the Councils. Such is the case mainly due to the non-inclusion of the

requirement in the existing contractual agreement.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	3

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Key findings	Policy framework governing contractual engagements

	The Department of Local Government has no standard guideline in place

governing contractual engagement to be used by all Municipal Councils.

	The Department Local Government has not reviewed the existing 1992

Manual of Accounts used by the Councils to reflect changes and development

in the Councils

	Most of the Councils do not have detailed planning such as done by Suva City

Council to cover all activities at the commencement of, during and after the

contract period are conducted.

	None of the Councils have conducted risk assessment of contractual activities.

Key elements of contractual engagements

	Nausori Town Council did not have an engineer and head of the health to

provide technical input in the identification of contracted works.

	Responsibility of tender evaluations and approving tenders are not

separated.

	Most of the Councils did not have evaluation criteria to evaluate tender

proposals.

	Contractual agreement did not incorporate key items.

	Existing contracts approaching expiry term were not reviewed prior to their

renewal.

	Contractual agreements were not vetted by a solicitor in some Council.

	Documentation of contractual activities was generally lacking.

	Internal controls in the payment of contractors were lacking in some Councils.

Managing contractors’ performance

	Documentation of monitoring of contracted works were lacking in most

Councils.

	Nausori Town Council engaged a project manager to monitor works conducted

by five contractors without proper provisions in the agreement on monitoring

and reporting of the project manager.

	None of the Councils conducted an evaluation of contractors’ performance

following expiration of contracts.

	Monitoring, reporting and evaluation of contractors’ performance were not

included as part of the contractual agreement in most of the Councils.

	Complaints register were not updated in a timely manner in most of the

Councils.

General Recommendation The audit recommends that each Council covered in this audit look into the issues

raised in this report and work towards addressing the anomalies identified for

their Councils.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	4

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.0 INTRODUCTION

This section of the report provides a brief overview of contractual engagements by

Municipal Councils as well as reasons for the conduct of the audit.

2.1 Background

2.1.1	Local governments play an important role in improving living standards of communities

located within their municipal boundaries. In this context Councils are required to ensure

that resources are used efficiently and effectively and services are provided to best meet

the needs of the community and to improve the overall quality of life of people within the

community.

2.1.2	Municipal Councils provide a wide range of services that improve standards of living for

its rate payers, such as collection of household rubbish, maintenance of drainage and

roads infrastructure, provision and maintenance of public utilities, sports facilities,

recreation facilities, etc. The wide range of services required to be provided by Councils,

and given the limited resources available to them, has led many Councils to contract

some of its services to private contractors. Payments of contracts for such services

constitute a significant portion of a municipal councils‟ expenditure.

2.1.3	The fundamental best practice principles that Councils should apply to every contractual

engagements irrespective of the value and complexity of the arrangement include:

	Value for money

Obtaining value for money does not mean a Council is obliged to accept the lowest

price. The concept of value for money takes into account both costs and non-cost

factors including quality, service and support and advancing the Council‟s priorities.

	Open and fair competition

All prospective contractors must be treated fairly in an open and transparent

manner.

	Accountability

Council staffs are responsible for the actions and decisions they take in relation to

contractual engagements and for the resulting outcomes. Staffs must ensure that

they provide adequate and reliable advice to the relevant authorities to allow sound

decisions are made on contractual engagements.

	Risk management

All contractual engagement carries some level of risk. It is vital for Councils to

recognise these risks and develop appropriate strategies to deal with them.

	Probity and transparency

Councils must conduct their business in a fair, honest and open manner

demonstrating the highest level of integrity consistent with the public interest.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	5

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.2 Legislation governing municipal councils operations

2.2.1	Although they vary in sizes, geographies, populations and resources, all municipal

councils are governed by the Local Government Act (Cap 125). Altogether there are a

total of 13 Municipal Councils established around the country, consisting of eleven (11)

town councils and two (2) city councils.

2.2.2	Under Section 90 of the Act, Municipal Councils are required to;

(a)	promote or establish and maintain public utility services including public

transportation;

(b)	construct or maintain any public works which in the opinion of the council may be

necessary or beneficial to the municipality; and

(c)	contribute to the cost of the matters referred to in paragraphs (a)and (b).

2.2.3	Every Council is required to undertake activities lawfully and may expedient to promote

the health, welfare and convenience of the inhabitants of the municipality and to preserve

the amenities or credit thereof.

A Council may make by-laws prescribing forms, fees, matters and things which are

contemplated by this Act or are required or permitted by this Act to be prescribed, or

which appear to the council to be necessary or convenient for the peace, good order and

government of the municipality and for the purpose of effectually carrying out the

provisions of this Act, or for better effecting the operation, objects and purposes thereof.

2.3 Reasons for undertaking the audit

2.3.1	The choice of contracting services to deliver programs and services required is

considered a risk. Since payments of contract services constitute significant expenditures,

it is susceptible to collusion and mismanagement.

2.3.2	Previous financial audits conducted have highlighted a number of deficiencies with

regards to how contracts are tendered, issued, managed and controlled by Municipal

Councils, and have raised some concerns on non-compliance with required policies, laws

and regulations.

2.3.3	The contracting process and directives on contracting have not changed and as such an

audit in the area could also lead to some improvements such as policy reviews or

development, and improved contracting practices in municipal councils.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	6

| Division | Councils |
| --- | --- |
| Central |  Suva City Council  Nausori Town Council  Nasinu Town Council  Lami Town Council |
| Western |  Lautoka City Council  Nadi Town Council  Ba Town Council |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

3.0 AUDIT	OBJECTIVES	SCOPE AND

METHODOLOGY

This section of the report describes the objective and scope of the audit. It also

discusses the methodology utilised to gather information for the audit.

3.1 Audit objectives

3.1.1	The overall objective of the audit is to determine the effectiveness of municipal councils in

managing contracts of services by examining:

	the policy framework governing contractual engagements;

	key elements of contractual engagements; and

	managing contractors‟ performance.

3.2 Audit scope

3.2.1	The audit focused on contracts executed by 7 of the 13 municipal councils [i.e. 4 from the

Central division and 3 from the Western division] for the years 2012 to 2014. The

Councils are listed in the table below:

Table 3.1: Councils visited

3.2.2  	The audit did not look into any contracts entered into under the old local government set

up i.e. prior to 2008, however the audit may use any guideline or system from those years

that is currently valid and used by the Councils.

3.3 Audit methodology

The audit used the following methodology to gather information for the audit:

	Documentary review

The audit reviewed various documents to gather information on the management of contracts in

the municipal councils. The major documents reviewed are listed below:

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	7

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 3.2: Details of documents reviewed and source during audit

Municipal Council	Documents

Ba Town Council		Annual Corporate Plan 2011

	Strategic Plan 2010 – 2015

	Contract file

	Complaints register

Lami Town Council		Annual Corporate Plan 2010

	Annual Corporate Plan 2012

	Strategic Plan 2010 – 2014

	Contract Agreement between Nasinu, Lami

and Nausori Town Councils

	Contract file

	Complaints register

Lautoka City Council		Annual Corporate Plan 2011

	Annual Corporate Plan 2012

	Contract Agreement

	Contract file

	Complaints register

Nadi Town Council		Corporate Plan 2003 – 2012

	5 Year Strategic Plan 2010 – 2014

	Contract file

	Complaints register

Nasinu Town Council		Contract documents

	Payment vouchers to contractors

	Minutes of tender meetings

	Complaints register

Nausori Town Council		Contract documents

	Payment vouchers to contractors

	Minutes of tender meetings

	Complaints register

Suva City Council		Contract documents

	Payment vouchers to contractors

	Minutes of tender meetings

	Annual Corporate Plan 2010

	Annual Corporate Plan 2012

	Strategic Plan 2010 – 2014

	Interviews

Interviews were carried out with the following individuals in the various municipal councils.

Table 3.3: List of Interviewees

Municipal Council	Officer

Ba Town Council		Chief Executive Officer

	Accountant

Lami Town Council		Acting Town Clerk

	Acting Senior Accounts Officer

Lautoka City Council		Manager Finance

	Accounts Officer

	Manager Health

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	8

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Nadi Town Council		Manager Finance

	Manager Health

	Manager Engineering

Nasinu Town Council		Internal Auditor

	Engineer

	Health Inspector

Nausori Town Council		Special Administrator

	Finance officials

Suva City Council		Acting Chief Executive Officer

	Director Engineering Services

	Administration Secretary

	Other

Correspondences through e-mails were also made to clarify issues.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	9

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.0 POLICY FRAMEWORK GOVERNING

CONTRACTUAL ENGAGEMENTS

This section of the report looks into the policy aspect governing the identification,

awarding, execution and management of contractual engagements within the

municipal councils. The area also covers contract planning and risk assessment.

4.0.1	All Councils should have a documented contract policy in place to assist them in

managing contractual arrangements. The purpose of a documented contract policy is to

promote value for money, reduction of risk and fraud, waste or other irregularities.

4.0.2	Contract planning and management covers all activities at the commencement of, during

and after the contract period. It is the process that ensures both parties to a contract fully

meet their respective obligations as effectively and efficiently as possible, in order to

continually deliver both the business and operational objectives required from the

contract.

4.0.3	Risk assessment should be an integral part of all aspects of contractual engagements.

This requires the identification of risks and where appropriates the implementation of risk

treatment. This in turn involves identifying the events where risks are likely to be the

highest and/or adverse effect of an event or occurrence is likely to be the greatest.

4.0.4	Success in contract management occurs when the arrangement of service delivery

continues to be satisfactory to both customer and supplier, expected business benefits

and value for money are being delivered and realized, the supplier is co-operative and

responsive, disputes are rare and the contract is fully compliant and satisfies both

legislative and audit requirements.

4.1 Existence of effective policy framework

4.1.1	A written policy should be in place for all Municipal Councils to provide guidance on

aspects of contractor selection, management and monitoring of contractors and the legal

issues pertaining to contract implementation.

4.1.2	Suitable policies to support the management of contract should be established,

maintained and communicated.

4.1.3	The Manual of Accounts for municipal councils should be reviewed to take into account

changes in developments and expectations having an effect on the subject matter.

4.1.4	Discussions with responsible officers in the Municipal Councils revealed that there is no

uniform policy for all municipal councils governing the contractual engagements.

4.1.5	None of the Councils visited have a policy in place to govern the management of

contracts. Most of the Councils have developed and adopted preferable Tender Policies

to guide the respective tender processes.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	10

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

In addition, all Councils have been using the Manual of Accounts that was introduced in

1992. The idea behind this Manual was to provide an accounting manual for

municipalities originated from a discussion that took place between the Auditor General

and the Local Government Association some 10 years back. The idea was suggested by

the Auditor General at the time because of the obvious need to institute uniform and

appropriate accounting standards and procedures for the effective control and

management of municipalities‟ finances. For various reasons the municipalities have been

using different accounting standards which over the years have proved somewhat

inadequate for proper control of their finances.

4.1.6	The table below summarises our findings on existence of a contract policy within the

Councils visited.

Table 4.1: Existence of contract policy

Council	Is	a	contract	Audit comments

policy in place?

Ba	No	Accounting manual is in draft form and it has a section on

contract and contractual payments. The manual is yet to be

presented to council for approval

Lami	No	The Council uses the Manual of Accounts.

Lautoka	No	The Council‟s accounting policies and procedure manual is in

a draft form and is yet to be approved by the Council.

Nadil	No	The Council operating procedures is yet to be approved by the

Council. The Council is following the Manual of Accounts.

Nasinu	No	The Council has a Tender Policy and the old Manual of

Accounts in place to guide them.

Nausori	No	The Council is currently using a tender policy which is

currently under review.

Suva	No	There is a procurement instruction but staffs were not using it.

It can be interpreted from the above table that there is no specific policy on management

of contracts. Most of the Council are following tender procedures stated in the Manual of

Accounts for municipal council which was endorsed in 1992.

4.1.7	The use of draft policies in some of the Council indicates that such policies have been

adopted without proper endorsement of management. In addition untimely review of the

existing manual indicates that required changes and developments relating to contract

management are not incorporated as part of the document.

4.2 Existence of contract planning

4.2.1	Contract planning ensures delivery of desired project outcome. It considers a broad range

of factors including driving continuous improvement, value preservation and additional

value creation, performance management, risk mitigation, role clarity, and the value of

contractors‟ relationship, and quality assurance.

4.2.2	Our review on the contract planning gathered that most of the Municipal Councils have

plans for capital projects and development in their jurisdiction. This is incorporated in the

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	11

| Councils | Existence of contract planning? | Audit comments |
| --- | --- | --- |
| Ba | No | The project planning for the Council is covered in the 5year strategic plan from 2010 – 2014. The plan has been prepared after consultation with the stakeholders. The plan covers the review of the current process and the identification of infrastructure and implementation and changes that has to be made in a five year period. |
| Lami | No | Capital projects identified with its estimated costs incorporated in the Strategic Plan 2010-2014. |
| Lautoka | Yes but no specifications provided | The Council has a strategic plan (5yr plan) for improvement of infrastructure. The formulation of the strategic plan involves various stakeholders and their views were also incorporated in the plan. |
| Nadi | No | Indications were made that a strategic plan exists but no copies were provided to audit. |
| Nasinu | No | No capital project plan was provided from Engineering Department; however capital expenses were incorporated in the budget. |
| Nausori | No | No capital project plan was provided. There were no HODs for Engineering, Health, and Building to prepare the plans. However, capital expenses were incorporated in the budget but no project work details provided. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

form of capital works program and with some Council and is inserted as part of the capital

budget. The respective Councils formulated a 5 years Strategic Plan for 2010 – 2014

which incorporates the strategic plan for capital projects. However, audit noted at this

planning stage, most of the Councils have not decided on the project works that will be

contracted.

Plans for capital projects usually planned out by the different departments within one

Council. For example, the engineering department provides plan for the construction

works such as ground development, roads infrastructure repairs, etc. while the building

department provides plan for any building development projects, repairs and

maintenance.

4.2.3	For the Councils that were visited, except for Suva City Council all other Councils showed

no evidence of detailed project planning conducted on contractual works undertaken. For

the Suva City Strategic Capital Project Plan, when a project is identified, the following

details were specified:

i.	Different tasks name with an identification number

ii.	Duration of the project

iii.	Starting date

iv.	Finishing date

v.	Work schedule that shows the time period when a task ID needs to be

completed.

4.2.4	For the remaining Councils visited the following were noted after our review of the

contract planning system;

Table 4.2: Observations on contract planning system

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	12

| Sources of risk | Examples of risk |
| --- | --- |
| Contract management knowledge and capability |  Lack of understanding of Council contractual policies and reporting requirements.  Lack of experience in the management of contracts.  Lack of training in the area of contract management. |
| Resourcing |  Inability to obtain and retain necessary level of resources including staffing advice.  Failure to obtain senior management support and involvement.  Insufficient time to develop contractual agreement. |
| Contract performance measurement |  Failure to specify performance indicators that can be cost effectively measured.  Failure to link contract payment to satisfactory performance.  Failure to establish cost-effective performance monitoring and assessment arrangements. |
| Contract management capability |  Failure to have sufficiently skilled and experienced resources to effectively manage contractual services  Failure to act on contractor under-performance |
| Contractor performance |  Failure to provide services on time to agreed quality and standards  Failure to adhere to agreed budget  Failure to comply with contractual agreement provisions  Fraud and/or unethical conduct by a contractor |
| Changes in circumstances and/or requirements |  Contract changes not dealt with as contract variations  Contractor not prepared to agree to contract variations to accommodate changes in entity requirements  Changes in circumstances not managed in a timely manner |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.5	Absence of key details in project planning may lead to projects not delivered as planned

by the Council.

4.3 Risk assessment

4.3.1	Risk assessment for contractual purposes comprises those activities associated with

identifying and controlling the risks that may potentially affect the successful fulfilment of

the contracted work.

4.3.2	The following table detailed some of the key sources of risk and examples of risks that

needs to be considered when contracting services to an external party.

Table 4.3: Sources and examples of risk

4.3.3	Our audit at the seven Councils visited gathered no evidence to indicate that risk

management has been addressed in detail in all activities relating to contracting of

services.

4.3.4	The effective management of risks attached to contractual activities has the potential to

save the Councils considerable monies as well as ensuring that the Councils are deriving

maximum return from monies invested in contractual works.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	13

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

RECOMMENDATIONS

Department of Local Government

	The Department should review the existing Manual of Accounts used by the Councils to reflect

changes and development in the Councils. The revised Manual should include a standard guideline on

contractual engagements.

Ba Town Council/Lami Town Council/ Lautoka City Council/Nadi Town Council/ Nasinu Town

Council/Nausori Town Council

	The above Councils should ensure that proper project planning is conducted. Project plans should

include programmed objective and description, plan of work and methodology, sources of information,

deliverables of the programme, required expertise of the service provider, time schedule and

management structure and reporting.

All Councils

	All Councils should conduct continuous risk analysis and assessment throughout the contractual

period in order to effectively manage the risks that arise.

Management Comments

Department of Local Government comments

No comments received

Ba Town Council comments

Policy Framework Governing Contractual Engagements - The above Councils should ensure that proper

project planning is conducted. Projects plans should include programmed objective and description, plan

of work and methodology, sources of information, deliverables of the program, required expertise of the

service provided, time schedule and management structure and reporting. Council will follow the advice

from Auditor General and will monitor and continuously assess the contractual works

Nadi Town Council comments

Policy Framework Governing Contractual Engagements - The Council does not have a separate policy

for managing contractual agreements but merely follows the Manual of Accounts. Nadi Town Council

agrees that there is no detailed project planning schedule but has the following details as mentioned

below:

	Different Task Name

	Budget Allocation.

We will make sure that the details as outlined on page 11(4.2.3) will be incorporated in the future

projects.

From the past review done by the Office of the Auditor General, Council has made improvements governing  the

Policy Framework for Contractual Engagement in terms of Risk Assessment but this is only evident in contracts that involves large infrastructure building where consultants are engaged to cover the monitoring of the projects and the risk associated with the project planning. Due to the council not having appropriate human resources capabilities, it has been emphasised that the total contract oversight is outsourced to specialists who are equipped with the skills and capabilities to manage the contract. Nevertheless, the council project team also assists the consultants to see that the project is in line with the scope and time for the deliverance of the entire project.

It has become a necessaity that the contractors have public liability coverage and also covers for workmens compensastion to mitigate the risk associated with the Council activities.

Nasinu Town Council

The Nasinu Town Council fully support the recommendation made that the existing Manual of accounts

for the Municipal Councils in Fiji should be reviewed. It would be of great benefits to the Councils if the

revision also takes into account all the financial, administrative and any other issues related to the

operations of Municipal Councils. In this way the Municipal Councils will have a uniformed policy for

running the Councils.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	14

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

The recommendation on the proper project planning will be discussed with the section concerned and will

be implemented immediately.

Risk analysis and assessment throughout the contract period will now be carried out by our Internal

Auditor.

Nausori Town Council

1.  A special monitoring policy shall be established by council to ensure amongst other things

requirements of documentation of monitoring activities.

2.  Council has established a resolution where overall evaluation of a contractual arrangement

(including Human Resource) is undertaken following expiration of the contract.

Suva City Council comments

Auditor General’s comments are noted that the Council is generally incompliance. In absence of a revised

Contract Policy in place by MLG, we do have the Procurement Procedure in place. We’ll ensure all staff

handling procurement issues are trained and follow same.

At the outset, as a municipality, proactively our most desirable goal is where possible to completely

eliminate the risks and at places where it cannot be eliminated is to minimize it. Risk assessment is

somewhat a new concept now being factored into Contract management which was not separately

incorporated into conventional contracts but mostly embedded in. This does not mean that we do not

manage risks. Under the Agreements it is a prerequisite that each Contractor provides following

Certificates of Insurance as a strategy to transfer greater percentage of the risk;

	Performance Bond

	Public Liability coverage

	Workmen’s compensation

Besides because Council is a public entity we have our own comprehensive Public Liability coverage with

our Insurance Company. With regards to maintenance Contract administration, claims arising out of non-

performance by the ratepayers against Council is very minimal. The type of work we do is basic municipal

services through engagement of Contractors. A service contract generally includes terms about a

contractor’s labour, time or effort to perform a service. This is really a day-to day cleansing service issue

does not directly constitute of financial loss to Council, Contractor or the ratepayer. In essence if service

is delayed by the Contractors, then Council has a contingency plan as a back- up flying gang who quickly

move in to complete. Substantial potential risks are eliminated in our rigid screening process when we

choose the right Contractor.

Again, the contract is a primary document, which is reviewed as & when required to help those involved

to know and respect the roles of the parties to the contract, among other things. Needless to stress that

appropriate and timely performance monitoring and documentation, and maintaining a business

relationship are important contributors to successful service contract administration. When choosing a

municipal entity as a service provider, the Municipality retains accountability for service provision and

the success of the municipal entity despite the fact that the Municipality has outsourced the function. The

Council is explicitly obliged to ensure the municipal entity is managed responsibly and transparently, and

meets it statutory, contractual and other obligations. Some strategies adopted by the Council to minimize

risks are as follows

Meetings - We conduct Contractors meetings before the contract work begins. Such meetings may help

clarify the procedures to be used during the performance of the contract work and enable management &

contractors involved to better understand various perspectives and expectations.

This approach may help build a strong relationship based on cooperation and mutual respect. Such a

relationship may later help the contractor and municipal staff to reach a mutually satisfactory resolution

to any contract performance issue should it arise. Besides we also have quarterly meetings where all the

Contractors are present to discuss issues concerning work performance and other contractual related

issues. These face-to-face meetings are all important in building a close healthy working relationship.

When the municipal staff and the contractor already have a professional relationship in place, these

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	15

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

preliminary meetings often focus on changes in the work environment since the previous contract work

was carried out.

Performance Monitoring - Monitoring the contractor’s performance provides information needed to help

ensure that contracted services are being delivered. It may also strengthen accountability, help improve

performance, stimulate productivity and creativity. We have in place an acceptable level of performance

system in place on daily basis, through checklist and reporting mechanism.

Relationship Management - Relationship management is about understanding the needs of contractors

and satisfying those needs while building trust between all parties. Sound contract administration is held

together by people, not by forms, surveys, diaries or other monitoring tools. It often depends more on the

skills of the contract monitors than on particular monitoring methods or forms used. With many years of

experience our Field Staff are able to attain this essential expertise.

There is always an element of “trust” we understand as a non-written agreement between parties, based

on friendship, respect, past experiences, convenience. It is less specific than the contract in terms of

regulations, price, expected return and way of managing disagreement. From our experience even the

most stringent of the Contract will practically become difficult to manage if the element of trust is missing.

In municipal service delivery contract the services must go on as opposed to practical solution on

Contracts being abandoned, taking legal action against the party is both cumbersome and costly and if

anything financial pay-back hardly comes our way.

Payment system - Our payment system is on a retrospective mode meaning the Contractors invoice upon

completion of works on a monthly basis. There is no advance payment released. So always we pay for the

value of works done, which in any case will always be below the Contractual price. More over there is

provision in the Contract for penalty clause where appropriate deduction is made for work/activities not

done or for that matter not performed up to standard.

Further OAG Comments

	Suva City Council

The Council‟s initial response only described processes and procedures followed by the Council for tender and

contracts. Following further consultation, the Council agrees that it will incorporate risk management in future

contracts and tenders.

	Nausori Town Council

Further discussions with the Council‟s Chief Executive Officer confirmed that initial assessments for project planning

are conducted by technical personnel from engineering and building sections. Considerations determine how the

projects will be implemented (methodology) and resourced, that is, whether projects will be fully outsourced (i.e.

General contracts whereby contractor provides all labor and materials, and the Council‟s technical officer will

supervise works); partly outsourced (i.e Labour contract where the Council provides materials and the contractor

provides labour only); or the project is completely undertaken by the Council (in-house work).

The Council agreed that continuous risk analysis and assessment is not done throughout the contractual period.

However the Council considers in house works as having high risk compared to outsourced contracts as projects are

managed internally and all resources are provided by the Council. Fully outsourced contracts pose less risk as they

only require overview monitoring and validation of work at the end of the contract.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	16

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.0 KEY ELEMENTS OF CONTRACTUAL

ENGAGEMENTS

This section of the report looks into key elements encompassing contractual

engagements by the Councils. This includes the human resources involvement,

tendering of contractual works, records management and payments of contractors.

5.0.1	Human resources play a critical role in the proper management of contracts within the

Councils. As such the Councils should ensure that staffs have the capability to effectively

administer activities relating to contractual engagements.

5.0.2	It is pivotal that tenders are called for all contracting works planned by the Councils.

Tendering of such works clearly indicates transparency in the contractual engagements

and ensures value for money is achieved.

5.0.3	All records that are created and received in contractual arrangements, whether paper

based or electronic, should be captured in the Councils recordkeeping system. A

systematic approach to recordkeeping at the beginning of the contractual engagement

and throughout the contracting cycle will assist the Council to provide evidence of

business conducted and decisions made, manage legal and other risks, and meet its

accountability obligations. As such, keeping good records should be seen as an integral

part of, rather than incidental to, contracting activity.

5.0.4	Payment of contractors by the Councils should follow a proper process. The Councils

should ensure that payments are made when works or services are conducted to the

satisfaction of the Council and within the requirements of the contractual agreement.

5.1 Human resources involvement in contractual works

5.1.1	Staffs involved in contracting arrangements should have at a minimum a broad

understanding of the policy framework as well as practical work knowledge of contracting

practices that apply to the particular contracting activity in which they are engaged.

5.1.2	Technical expertise should be sought externally by the Council if it is not available in-

house or if required.

5.1.1 Technical expertise in the identification of contracted works

5.1.1.1 The identification of works or projects to be contracted by a Council should follow a

rigorous and detailed consultation and evaluation process. Technical expertise is critical

in the identification of such works.

5.1.1.2 Under the current practice in most Council, the responsibility of identifying the contract of

services is done by the different Departments within the Councils. It was noted that all

works contracted out by the Councils were results of initiations proposed by the technical

personnel in their various Departments.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	17

| Department within council | Responsible Technical Personnel | Works usually identified by the department |
| --- | --- | --- |
| Health & Environment |  Director Health Service  Senor Health Inspector  Health Inspector |  rubbish collection  transportation to the rubbish dump  other hygiene service. |
| Works |  Director Engineering Service  Senior Engineer  Engineer |  cutting of the grass.  maintenance work on the roads.  upgrading of public utility facilities e.g. picnic parks, walkways inside the town and city boundaries. |
| Building |  City/Town Planner |  maintenance or repair of existing buildings.  construction of new building.  renovation and upgrading of buildings. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.1.1.3 The different projects contracted out by the councils are directly related to the various

departments that exist within the Council. Tabulated below are the three main

departments that commonly exist in most council with details of works to be contracted:

Table 5.1: Main departments in councils visited and works identified to be contracted out

5.1.1.4  Audit noted that for all Councils visited only Nausori Town Council did not have an

Engineer and Health Head for certain period but there has been continuous project work

on both departments contracted out indicating the absence of technical input in the

identification of projects for contracted purposes for the two departments.

5.1.1.5 In the absence of technical expertise the Council may end up identifying the wrong

projects to be contracted out which may result in the Council incurring additional costs on

the specific work then that initially planned.

5.1.2 Contract management skills and knowledge

5.1.2.1 A range of skills and knowledge are required throughout the contracting stages. The

types of skills and knowledge required vary with the different stages of contracting

services and with the size and nature of the services required. As such it is critical that

officers of the Councils involved in managing contracts are appropriately trained in the

areas of contract management.

5.1.2.2 The successful management of contractual works would generally require skills and

knowledge in the areas outlined below:

Table 5.2: Contract management skills and knowledge

Skills and knowledge	 Details

Interpersonal	and		Undertake tasks in a motivated and professional way

relationship		Build strong relationships.

	Encourage co-operation and communicate orally in writing.

Project management		Plan, schedule, organise work, manage tasks and consult with

stakeholders

	Establish relationships to get tasks done in a timely way

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	18

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Managing contractors		Understand tender criteria and evaluations

	Able to understand and ensure compliance of contractual

agreements.

measurement         	

Performance

Provide feedback both positive and negative

Problem solving		Have positive approach to solving problems

	Encourage mutual co-operation to address issues

	Have the ability to make decisions in circumstances where

there may not be full knowledge of all relevant facts in the

available timeframe

5.1.2.3 It was noted that the Councils officers involved in the contract works process generally

lack some of the skills and basic knowledge of contractual works. Officers in charge of

handling tenders have not undertaken any formal training on contracts management

and/or tender process including monitoring of contractual works.

5.1.2.4 Training of officers on contract management has the potential to ensure proper and

effective management of contracts by officers of the Councils.

5.2 Tendering of contractual works

5.2.1	The Councils should ensure that tenders are called for all contracting works/services.

Tendering of such works indicates transparency in the contracting services and allows the

Councils to secure the right contractor to carry out the work.

5.2.2	A proper and transparent process should be in place governing the evaluation of tenders.

This requires the existence of a proper evaluation criteria and transparent evaluation of all

tender proposals.

5.2.3	It is also important that the Councils maintain proper documentation to evidence all

activities relating to the contractual engagement.

5.2.1 Responsibility of evaluating and approving tenders

5.2.1.1 To ensure transparency in a Council setting it is important that the responsibility of

evaluating tenders and approving tender allocations are conducted by two separate

parties.

5.2.1.2 Scrutiny of the tender minutes in most Council revealed that Council officials made up the

committee members that make decisions on the opening and vetting of tenders received.

The members of the committee mainly comprise of Heads of Departments (HODs) who

are also the parties responsible for proposing works to be contracted.

5.2.1.3 Audit further noted that in most of the Councils visited the Heads of Departments are also

the main party regarded as the Council that deliberate on the awarding of tender. Refer to

the following table for details:

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	19

| Municipal Council | Details of tender deliberations |
| --- | --- |
| Ba | Council has two meetings. The first meeting is the tender committee meeting where they analyse and prepare a report on the applicants. Tender reports is discussed in the staff and tender board meeting The final approval is sought from the council meeting and once approved the approved tender letter is issued to the successful tenderer. |
| Lami | The tender committee analyses the tenders and submit the report either to the ordinary council meeting before its onward submission to the full council meeting. |
| Lautoka | Tender committee opens the tenders which comprises of the Heads of Sections who analyses the applicants and a report is prepared during the Development and finance committee meeting. Once they approve on the tenderer the final approval is sought from the full council meeting before the tender letter is being issued. |
| Nadi | Two meetings are conducted. First meeting is the tender committee meeting where they open the tender box and analyses the applicants. Once the report is presented either the following meetings the Development, Finance or Engineering depending on the nature of the tender. Further to the above, the departments involved are as follows: Health – Garbage Contract Building – Infrastructure Building Engineering- Services and other works Finance – IT In the first meeting where the tender is been opened, the Council is also working towards opening the tenders right after the closing time and the contractors are also been invited with a Police Officer. In this meeting the tenders are opened and the tender sum is also disclosed and recorded in everyone’s presence and the tender documents are either signed by the SA or CEO. The whole tender documents are then given to the respective HOD who will analyze and provide a detailed submission in the respective HOD Committee monthly meeting for further deliberation and selection of the contractor to be engaged. |
| Nasinu | A meeting titled “Finance & Tender Sub-Committee Meeting” is called where all HODs are committee members. The SA usually chair the meeting and the HODs will have to provide proposals on the respective projects contracts which favor the Council to undertake. |
| Nausori | The Council has two separate meetings held to discuss the tender for contracts.  The first meeting is called “Opening of Tender Documents Meeting” where there is no restriction to the members of the Committee and any of the TC officials present at the meeting can chair the meeting.  The second meeting is made up of the individual Department‟s “Sub Committee Meeting” where the Special Administrator usually chairs the meeting. |
| Suva |  The day and time a tender closes a meeting is held where the tenderers and public are present as well. The staffs from S.C.C are present including Directors of each section, City Lawyer, Administration Secretary and the Special Administrator. Tenders are opened and announced. As soon as the bids are announced the meeting ends.  All the tenders submitted are evaluated on the documents furnished. This is discussed in the monthly council meeting held each month. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 5.3: Details of tender deliberations

5.2.1.4 The above observations question the independence of the tender committee and the

ultimate awarding of tenders.

5.2.2 Evaluation and documentation of tender

5.2.2.1 The evaluation of tender responses is the most important aspect of the value for money

consideration. As such it is essential that decisions should be taken strictly on the basis

of evaluation criteria to appropriately evaluate tender responses and justify selection of

the successful supplier.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	20

| Councils | Existence of documented tender evaluation criteria? | Audit comments on criteria |
| --- | --- | --- |
| Suva | Yes |  Criteria are quite limited and do not extend to include evaluation of the suppliers‟ experience, capability and capacity, technical support, evaluation of performances in engaged contract with the Council etc.  No scaling and points allocation to each criterion. |
| Lami | No |  Council apply the lowest tender criteria |
| Nausori | No |  Council apply the lowest tender criteria |
| Nasinu | No |  Council apply the lowest tender criteria |
| Lautoka | No |  Council apply the lowest tender criteria |
| Ba | No |  Council apply the lowest tender criteria |
| Nadi | Yes |  Council has a detailed criteria in place outlining the following:  Contract sum  Within approved budget  Performance if engaged in previous contracts with the Council  Insurance  Work knowledge and experience  Tools plants and machinery  Scaling and points system are applied to each criteria. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.2.2.2 Tenders should also be evaluated by an officer competent to do so. Where expertise is

not available within the Council for evaluation of tenders, local and/or overseas

consultants, if necessary, will be engaged to evaluate tenders, local and/or overseas

consultants, if necessary, will be engaged to evaluate tenders.

5.2.2.3 Appropriate documentation tender evaluations should be made to ensure that the process

has been adhered to in a transparent manner. Risk assessment also needs to be

undertaken on tenders received.

5.2.2.4 The common tender evaluation criteria used by most the councils are that the lowest

bidder usually awarded with the contract. However, the lowest bidder approach cannot be

applied if there are high technical works that require high cost equipment and service

providers. Our audit at the various Councils visited noted the following observations in

respect to the existence of tender evaluation criteria:

Table 5.4: Details of evaluation criteria

5.2.2.5 In addition, the overall documentation of the tender evaluation was lacking in some of the

Councils visited. Report summary on the tenders and their selection were not included in

the file.

5.2.2.6 The absence of tender evaluation criteria in most of the Councils may indicate that the

selection of a contractor with the most appropriate capability and capacity is not a priority

in the allocation of tender. Furthermore, the lack of documentation in the evaluation

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	21

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

process indicates lack of transparency and accountability in the tender process followed

by the Councils.

5.2.3 Contractual agreement

5.2.3.1 A formal contract for contractual engagement should be entered into with the Contractor

who has been approved to carry out the contracted works.

5.2.3.2 Contractual agreements are legally binding and are drawn up to ensure that required

works are carried out in accordance to its requirements. A contract is required where the

nature of the relationship with the supplier involves the need to specify certain

requirements that the contractor should be aware of.

Format and contents of the agreement

5.2.3.3 When drafting a contract it is important to include clauses that protect the interests of the

Council. These same clauses frequently also offer protection to the contractor.

5.2.3.4 Review of existing contractual agreements provided by the Councils visited found that all

of the contracts included requirements covering insurance, liabilities and indemnities and

payment arrangements. However a number of key items were not included as part of the

contracts. Also most of the contracts did not have a proper format. Refer to the following

table for details:

Table 5.5: Contract anomalies pertaining to format and contents of Councils visited

City/Town	Contract (s) examined	Audit comments

Council

Ba	Ba Town Council and		Contract is not appropriately divided up into

Lalesh Naidu trading as	different sections with specific headings.

Laka Transport for the		A number of key items are not included as part of

disposal of garbage	the contract. The items include:

	Contract variations - formal procedures

specifying the mechanism to be used if the

contract needs to be varied.

	Disputes	-	provisions	specifying	the

requirements on both parties if a dispute

arises during the performance of the

contract.

	Termination	and	contract	end	dates-

provision that allows the Council to terminate

a contract for convenience. The end date of

the contract should also be specified.

	Confidential information - clauses relating to

how confidential	information is	to be

identified, dealt with and returned on

completion of the contract.

Lami	Lami Town Council and		Contract is not appropriately divided up into

Construction	Equipment	different sections with specific headings.

Hire Limited for the Backfill		A number of key items are not included as part of

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	22

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

and leveling of Tikaram

Park

the contract. The items include:

 Disputes - provisions specifying the

requirements on both parties if a dispute

arises during the performance of the

contract.

	Termination and contract end dates -

provision that allows the Council to terminate

a contract for convenience. The end date of

the contract should also be specified.

	Confidential information - clauses relating to

how confidential	information is	to be

identified, dealt with and returned on

completion of the contract.

Lautoka	Lautoka City Council and		The General Condition of the Contract is not

Ambika Nand for grass	appropriately divided up into different sections

cutting and cleaning of	with specific headings. The Special Condition of

drains in Waiyavi Ward	the Contract is divided up into sections.

Area „B‟		A number of key items are not included as part of

both the General and Special Condition of the

contract. The items include:

	Contract variations - formal procedures

specifying the mechanism to be used if the

contract needs to be varied.

	Confidential information - clauses relating to

how confidential	information is	to be

identified, dealt with and returned on

completion of the contract.

	Disputes	-	provisions	specifying	the

requirements on both parties if a dispute

arises during the performance of the

contract.

Nadi	Nadi Town Council and	A number of key items are not included as part of

M.Y.Azaad Transport for	both the General and Special Condition of the

the collection and removal,	contract. The items include:

cartage and disposal of

garbage at LCC‟s rubbish		Confidential information - clauses relating to

dump.	how confidential	information is	to be

identified, dealt with and returned on

completion of the contract.

	Termination and contract end dates -

provision that allows the Council to terminate

a contract for convenience. The end date of

the contract should also be specified.

	Penalties - penalties for contractor under-

performance.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	23

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Nasinu	Nasinu Town Council and

Kinoya	Old	Boys

Association	Company

Limited	for	the	grass

cutting on road side and

cleaning of drain.

The contracts are appropriately divided into sections

with specific headings. Apart from the confidential

information clause the contracts include all other key

requirements.

information   and   termination,   penalties   and

contract end dates requirements.

 	The second contract did not specify confidential

variation and penalty requirements.

Nasinu Town Council and

Waste Clear Fiji for the

collection or garbage and

removal to Naboro landfill.

Nausori	Nausori Town Council and		The three signed contracts all have different

Viti e Loma Youth Club for	formats.

the raking and maintaining		The General Condition of the first contract did not

the drains, mowing the	divide requirements into sections and with

lawns and road verges.	separate headings. The Specific Condition

divided up requirements into sections and under

Nausori Town Council and	separate headings.

e-Care	Environmental		The first contract did not specify confidential

Consultants for the initial

environmental

examination.

information, disputes and penalty requirements.

Nausori Town Council and		The third contract did not specify contract

Tahila Group for the pre-

feasibility study for the

proposed relocation of the

market	and	transport

terminal

Suva	Suva City Council and		Contract is not appropriately divided up into

Constructive Builders for	different sections with specific headings.

the	construction	of		A number of key items are not included as part of

compost site building	the contract. The items include:

	Disputes - requirements on both parties if a

dispute arises during the performance of the

contract.

	Termination	and	contract	end	dates-

provision that allows the Council to terminate

a contract for convenience. The end date of

the contract should also be specified.

	Confidential information- clauses relating to

how confidential	information is	to be

identified, dealt with and returned on

completion of the contract.

5.2.3.5 The non-inclusion of several key requirements in the existing contracts by most of the

Councils indicates that their interests may not be adequately protected in the contractual

arrangements.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	24

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Vetting of contracts by a solicitor

5.2.3.6 As contracts are legal documents it is pivotal that all contractual agreement between a

Council and its contractors are vetted by a solicitor.

5.2.3.7 Our review of the contracts entered into by the Municipal Councils revealed that some of

the Councils do not have their contracts with the contractors vetted by a solicitor. Refer to

the table below for details.

Table 5.6: Details of contract vetting by a solicitor

Councils	Contract vetted by solicitor?

Ba	No as the contracts are on-going

Lami	Yes

Lautoka	Yes

Nadi	No – All contracts are now being vetted by the Solicter Generals Office

Nasinu	Not vetted by solicitor despite having a legal section in the Council

Nausori	No legal section to vet contracts but Council outsourced any legal service required

Suva	Yes vetted by the city solicitor

5.2.3.8 Non vetting of contract agreements by a solicitor could expose the Councils to future

lawsuits.

Contractor engaged and re-engaged through a formal letter

5.2.3.9 Upon expiration of a contract the terms and conditions of the existing contract should be

reviewed before the contract is renewed. Also the contractor‟s performance should be

appropriately evaluated before the decision of extension of the contract is made.

5.2.3.10 It is important that a contract is drawn up and signed by both the Council and the

contractor before the services are rendered or continued to be rendered.

5.2.3.11The audit found that contractual agreements between the Lautoka City Council and two

contractors had expired and the contractors were informed through a letter to continue

providing the service without the contract being renewed.

In addition the audit found that Nasinu Town Council engaged a contractor without a

contractual agreement signed. The contractor was only provided with the letter indicating

award of contract. The following table provides further details of these engagements:

Table 5.7: Anomalies noted in the existing contracts

Council	Contractor/Services	Remarks

Lautoka City

Council

Sheik Mohammed-

cleaning of the Park

Ravindra Kumar

Collection and disposal

of refuse

Contract expired on Jan 10th 2014 and the Council vide

letter dated 3rd Jan 2014 to continue until 29th June 2014.

Contract had expired on 10th Jan 2013 and the Council

advised the contractor to continue till Feb 1st 2013 and then

continue till June 2013 where a new contract was later

awarded to the supplier.

Council     	Hire of Truck - Collection

Nasinu Town

and disposal of garbage

– A Kumar Transport

No contract was developed for this contractor. On 13th May,

2011, the Nasinu Town Council provided a letter to

acknowledge the receipt of A Kumar Transport tender and

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	25

| Date | Cheque Number | Amount |
| --- | --- | --- |
| 13.06.13 | 310217 | 168,643.22 |
| 20.11.13 | 310239 | 10,000.00 |
| Total |  | 178,643.22 |

| Years | Amount $ |
| --- | --- |
| 2011 | 124,825 |
| 2012 | 106,000 |
| 2013 | 125,712.5 |
| 2014 (first 4 months) | 113,755 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

also on the same letter agree to award him with the

contract. For the past 3 years, Nasinu Town Council has

paid A Kumar Transport with the following amount:

The total amount paid annually to this contractor is

substantial when compared to the total budget of the council

e.g. in 2014, the Health Service Department have been

allocated with $978,700 but within the first 4 months, the

Nasinu TC has paid almost 12% of its total annual budget

allocation to the contractor.

5.2.3.12 The use of existing contract without proper renewals indicates that the Councils

engagement of contractors for the extended period has no proper legal basis.

Engagement of Ravindra Singh & Company by Nausori Town Council

5.2.3.13 A contractual agreement was entered into by Nausori Town Council and Ravindra

Singh & Company.

5.2.3.14 Our review of the contractual agreement relating to the engagement of the contractor

noted the following:

	the agreement was not dated and not signed by either parties but the Council had

paid $178,643.22 to the contractor in 2013 alone. Refer to the following table for

details of payments made.

Table 5.8: Payments made to Ravindra Singh and Company in 2013

 	The nature and scope of the service provided was not clearly outlined in the contract.

The term used in the contract is “Service Provider” but the type of service was not

mentioned. The accounts section stated that the contractor was involved in some

construction work and the work was verified by another contractor namely “E-

Designs”.

	Our review conducted at the Registrar of Company‟s Office found that the company

just commenced business on 11/03/12 and is based in Matei, Taveuni raising

questions as to why a similar contractor in the Central Division was not engaged for

the service.

5.2.3.15 The above findings raises questions of transparency in the engagement of the contractor

by the Council.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	26

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.3 Records Management

5.3.1	Records management is crucial to all organisations unless to account for what has

happened in the past or to make decisions about the future. Records are a vital, corporate

asset and are required:

	to provide evidence of actions and decisions;

	to support accountability and transparency;

	to comply with legal and regulatory obligations, including employment, contract

and financial law,

	to support decision making;

	to protect the interests of staff and other stakeholders.

5.3.2	Recordkeeping involves making and maintaining complete, accurate and reliable

evidence of business transactions and is primarily the responsibility of all staffs within an

organisation.

5.3.1 Maintenance of file on contractual works

5.3.1.1 A file should be maintained for all tenders received in respect of what the tender is for and

all the documented work carried out up until the tender is awarded. All the relevant

supporting documents to substantiate the award of tender should be contained in the

files.

5.3.1.2 Key documents that should be retained during the contract management phase and

contained in the file include the following:

	Copy of the contract signed by both parties

	Risk assessments

	Contract management plan or checklists

	Records of payments

	Records of performance

	Variations to the contract

	Assistance or expert external advice received

5.3.1.3 It is important that the most up to date version of the contractual agreement incorporating

any variations is appropriately maintained in the file as it provides the basis for making

payments to the contractor.

5.3.1.4 A review of the files maintained at the Councils revealed the following observations:

Table 5.9: Observations on maintenance of records by Councils

Council	Audit Comments

Ba	File maintained for the contracts but all the necessary information pertaining to

the tenders not in the file. Papers filed in the files are not serially numbered.

Lami	File maintained but does not have all the necessary information pertaining to the

tenders. Papers filed in the file are not serially numbered.

Lautoka	Files maintained for the individual tenders with contracts but the papers in the file

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	27

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

are not serially numbered.

Nadi	Files maintained by the respective sections pertaining to the tenders of the

contracts were given for audit. Record maintenance was poor Papers filed in the

file were not serially numbered.

Nasinu	No copies of contracts maintained by the Registry Section but maintained by

respective Departments but not completed. The SA‟s secretary maintained all

the minutes in regards to any contracts undertaken.

Nausori	The Accounts Section maintaining all the operational contract files whilst the big

capital project contract files are maintained by the Project Manager. All the

minutes are kept by the SA‟s secretary.

Suva	Files maintained for the individual tenders with contracts etc. Files are serially

numbered. Documents filed in the file are not sequentially numbered.

5.3.1.5 In the absence of proper records there would be no clear trail of contractual activities

undertaken and Council management would not be in a position to make timely decision

regarding tender and contract engagements.

5.3.2 Existence of contracts inventory and register

5.3.2.1 Councils should compile a contracts inventory which lists and classifies all contracts. A

classification system must be established which identifies the classifications of contracts

taking into account at least the contract type or nature, strategic importance of the goods

and services, contract value, contract duration and contract complexity.

5.3.2.2 The contracts inventory should be entered into a register. A register containing all

contracts of the Council should be maintained centrally and a number of sub-registers

maintained by various departments of the Council that collectively represents the

Council‟s contract register centrally maintained.

5.3.2.3 Our examination at the Councils visited found no existence of contract inventory. In

addition all Councils visited did not maintain a contract register detailing all contracting

works/service of the Councils over the years.

5.3.2.4 In the absence of a contract inventory Councils would not be in a position to adequately

and efficiently establish the number of the contracting services they have engaged in.

5.3.2.5 The maintenance of contract register facilitates the effective monitoring of contract end

dates and opportunities to exercise contract extensions.

5.4 Payments of contractors

All payments authorised and payable to the contractor should be made strictly in

accordance with the provisions of the contract.

The Council should ensure that payments are made to contractors after proper evaluation

of work performed.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	28

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.4.1 Controls in payments of contractors

5.4.1.1 Internal controls can generally be classified under the headings of approval, authorization,

verification, reconciliations, and segregation of duties, analytical review, physical controls,

management controls, processing controls, computer controls and monitoring controls.

5.4.1.2 Before payment is made, a supplier invoice should be checked and approved by the

person who placed the original order to ensure it shows: the correct goods, the correct

quantity and correct price (including any agreed discounts).

5.4.1.3 Our review of the payment process revealed that all the Councils have a process in place

for payment; however there were lack of general internal controls in most Council. Refer

to the table for further details.

Table 5.10: Details of internal controls on contractual payments

Councils	Process of Payments	 Remarks on the internal control in payment process

Ba	Payments	are	made

fortnightly for garbage

collection services and

weekly	for	security

services.

Lami	After completion of work

invoices are raised and

passed on to finance for

payment.

 The Council uses MYOB for the payment process.

 The Department of Health signs on the invoice

certifying the work have been done.

 No reports were provided to substantiate the

verification done by the Department of Health.

 Copies of payment vouchers were not filed in the

individual contract file.

 No evidence in the payment voucher to show that

verification that the work was done according to

the contract before payment is done.

Department it  is  assumed  that  every  process  is

being followed because the invoice is signed off

which   signifies   that   the   invoice   is   ready   for

payment. Insufficient documentation to support the

verification of the work done by the contractor.

   No contract payment register to record payments

Lautoka	After completion of work,		Payments are made after review of supporting

invoices are raised and	documents, work done according to standard

passed on to the finance	requirements, certification and authorization.

department to prepare		For	grass	cutting	contract	inspection

the cheque. The cheque	measurement form are filled by the Horticulture

is then forwarded to the	Department to indicate that the work has been

signatories for signing.	done by the contractor and the garbage contract

invoice are certified by the department of Health.

	No reports to substantiate the verification done by

the Council.

	Copies of payment voucher not filed in the

individual contract file.

Nadi	The	invoices	are	 No supporting document is attached when the

submitted	by	the	invoices are submitted to accounts.

Engineering	and	the	 The accounts clerks always check for sign offs.

Health	Department	 Work done according to standard requirements is

signed	off.	Payments	checked by the department concerned.

clerk	prepare	the	 When	the	invoices	are	forward	Finance

payment vouchers and

checks that the amount

in the invoice matches

the	monthly	contract

amount to be paid to the

contractor

made to the contractor.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	29

|  | - Currently, the grass cutting and drain cleaning contract provides reports in the areas of the contract and this is also signed off by the officer responsible to check that the contractors has performed as per the contract. - The Council has also initiated a payment register to record payments made to the contractor |
| --- | --- |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Nasinu	Invoices are first verified

by the supervisors in the

fields	before	cross

checked by HODs and

submitted	to	Finance

Section for payments.

Nausori	Invoices are first verified

by the supervisors in the

fields	before	cross

checked by HODs and

submitted	to	Finance

Section for payments.

Suva	Any	claims	by

contractors are checked

before any payment is

made. The percentage of

work	or	schedule	of

works as stipulated in the

contract	must	be

completed	for	any

payments	are	to	be

 In some capital work construction, members of the

local communities near work sites were paid by the

council to supervise the work on behalf of the

council.

 Documentation from the field officials is

satisfactory.

 Internal controls in the Finance Section are good.

 The Council does not have the capacity to check or

verify the capital projects works under ITP, thus

the reliance on the project manager to verify on

behalf of the council

 The Council paid the Project Manager without any

independent verification on the work undertaken by

the Project Manager

 Ward inspectors check the respective works in the

ward daily. Reports are prepared and sent to the

Health Inspectors.

 Internal controls in the Finance Section are

functioning well as supporting documents are

checked before payments are authorized.

made.

For grass cutting and

drainage	cleaning

contracts, payments are

made after reporting and

validating officers check

the areas. Then this is

certified by the certifying

officer. After all this then

payment is authorized.

5.4.1.4 The payment process practiced by the various Councils is guided by the Manual of

Accounts. Some of the Councils visited have also developed their policies including

accounting manuals and procedures.

5.4.1.5 The non-compliance to the internal controls in place within the various Councils could

encourage fraudulent practises amongst the Council officials.

5.4.2 Deposit payments made by Suva City Council to Construction Builders

5.4.2.1 The Suva City Council entered into a contract with Construction Builders for the

construction of Compost Site Building on the 31st of May 2013. The funding for the

construction works was provided by the Japanese Embassy.

5.4.2.2 The contractual agreement between the Council and the contractor indicated provisions

for progressive payments as follows:

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	30

| Description | Amount ($) |
| --- | --- |
| Deposit | 7,920.00 |
|  Site clearance  site layout and profiling  footings and pad layout  pole arrangement and filing concrete  floor layout for shed  floor layout for office. | 5,500.00 |
|  Office layout  Shed structure layout  Shed roofing  Shed finishing  Office side wall fixing | 7,200.00 |
|  Office interior finishing  Sink, WC, table, door fixing, window fixing  Office painting | 2,360.00 |
| Finishing | 1,020.00 |
| TOTAL | $24,000.00 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

“That the SCC shall pay consideration to the Contractor for its services in the total sum of

Twenty Four Thousand dollars ($24,000) inclusive of Value Added Tax. The consideration

shall be paid in progressive stages payments as set out in the Schedule of payments and

upon the completion of the contract having being satisfactorily performed of completion of

the specified works and upon producing a Certificate of Practical Completion to that effect

issued by the Director Engineering Services or his authorised representative.”1

5.4.2.3 The Schedule of payments included as Annexure C of the contract outlined the

breakdown of the amount agreed between the two parties as follows:

Table 5.11: Contractual sum agreed

5.4.2.4  Audit found that the Council made the deposit payment of $7,920 to the contractor as

stipulated in the contract. However, the contractor did not complete the work and the

Council had to complete the project from where the contractor had left of.

Our discussion with the Council management gathered that the reason the deposit

payment was included in the agreement to be made were due to the following reasons:

	that it was required by contractors as a protection for non-payment; and

	suppliers may not have enough capital to purchase the item.

5.4.2.5 The Council‟s monetary calculation of the work conducted by the Contractor totaled

$5,278.59 indicating that the Council had been overcharged by $2,091.41. Audit gathered

that the amount was not re-imbursed by the Contractor to the Council. Our review of the

contractual agreement found that such situation was not addressed in the contract. The

Council however did not make any further payments to the contractor as stipulated in the

contract.

1

Clause 2

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	31

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.4.2.6 The above deficiency indicates that the Council did not conduct a thorough evaluation of

the Contractor‟s capability in terms of both financial standing and technical knowhow to

effectively carry out the construction works.

RECOMMENDATIONS

All Councils

All Councils should:

	ensure that staffs involved in contractual works are adequately trained with the appropriate skills and

basic knowledge of contractual engagements.

	create contracts inventory to identify control management at the various levels of the contracts

undertaken.

	ensure independence and transparency in the allocation of tender. All Councils should ensure that the

authorizing party making the decision of tender allocation does not entail all officers included as the

members of the tender committee. The authorizing party should include:

	the Special Administrator;

	the head of the section whose services is required to be contracted;

	the head of the Finance section and

	two representatives from the ratepayers.

	ensure that proper documentation is maintained to adequately reflect tender evaluations.

	ensure that key items specified in this report are integrated as part of their existing contractual

agreement.

	ensure that proper records are maintained to evidence activities relating to contractual works. Files

should be appropriately numbered for ease of reference.

	ensure that a contract inventory is maintained which should be entered into a register. The contracts

must be classified in terms of contract type or nature, strategic importance, contract value, contract

duration and contract complexity. The register should be updated on a regular basis as and when

contracts expire or new contracts are entered into by the Council.

	ensure that stringent internal controls are in place on the payment of contractors. Payments made to

contractors should be properly supported with relevant documentations. Proper documentation should

be maintained to evidence payments made.

Nausori Town Council

The Nausori Town Council should:

	ensure that an Engineer and Health Head are recruited to facilitate proper identification of projects to

be contracted out.

	develop tender evaluation criteria to use for evaluating tenders received. A scaling system should be

used to apply the criteria when evaluating tenders.

	ensure a standard format is used for its contractual agreement. The contracts should be appropriately

divided into sections with proper headings.

	ensure that contractual agreements are vetted by a solicitor.

	ensure that all contractual agreement drawn up for services to be rendered to the Council are signed

and properly dated. In addition the contract should specifically state the services agreed to be

provided by the contractor.

	ensure that all contractual engagements are conducted in a proper and transparent manner.

	ensure that contractors engaged to conduct services are based within the Central Division to avoid

charging of additional costs to the Council.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	32

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Lami Town Council

The Lami Town Council should:

	develop tender evaluation criteria to use for evaluating tenders received. A scaling system should be

used to apply the criteria when evaluating tenders.

	ensure that its contractual agreements are appropriately divided into sections with proper headings.

Nasinu Town Council

The Nasinu Town Council should:

	develop tender evaluation criteria to use for evaluating tenders received. A scaling system should be

used to apply the criteria when evaluating tenders.

	ensure that contract agreements are vetted by its solicitor.

	ensure that a contract is drawn up before engaging a contractor and making payments for the services

required.

Lautoka City Council

The Lautoka City Council should:

	develop tender evaluation criteria to use for evaluating tenders received. A scaling system should be

used to apply the criteria when evaluating tenders.

	ensure that the General Conditions of its contractual agreements are appropriately divided into

sections with proper headings.

	ensure that existing contracts approaching expiry term are first reviewed before the contract is

renewed. The performance of the contractor should also be reviewed prior to renewing the contract.

Ba Town Council

The Ba Town Council should:

	develop tender evaluation criteria to use for evaluating tenders received. A scaling system should be

used to apply the criteria when evaluating tenders.

	ensure that its contractual agreements are appropriately divided into sections with proper headings.

	ensure that contractual agreements are vetted by a solicitor.

Suva City Council

The Suva City Council should:

	improve its tender evaluation criteria and include other factors such as the experience of the

contractor, contractor‟s capability and capacity and past performances in contracts with the Councils.

A scaling system should be used to apply the criteria when evaluating tenders. [The issue pertaining to

engagement of Constructive Builders as raised in this report is directly related to the weakness in the

existing tender evaluation criteria]

	ensure that its contractual agreements are appropriately divided into sections with proper headings.

	improve its contractual agreement to address issues pertaining to payment of deposit as in the case of

Constructive Builders.

Nadi Town Council

The Nadi Town Council should:

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	33

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	ensure that contractual agreements are vetted by a solicitor.

Management Comments

Ba Town Council comments

When Council will make new contract with the garbage contractor the specific details as advised by the

Auditor will be included. Ba Town Council will engage Solicitor on vetting of contracts in future. Council

will follow as per auditor’s comments. However, Council has a voucher file where all the vouchers are

kept. Council will keep separate file for all contract payments and monitoring comments.

Ba Town Councils will develop tender evaluation criteria for evaluation of tenders received. Ba Town

Council will follow the advice of Auditor in the developing tender evaluation criteria for tender and the

contractual engagement will be properly divided when new contract are made which has to be vetted by

Solicitor.

Ba Town Council has a complaint register whereby all the complaints are recorded. However, Council

will ensure that it is maintained and monitored on regular basis.

Lautoka City Council comments

Details of tender deliberations - The Tender Opening Committee responsible for opening the tenders

comprising of the Special Administrator, Chief Executive Officer, Manager Finance Administration and

Human Resource Services and the Secretary opens the tender box after closing of tender. The results of

the tender are recorded in the minutes of the Tender Opening Committee and handed to the respective

Head of Departments for preparing a detailed report on the tenders and report is submitted to the

respective development committee for evaluation and assessment. The development committee then makes

it recommendation to the full council meeting for approval. Independence is maintained at all levels of the

tender process.

Evaluation criteria - The tenders at the Council are normally evaluated against the following general

criteria.

  Technical/Quality - overall level of compliance with the technical specifications.

	Price – consideration of costs and obtaining best value-for-money.

	Qualification of suppliers - business capability and capacity, including viability, staff

resources, commercial management, commercial terms, risk management, and company

quality systems.

	Relevant experience – the proven ability to supply or deliver the goods, services or works.

	Support service/warranty – providing warranty and long-term service support over the

duration of the contract, life of the product, etc.

Weighting given to cost and quality is dependent on the risk and value of the contract to be awarded. The

Council does not necessarily consider the lowest bidder but evaluates and selects a contractor based on

the above criteria.

Contract anomalies - The Council will ensure that it incorporates the recommended key items in the

newly updated contracts.

Anomalies in existing contracts - The contracts had expired and took longer than expected to finalise

tender and since it is an essential service the council has to request the current contractor to continue

performing the work under the same terms and conditions existing whilst it finalise its tender process.

Maintenance of file on contractual works - Henceforth, the Council will ensure that the documents in the

files are serially numbered.

Existence of contracts inventory and register - The Council maintains and updates the contract register

which contains all the details of contractors on a timely basis.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	34

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Controls in payments of contractors - The payment vouchers are prepared and filed in chronological

order in the payment voucher files which maintained by the Finance department, for this requirement the

council will make copies of payment voucher and file it in individual contract files.

Nadi Town Council comments

Activities of contractual engagements - Currently, it is true that the different capital works are identified

by the different departments but in Nadi Town Council the Engineering department is always consulted

before the council decides to go ahead with the project. This is further discussed at the monthly committee

meeting and from there is decisions are also made on whether we will contract out the project or have the

work done in house. Certain areas are taken into account like the urgency of the project, the cost and also

the type of expertise task that is needed to complete the project. (When a Special Administrator exists).

This process slightly changes when a council is run by nominated members from the different parties. It is

usually the different elected parties who suggest the projects with the consultation of the Engineers and

the Chief Executive Officer.

I do not agree with the report that the absence of technical expertise may result in the Council identifying

the wrong projects to be contracted out because at Nadi Town Council, the respective department with the

Engineering department itemizes the costing with the materials and the Finance department checks the

calculations. If the Engineering department and the respective department gives the wrong details to the

Finance department there will always be wrong computations done because the Finance department only

checks the calculations and the technical expertise can always under quote and over quote.

I agree that there needs to be two separate parties involved in the evaluation and also the authorizing

party. It is good to note that this was identified as per your report and we at Nadi Town Council will work

towards implementing the audit finding so that we can better manage the tenders and contracts. This will

be highlighted in the Council meeting so we as a Council can adhere to certain findings.

On the vetting of the agreements by a solicitor, Council is currently sending all contracts to the office of

the Solicitor General and this practice only started in 2014.

Nasinu Town Council comments

While we agree and will implement seven of the eight recommendations made, we feel that for bullet point

three, it would be wise to select one from a government agency and one from a statutory body instead of

two representatives from the ratepayers as we have seven Wards in our council.

We agree with all the recommendations made and we will implement them.

Nausori Town Council comments with respect to all Councils

1.  Nausori Town Council has been drawing contracts through input from respective technical areas

having appropriate experience and basic knowledge to provide relevant expertise. We have on board

two staff with Diploma in Civil Engineering (structural and civil) with experience who would provide

relevant expertise in technical area to draft contracts. For some contract we use standard agreements

and where specifically new contracts are to be designed we would get a solicitor to design a contract.

2.  Contract performance and payment recommendation would be by technical officers (assigned

responsibility) and relevant reports on the same would be tabled at council sector committee meeting

by relevant supervising officer.

3.  For Nausori town council performance and appraisal of contracts reports would be maintained by

relevant technical section such as financial matters relevant to the contracts with finance department,

supervision and performance with technical department and administration matters with the

administration department.

4.  Tender opening, analysis and recommendation would be through special tender committee

established. Tenders committee recommendation would be then evaluated and recommended by Chief

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	35

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Executive Officer to full council. Currently under the review of Local Government period all tender

committee recommendations would directly be placed to full council. Please note that Local

Government Act – Cap 125 Section 27 (2) restricts ordinary citizens and rate payers to sit in

committees to decide on financial matters. Finance committee members are strictly to be appointed

Council members.

5.  For all contracts, tender and specifications form part of the contract which would very much

established key result and required output areas. The tender and specification documents would

describe the work, resources required, supervision methodology and person supervising.

6.  All contractual agreements entered into are to national standard and quality to be competent under

law. Usually council would standard agreement to avoid reduce solicitors expenditure.

7.  All contract entered into by Nausori Town Council are properly signed by the service provider and

council. In reference to Ravindra Singh and Nausori town council, the agreement was signed by both

parties and before this an offer letter was sent to Ravindra which was accepted.

The contract agreement was based on:

-	Tender design and specification drawn by Engineering Designs

-	Expression of interest called through media advertisement

-	Interested bidders evaluated and short listed by engineered designs based on criteria established

-	Short listed bidders given tenders, specifications and designs

-	Contractors placing tenders before closing date at Tender Box located at Council main

office

-	Tender box opened by consultants and council, evaluated and awarded

Nausori Town Council comments

1.  Council has employed from 2010 two (2) Senior Health/Building Inspectors and two Diploma in

Civil Engineering (structure and civil) staffs with experience to guide on relevant key technical

areas including contract awards and supervision.

2.  For the Transport Project Council has outsourced technical services to a number of personals to

assist council in various areas as follows:

a.  Project management

b.  Project architecture

c.  Project engineering

d.  Project quality surveying

e.  Project services engineering

f.	Project financial consultants

3.  The consultants have designed and recommended all construction works to Council which had

been tabled in twelve technical committee meetings having Council and relevant government

agencies as members. Consultants have been engaged using various international professional

standard agreements designed for eleven areas.

4.  For all relevant works, council has established a benchmark for entry. Assessments would be

carried out before work commences and qualified bidders will be evaluated based on tenders

received and available internal pre assessment.

5.  Council shall consistently review its Procurement Policy and work closely with the department of

Local Government to review the existing Manual of Accounts. In 2012, a new procurement policy

has been established with an improve procurements in totality.

6.  Tender process, award and performance process have been consistently reviewed to ensure that

contractual engagements are conducted in a proper and transparent manner. In 2012, council

prepared and adapted to a Procurement Policy document.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	36

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Suva City Council comments

Agreed that the Policy governing the management of Contracts (existing 1992 Manual of Accounts by

MLG) is an out-dated document and needs to be revised urgently.

Evaluation process - Currently the evaluation is done in-house by Senior Managers in consultation with

respective Dept HOD’s thence recommendation submitted to the Council. A weighting & scaling system is

in place for HSD which will be replicated across in other Depts. To improve upon in terms of

transparency, as a way forward we will possibly rope in external party/agency like MLG staff; Solicitor

General’s Office or a senior staff of sister municipality. Our tender awarding policy is of acceptable level

if not the best as captured elsewhere in your report. As a premier municipality we do manage many

contracts across.

Contractual Agreements to be in sub-headings – Changes will be accommodated in new Contracts

Issues relating to Constructive Builder - The one highlighted involving Constructive Builders needs

further elaboration. The Contract Document was drawn exactly in line with other similar Contracts

involving small building works and of course vetted by our City Solicitor.

In this instance Embassy of Japan wished to sponsor SCC Compost Project by assisting in acquiring a

Shredder and providing a Compost Shed. They had allocated a budget of $90,000 for this. They asked

Council to facilitate quotations from suppliers preferably with small Contractors already engaged with

Council. The Shredder was not an issue since it was already decided by sponsors to purchase from

Niranjans who had earlier supplied similar machines to Lautoka City Council through JICA. As for the

Compost Shed we as recipient were obliged to facilitate this request and we did so by obtaining quotations

based on our plans, from a handful of reputable Contractors. Constructive Builder at that time was doing

small works for Council and on that strength was approached and did oblige. Their quotation of $24,000

VIP being the lowest was accepted by the Embassy since they had $ 24,000 to work with realizing that out

of $89,000, $65,000 was paid to Niranjans for Shredder.

The Embassy did all the documentation work and forwarded preliminary Contract documents to Council

to enter into agreement with the two chosen suppliers namely Niranjans & Constructive Builder. As a

recipient we did not have much choice but cooperate with the Embassy in good faith. However we felt to

strengthen our position and entered into a formal Agreement with the Builder. The upfront deposit formed

part of the agreement endorsed by the Embassy which was a normal practice with all their chosen

Contractors in all Embassy sponsored Projects.

Essentially we did not have any obligatory input to decide the Contractors but was solely a decision by the

Sponsor. The response by the Second Secretary Mr Kuroki of Embassy of Japan via email dated 24th July,

2013 is self-explanatory. They followed their procurement procedures and because of the budgetary

limitation chose the lowest bidder in this case Constructive builder. Since the Builder abandoned the

project with approx. 30% works completed, Council had to move in to complete the project on timely basis

(project delivery date of February, 2014 was around the corner) in maintaining our healthy relationship

with the Embassy and more importantly to see this new initiative/model of sustainable municipal

composting through for the City. We were confident that the benefits derived from the project will far

outweigh the monetary input the Council was forced to take on.

Transparency in Tender evaluation process

Agreed in principal. A standard policy guideline to be implemented across all municipalities is most

desirable. In absence of one we comply with whatever at our disposal the “Manual of accounts for

Municipal Councils’ by MLG. We recommend that MLG come with a new standard manual for all

municipalities. Agreed that the Manual has to be revised and not only that but as expressed elsewhere

standardized to be applicable to all municipalities across. The recommendation from your Office has to be

put to MLG.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	37

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Further OAG Comments

Suva City Council

Following further consultation, the Council agreed that advance payment will be avoided as much as possible and in

the future contracts would contain provisions where the Council could take the contractor to court for works not

completed.

Nausori Town Council

The following matters were clarified following further consultations with the Council‟s Chief Executive Officer on

31/10/14.

With respect to recommendations directed at all Councils, the Council is currently developing an electronic contract

register. The Council agrees with the audit recommendation to maintain independence between the Tender

Committee that evaluates tender applications and makes recommendations, and the Finance Committee that

endorses tenders recommended by the Tender Committee. Tender Committee members include all section

heads/technical officers and the Finance Manager, whilst the Finance Committee comprises of the Special

Administrator, the Chief Executive Officer and the Finance Manager.

However the Council maintains that representation of ratepayers in the Finance Committee is unacceptable as this

contradicts requirements of the Local Government Act. In agreeing with the audit recommendation that

documentation is important, the Council has proposed that it will develop an index system to boost their current

documentation system. Furthermore the Council agrees with the audit recommendation to maintain a contract

inventory and will be developing an electronic database which will consider incorporation of specific fields identified by

the auditors.

The Council has concurred with most of the recommendations proffered. It proposes to develop a more detailed and

comprehensive tender awarding process. The Council intends to have a standardized format for all contractual

agreements but which will explicitly define the nature and scope of works to be conducted. The council proposes to

have contract agreements for major projects vetted by the Office of the Solicitor General whilst contract agreements

for minor projects can be dealt with by the Council‟s Prosecutor.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	38

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.0 MANAGING	CONTRACTORS

PERFORMANCE

This section of the report looks into the management of contractors’ performance

by the Councils. In particular the section seeks to determine whether the Councils

have effective system to monitor and evaluate the performance of the contractors to

ensure that value for money has been obtained and the intended outputs have been

attained from such contractual arrangements. The section also covers management

of complaints by the Councils.

6.0.1	Performance management should be undertaken throughout the contractual stages.

Performance management involves:

	performance monitoring - collecting data on performance;

	performance assessment - deciding whether performance meets the organisation‟s

needs; and

	taking appropriate action - understanding and extending features of good

performance, correcting areas of under-performance or amending contract

requirements to meet changing needs.

6.0.2	Along with performance indicators and standards, arrangements for monitoring and

assessments should be set out and agreed in the contractual agreement along with action

that should be taken in instances of non-performance. Clear links should be established

in the contractual agreement between payments for performance and the effect of non-

compliance or under-performance on these payments and the intent to invoke penalties

contained in the agreement if necessary.

6.0.3	Systematic monitoring underpins performance assessment and they do not occur in

isolation from one another. In practice, performances are assessed and feedback and

reports provided throughout the monitoring process.

6.1 Monitoring system

6.1.1	Monitoring provides a means for ensuring that implementation goes according to plan. As

such Councils should have a monitoring system in place to effectively monitor the work of

contractors.

6.1.2	Effective monitoring should be reinforced by policies and procedures that present a

framework for Councils to ensure that financial and operational performance of the

contractual work is measured against established targets.

6.1.3	Different approaches to monitoring may be used at different phases in contract delivery or

for particular aspects of performance. Whatever monitoring arrangements are determined

they should be cost effective to implement and manage and the necessary skills should

be available.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	39

| Council | Frequency of monitoring | Audit comments |
| --- | --- | --- |
| Ba | Daily | No documented evidence of monitoring noted. |
| Lami | Daily | No documented evidence of monitoring noted. |
| Lautoka | Daily | No documented evidence of monitoring noted. |
| Nadi | Daily | No documented evidence of monitoring noted. |
| Nasinu | Daily | Field officers have log books which are cross checked with the invoice sent by invoices before submitted for payments. |
| Nausori | Daily supervision on operational contracts | Monitoring reports maintained by respective Department. |
| Suva | Daily | There are monitoring reports which is prepared when payments are made progressively. Records maintained by the Ward Managers on daily inspection. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.1.4	Audit gathered that the different Councils visited have different monitoring systems in

place. The general observation on the monitoring of contractual works found that most

Council have some system in place to monitor contractual works. However, the notable

weakness in the Councils is the lack of a monitoring policy governing monitoring works of

all their capital projects including projects arising out of contractual engagements.

6.1.5	Discussions with the officers at the respective Councils revealed that monitoring of

contractors work were conducted on a regular basis. However, there were specific issues

noted in relation to certain Councils which are detailed below.

Table 6.1: Monitoring of contractors’ work

6.1.6	The accepted practice utilized over the years requires that the respective sections

document monitoring of contracted works under their department. However, as can be

gathered from the table lack of proper documentation of monitoring works is still in

existence in most of the Councils visited.

6.1.7	Lack of documentation of monitoring works may result in the Council‟s management not

being able to make prudent and timely decisions on matters pertaining to contracted

engagements.

6.2 Monitoring of contracted works by an external party

6.2.1	On the 20th of December, 2012, the Nausori Town Council entered into an agreement

with a Consultancy Company namely G.A. Consultants Ltd, which acts as Project

Manager on behalf of the Council. The Project Manager was engaged to monitor few of

the Integrated Transport Project (ITP) contracts for the Council with the objective of

achieving the Council‟s scope, time, costs and other specified objectives.

6.2.2	Annexure C to the contract indicates the Council have engaged the services of the

Project Manager at the agreed sum of $110,000 (VEP).

6.2.3	The Project Manager monitored the work of five contractors. The following table

summarises the five contractors and the amount that have been paid by the Council to

the various contractors for their contractual services as at the end of April 2014:

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	40

| Date | Cheque No. | Amount ($) |
| --- | --- | --- |
| 13.06.13 | 310215 | 7,441.18 |
| 31.07.13 | 310221 | 22,323.54 |
| 08.10.13 | 310233 | 14,882.36 |
| 13.11.13 | 310238 | 7,441.18 |
| 04.12.13 | 310240 | 7,411.18 |
| 03.03.14 | 310246 | 14,882.36 |
| 26.04.14 | 310250 | 7,441.13 |
| Total |  | 81,852.93 |

| Contractors | Service provided | Amount Paid ($) |
| --- | --- | --- |
| Ashok Balgovind | Architect | 201,362.47 |
| E-Designs | Geo Tech & structure | 46,158.25 |
| Erwin Alsop | Service Engineer | 57,509.00 |
| William & Associates Ltd | Quantity Surveyor | 128,546.11 |
| Ragwan | Construction | Not provided |
| Total |  | $433,575.83 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 6.2: Contractors monitored by the Project Manager with amount paid to

them by the Council

6.2.4  	Audit noted that even though a contract was signed between Nausori Town Council and

the company the Council did not regard the Project Manager as a contractor but as part of

the Nausori Town Council organisation employee.

6.2.5	The Council paid a total of $81, 852.93 to the Project Manager as at the end of April

2014. The following table provide details of the amount paid.

Table 6.3: Breakdown of amount paid to the project manager as at 30th April 2014

6.2.6	Considering the magnitude of the amount paid to the Project Manager the audit found the

following anomalies in the engagement.

	the provisions in the Contract/Agreement have no requirements to compel the

Council to monitor the work of Project Manager. Thus the Council did not verify the

monitoring works conducted by the project manager.

	the contract did not include a requirement for reporting of results of monitoring by the

project manager.

	payments were made to the project manager on the strength of the invoice without

documentary evidence of monitoring works conducted on each of the five contractors.

6.2.7	There is a risk that the Council may be paying more than the actual monitoring work

conducted by the project manager.

6.3 Evaluation of contract performance

6.3.1	An evaluation should be undertaken by the Councils at the end of the term of a contract.

Contract evaluation should encompass the overall performance of the contractor and the

Council. Such evaluation should be conducted so that any problems that have occurred

with aspects of the contractual arrangement are identified and where appropriate,

improvements made in future contractual arrangements.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	41

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.3.2	To get the best out of the evaluation Councils should review all aspects of contract

performance and its management, provide feedback to the contractor and identify lessons

learnt. The evaluation should consider both the effectiveness and efficiency of the

contractual arrangement.

6.3.3	A contract performance report should be prepared to evidence the evaluation results. In

addition to specific requirements outlined in the contractual agreement the following table

outline key activity where the evaluations should be concentrated.

Table 6.4: Key activities for performance evaluation

Activity		Details

Administration of contractual		Timely responses to correspondence between the

agreement	parties

	Timeliness of any required approvals

Contract documents		Clarity and adequacy of scope

Delivery of services		Completion time

	Quality of work

Progress payments		Fairness and reasonableness of claims

	Timeliness of payments

Claims management		Processing of claims in a timely manner and in

accordance with the contract.

	Assessment of claims was fair and reasonable.

6.3.4	Our examination found that none of the Councils visited conducted a performance

evaluation of contractors upon expiration of the terms of their contracts on services

rendered to the Council. In addition audit found no evidence that any of the Councils

prepared a contract performance report.

6.3.5	Conduct of evaluation and preparation of contract performance report would assist the

Council in identifying areas for improvement for future contractual engagements.

6.4 Monitoring, reporting and evaluation of performance

requirements included in the contract agreement

6.4.1	Contractual agreement should generally contain provisions for monitoring progress and

evaluation of the performance of a contractor. In this regard contracts should include

provisions that cover the person responsible for undertaking performance monitoring

including the responsibility for collecting and analysing data, the frequency of monitoring,

the reporting arrangements; and any processes to review the performance of the

contractor.

6.4.2	Our review of contracts gathered from various Councils visited gathered the following

observations in respect to the integration of monitoring requirements.

Table 6.5: Details of integration of monitoring requirements in contracts

Council	Audit observation

Nadi Town

Council

Monitoring requirements, reporting arrangements and review process to

review the performance of the contractor were not included in the

contract.

Ba Town Council	Monitoring requirements, reporting arrangements and review process to

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	42

Council	Clause 32 of a contract reviewed requires that routine inspections be

Council	Clause 9 of a contract drawn by the Council incorporates performance

Council	Clause 4.3 of the Special Conditions of Contract requires that the works

Council	The  special  conditions  under  one  of  the  three  contracts  examined

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

review the performance of the contractor were not included in the

contract.

Lami Town

carried out randomly by the Building Inspector and Work Supervisor of the

Council with the representative of the contractor and a report to be

submitted weekly to the Council.

Contract however did not incorporate requirements to conduct overall

evaluation of the contractor‟s performance.

Nasinu Town

and monitoring. The requirement includes identification of officer

responsible for monitoring and reporting of contractor‟s performance. In

addition the requirement provides that any deficiency identified should be

brought to the attention of the Contractor and which should be rectified

within 24 hours to the satisfaction of the Council but at the expense of the

Contractor.

The clause however did not incorporate requirements on the frequency of

reporting and processes to review the performance of the contractor.

Lautoka City

shall be inspected by the Director Engineering Services or his

representative and any shortcomings to be rectified within 24 hours.

Inspection work required in the contract to be conducted daily for the

duration of the contract.

However, there is no specific requirement on the reporting of contractual

works by the responsible officer. Also neither the general nor the special

condition contract outlines requirements on the process governing

evaluation of the contractor‟s performance.

Nausori Town

included requirements on inspection of works to be conducted by the

Field Supervisor of the Council or nominee and any short comings to be

rectified within 24 hours or no later than 7 days. The frequency of

inspection is also indicated under the condition.

There is however no specification on the reporting arrangement and

process to evaluate the Contractor‟s performance.

The remaining two contracts did not provide any requirements on the

monitoring requirements, reporting arrangements and review process of

contractual arrangement to review the performance of the contractor.

Suva City Council	Clause 26 provide requirement for routine inspections to be carried out by

the Engineering Department of the Council.

There is however no specification on the frequency of inspection, the

reporting arrangement and process to evaluate the Contractor‟s

performance.

6.4.3	It can be noted from the above table that not all Councils integrated monitoring, reporting

arrangements and performance evaluation of the contractor as part of the contractual

agreement.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	43

| Council | Audit Comments |
| --- | --- |
| Ba |  The register was not appropriately maintained and updated on a regular basis. |
| Lautoka |  The Council carries out inspections, gives out notices and even take legal action where necessary. When complaint is received by the ratepayer, an inspection is carried out and a notice sent. If there is still non- compliance, a second notice may be sent or legal action taken  Complaint register maintained however register was not updated in a timely manner. |
| Nadi |  The Council informs the complaint about the processes and the cycle and the contractor is informed to address the complaint and if it is not done by the contractor the task is carried out by the contractor and the cost is deducted from the sum agreed to be paid to the contractor.  The register was not appropriately maintained and updated on a regular basis. |
| Nasinu |  Scrutiny of the complaints register revealed that the Council has been attending to the complaints received satisfactorily.  Dates of complaints received and attended to with the details of work provided by the Council are provided in the complaints register. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.4.4	The anomaly clearly indicates that the various Councils do not place emphasis on

monitoring and evaluating performances of contractors once they are engaged.

6.5 Managing complaints on contractors work

6.5.1	Complains are an important way for the management for the Council to be accountable to

the ratepayers as well as providing valuable prompts to review organisational

performance and the conduct of people that work within and for it. As such Councils

should maintain a register to record complaints from ratepayers for inadequate services

conducted by contractors.

6.5.2	An effective complaint handling system provides three key benefits to an organisation

which includes the following:

	resolves issues raised by a person who is dissatisfied in a timely and cost-

effective way;

	provides information that can lead to improvements in service delivery; and

	improve the reputation of an organisation and strengthen public confidence in an

organization‟s administrative processes.

6.5.3	Complaint handling should have sound processes that embody the five fundamentals

principles of fairness, accessibility, responsiveness, efficiency and integration as its basis.

The aim is to ensure that complaints are dealt with efficiency and effectively and the

clients have confidence in the Council‟s complaint system.

6.5.4	Our review gathered that except for Suva City Council all other Councils visited maintain

a complaint register where all complaints raised concerning their operations are entered

into. Such information entered into the register also includes complaints relating to

contractors engaged by the Councils.

In addition audit gathered the following findings in the management of complaints within

the Councils visited.

Table 6.6: Monitoring of contractors’ work

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	44

| Nausori |  The Council maintains both a manual and electronic copy of complaints register. Audit review of both registers found that both registers were not updated on a regular basis. |
| --- | --- |
| Suva |  When complaint is received by the ratepayers an inspection is carried out and a notice sent. If there is still non- compliance, a second notice may be sent or legal action taken. |
| Lami |  Council has a register in place and is updated in a timely manner. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.5.5	It can be noted from the above table that some Councils do not update the status of the

complaints raised.

6.5.6	The non-update of the complaints register disallows the Council from establishing the

effectiveness and efficiency in addressing complaints.

RECOMMENDATIONS

All Councils

All Councils should:

	ensure that a monitoring policy is developed which should include monitoring of contractors‟ work. The

policy should cover amongst other things requirements of documentation of monitoring activities. Such

policy once developed and endorsed by management should be strictly complied with by the Councils.

	ensure that an overall evaluation of a contractual arrangement is undertaken following expiration of the

contract. A contract performance report should be prepared to detail the results of the evaluation.

Ba Town Council

The Ba Town Council should:

	ensure that monitoring works conducted are documented in the form of a report. The report should be

included in the relevant contract‟s file for reference.

	ensure that contractual agreements with contractors should integrate requirements on monitoring,

reporting arrangements and review of contractor‟s performance. The frequency of monitoring and

reporting should be specifically outlined in the agreement.

	ensure the proper documentation of complaints in the complaints register. The register should be

updated on a regular basis such that the Council is aware of the status of complaints at a particular

point in time.

Lami Town Council

The Lami Town Council should:

	ensure that monitoring works conducted are documented in the form of a report. The report should be

included in the relevant contract‟s file for reference.

	improve its contract with contractors to incorporate requirements on the evaluation of contractor‟s

performance following completion of the contract.

Lautoka City Council

The Lautoka City Council should ensure that:

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	45

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	monitoring works conducted are documented in the form of a report. The report should be included in

the relevant contract‟s file for reference.

	its contract with contractors be improved to incorporate requirement of the reporting of the results of

inspections by the Director Engineering Services and the evaluation of contractor‟s performance

following completion of the contract.

	proper documentation of complaints in the complaints register. The register should be updated on a

regular basis such that the Council is aware of the status of complaints at a particular point in time.

Nadi Town Council

The Nadi Town Council should ensure that:

	monitoring works conducted are documented in the form of a report. The report should be included in

the relevant contract‟s file for reference.

	for future engagements of consultants to monitor contractual engagements the contractual agreement

should incorporate requirements of monitoring works by the project manager to be checked by an

officer of the Council and the provision of reports by the project manager evidencing monitoring

activities. In addition, the Council should ensure that any claims made by the project manager should

be supported by a progress report of monitoring works in addition to the invoice and that such reports

should be verified before payment is made.

	contractual agreements with contractors should integrate requirements on monitoring, reporting

arrangements and review of contractor‟s performance. The frequency of monitoring and reporting

should be specifically outlined in the agreement.

	proper documentation of complaints in the complaints register. The register should be updated on a

regular basis such that the Council is aware of the status of complaints at a particular point in time.

Nasinu Town Council

The Nasinu Town Council should improve the clause of its existing contract on monitoring and

performance to include the frequency of reporting by the Council Liaison Officer and also the

requirement to conduct evaluation of the contractor‟s performance upon expiration of the contract.

Suva City Council

The Suva City Council should:

	improve its contracts with contractors to include requirements on the frequency of inspection, the

reporting arrangement and process to evaluate the contractor‟s performance.

	maintain a complaints register to record all complaints received in the provision of its services

including services provided by contractors.

Nausori Town Council

The Nausori Town Council should ensure that:

	all its contractual agreements with contractors should integrate requirements on monitoring, reporting

arrangements and review of contractor‟s performance. The frequency of monitoring and reporting

should be specifically outlined in the agreement.

	the complaints register (both the manual and electronic record) are updated on a regular basis such

that the Council is aware of the status of complaints at a particular point in time.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	46

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Management Comments

Ba Town Council comments

Council noted the comments by auditors regarding the monitoring works of contractors. Council has been

monitoring the performance before the payments are made but proper documentations on performance

were not kept. In future, performance report will be recorded and kept by the Health Department.

Council has a Complaint register whereby all verbal and written complaints received are recorded in the

complaints register and actions are taken. The register is updated on regular basis.

Lautoka City Council comments

Monitoring system - Currently the contracts are monitored by the respective departments they fall under

and their performance is part of the department’s report tabled in the monthly council meeting. For non-

performance and breach of any contract conditions the council decides on the appropriate corrective

action to take and if it decides to terminate the contract then it will also determine how the work will be

carried out in the interim while it tenders the contracts. These are filed in the council minutes. For this

purpose we will extract minutes pertaining to contract performance to be filled in the individual contract

file.

Monitoring, reporting and evaluation of performance requirements included in the contract agreement

- The condition though not explicitly stated on the contract, the responsible officer’s report is tabled in the

council meeting as in 6.1.5 above. However we are reviewing our contract documents we will include this

requirement with other conditions that the council has already resolved to incorporate in our contract

documents.

Managing complaints on contractors work - The Council always maintain and update its complaint

register on regular basis and complaints are attended to promptly.

Nadi Town Council comments

Managing contractors’ performance - Absence of proper documentation to assess the monitoring of

contractual works exists at Nadi Town Council. We are currently working towards this and at the moment

we have a government funded project (New Nadi Market Extension and Vendor Hostel) and have engaged

a reputable consultant to monitor the works and the consultant has provided a detail plan with the costing

together with the percentage and this is done in joint consultation with the project officer who may be

from the Engineering or Building department before the invoice is forwarded to the Finance department

to pay. With the current market project, the building department has kept a separate file which

accommodates the agreement, plans and all other details.

Nasinu Town Council comments

Nasinu Town Council agree with the two recommendation made for all Councils and we will implement

them. The recommendations to improve some clauses in our existing contract agreements to include

monitoring, performance, evaluations and reporting will be implemented.

Nausori Town Council comments

A special monitoring policy shall be established by council to ensure amongst other things requirements

of documentation of monitoring activities.

Council has established a resolution where overall evaluation of a contractual arrangement (including

human resource) is undertaken following expiration of the contract.

Suva City Council comments with respect to recommendation to all councils

Contract performance system is essential to closely follow with Contractors performance for a value for

money service. Performance-based service contracting emphasizes that all aspects of an acquisition be

structured around the purpose of the work to be performed as opposed to the manner in which the work is

to be performed or broad, an objective assessment of contractor performance. It is designed to ensure that

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	47

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

contractors are given freedom to determine how to meet the Council’s performance objectives that

appropriate performance quality levels are achieved, and that payment is made only for services that meet

these levels. The use of these methods should lead to more cost-effective acquisitions, better value, and

greater competition. They should have the net effect of shifting some of the manageable performance risk

from the municipality to the contractors. Contractors will be given more latitude for determining methods

of performance, with more responsibility for performance quality. By doing this the Council should

experience fewer cost overruns, schedule delays, and performance problems. This creates a "win/win"

situation for both agencies and contractors.

It is important to focus monitoring activity on the key deliverables; very detailed monitoring can be costly

and can unduly shift the focus away from achieving the contract outcomes. One thing we need to capture

is often it is not practical to neither objectively measure nor document all the works that is required to be

done as per scope. This may vary in different sectors/zones/wards largely depending on external factors

whereas our Contracts are consistent for all sectors. Having a systematic approach to monitoring, which

includes the sort of information required and when it is required, can assist in identifying any potential

problems and allow early remedial action to be taken. It also allows timely reporting to senior

management and other stakeholders. Obtaining relevant information and data may need to be supported

by management information systems or databases. It is important to collect and analyse all the relevant

information needed to assess performance. After analysing the information, feedback should be provided

to the contractor in a professional and constructive manner and in line with any communications protocol

that exists.

Suva City Council

The Council agrees to some extent with the findings:

1)	We have in place a rigid performance management system of the Maintenance Contractors, such as

daily checklist, fortnightly and monthly report compilation for evaluation & processing of payments.

We are working closely with Fiji Roads Authority on this. For now this is being of acceptable level to

them. Regardless we will strive to improve upon same to eliminate possible gaps.

2)	Current practice is that each Department (Health & Engineering) deals with Contracts under their

respective responsibility. At Department level Health Department does maintain Inventory of

Maintenance Contractors. In addition we do maintain a Complaint Register as well. Likewise we will

ensure that the Engineering Department also complies with above. Apart from this the Copies of all

contract documents are kept by our Central Registry Section. We are in the process of updating the

one kept by Central Registry.

Further OAG Comments

Suva City Council

Following further consultations, the Council agreed that the Engineering Department does not conduct performance

evaluation of contractors. It intends to develop a Monitoring Policy and to conduct overall evaluation and prepare

performance reports for contract works undertaken.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	48

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

7.0 CONCLUSION

7.1	None of the Councils visited have developed a policy governing the management of

contractual engagements. Most the Councils visited were following tender procedures

outlined in the Manual of Accounts for Municipal Councils in Fiji which was endorsed in

1992. Detailed planning of outsourced services were lacking in six of the Councils visited.

Further to this risk assessment of contractual activities were not conducted by all the

Councils visited.

7.2	Generally records maintained on activities relating to contractual engagements needs to

be improved. It is pivotal that contract files contain information relating to tender

evaluations, contractual agreement, correspondences between the Council and the

contractor and other key activities of the engagement. Equally important is the

compilation of contracts inventory and contracts register to evidence the contracts

undertaken by the Councils over the years.

7.3	There is also a need to separate parties currently involved in the evaluation and approval

of tender proposals to ensure transparency in the tender process. The criteria for tender

evaluation is also lacking in most of the Councils. Contractual agreements being entered

into by most of the Councils needs to be reviewed to incorporate other key items

highlighted in this report. A few of the Councils also need to have their agreements vetted

by a solicitor. Stringent controls also need to be put in place to ensure payments made to

contractors are within the requirements of the contract agreement.

7.4	Some evidence of monitoring of contractual engagement was noted to have been

conducted by most of the Councils; however there have been lack of proper

documentations to indicate the results of monitoring works. This anomaly was mainly

attributed to the absence of a monitoring policy in place and non-specification of

monitoring requirements in the contractual agreements. The evaluation of the contractors‟

performance and preparation of a contract performance report was not conducted by all

the Councils. Such is the case mainly due to the non-inclusion of the requirement in the

existing contractual agreement.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	49

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

8.0 REFERENCE

1.	Better Practice Guide, Developing and managing contracts getting the right outcome

paying the right price (2007); Australian National Audit Office.

2.	Contract Management Framework; (2010) Department National Treasury- Republic of

South Africa.

3.	Contract Management Guide (2007); The Chartered Institute of Purchasing and Supply;

Contract Management Guide.

4.	Contract Management Guidelines” Supporting Councils in developing a sound, consistent

and effective approach to managing their diverse range of contracts; Victoria Local

Government.

5.	Contract Management Policy (2008); Frances BAARD District Municipality.

6.	Manual of Accounts (1992); Department of Local Government.

CONTRACTUAL ENGAGEMENTS BY MUNICIPAL COUNCILS	50

Management of Multilateral

Environmental Agreements

A Performance Audit Report of the Office of the Auditor General of the Republic of Fiji

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Multilateral environmental agreements [MEA] are legal instruments with binding effects on countries that have

agreed to become parties to a particular agreement through ratification or accession. Currently, Fiji has

acceded to and is a member of thirteen Multilateral Environmental Agreements of which ten are international

and 3 regional.

This report contains findings on the actions taken by the Department of Environment as the focal agency and

related stakeholder agencies in ensuring commitment to the MEAs are met.

Table of Contents

1.0	EXECUTIVE SUMMARY..........................................................................................................3

2.0	INTRODUCTION.......................................................................................................................5

2.1	An overview .......................................................................................................................5

2.2	Key benefits of an MEA ........................................................................................................6

2.3	Management of MEAs in Fiji and responsible implementing agency ...............................................7

2.4	Reasons for undertaking the audit...........................................................................................8

3.0	AUDIT OBJECTIVES, SCOPE AND METHODOLOGY ...........................................................9

3.1	Audit objectives and scope ....................................................................................................9

3.2	Audit methodology...............................................................................................................9

4.0	IMPLEMENTATION ARRANGEMENTS FOR HONOURING REQUIREMENTS OF MEA’S 11

4.1	Absence of adequate implementing legislation for MEAs............................................................11

4.2	Absence of standard operating procedures .............................................................................13

4.3	Existence and adequateness of national plans for implementing MEAs .........................................15

4.4	Diversion of funds provided for the implementation of the NIP for the Stockholm Convention .............17

4.5	Alignment of MEA implementation activities and targets in organizational plans ..............................18

4.6	Public awareness and education on MEA obligations ................................................................19

4.7	Review of National Measures in implementing MEAs ................................................................20

4.8	Lack of in-house and capacity building...................................................................................21

4.9	Lack of technical knowledge and skills ...................................................................................22

4.10	Lack of manpower to handle tasks ........................................................................................23

5.0	ACCOUNTABILITY AND REPORTING RELATIONSHIPS ....................................................26

5.1	Monitoring implementation of Conventions..............................................................................26

5.2	Internal Reporting..............................................................................................................27

5.3	External Reporting.............................................................................................................28

5.4	Participation in international and regional meetings...................................................................30

5.5	Dissemination of outcome of meetings and conference of parties ................................................32

5.6	Maintenance of a database to provide information on environmental agreements ............................34

6.0	CONCLUSION ........................................................................................................................35

7.0	REFERENCES ........................................................................................................................36

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	1

| ACP | Annual Corporate Plan |
| --- | --- |
| BP | Business Plan |
| CBD | Convention on Biological Diversity |
| CBH | Central Board of Health |
| CFC | Chlorofluorocarbon |
| CITES | Convention on International Trade of Endangered Species |
| CMS | Convention on Migratory Species |
| COP | Conference of Parties |
| DoE | Department of Environment |
| EIA | Environment Impact Assessment |
| EMA | Environment Management Act |
| EPS | Endangered and Protected Species |
| GEF | Global Environment Facility |
| HCFC | Hydro chlorofluorocarbon |
| IF | Implementation Framework |
| IWP | Individual Work Plan |
| MEAs | Multilateral Environmental Agreements |
| MoP | Meeting of Parties |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NGO | Non-Government Organisations |
| NIP | National Implementation Plan |
| NOU | National Ozone Unit |
| NSWMS | National Solid Waste Management Strategy |
| ODS | Ozone Depleting Substances |
| OEWG | Open-ended Working Group |
| POPs | Persistent Organic Pollutants |
| RMU | Resource Management Unit |
| SAICM | Strategic Approach to International Chemicals Management |
| SOP | Standard Operating Procedures |
| SPREP | Secretariat of the Pacific Regional Environment Programme |
| UNDP | United Nations Development Programme |
| UNEP | United Nations Environment Programme |
| WMU | Waste Management Unit |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Acronyms

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	2

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

1.0	EXECUTIVE SUMMARY

Background	Multilateral Environmental Agreement” or MEA is a broad term that relates to any of a number of

legally binding international instruments through which national governments commit to

achieving specific environmental goals. These agreements may take different forms, such as

“convention,” “treaty,” “agreement,” “charter,” “final act,” “pact,” “accord,” “covenant,

”protocol,” or “constitution” (for an international organization). Put simply an MEA is a legally

binding instrument between two or more nation states that deals with some aspect of the

environment

The Department of Environment is the focal agency for these agreements and is responsible for

the administration and implementation of these agreements. The department with its

stakeholders plays the pivotal role in coordinating and managing strategies for ensuring the

effective implementation and compliance to the requirements of the conventions.

Coverage	The audit on Management of Multilateral Agreements focuses on two areas namely

“Implementation arrangements for honouring requirements for MEA’s and its implementation

and Accountability and Reporting Relationships.”

The audit looked into records held at the Department of Environment for the years 2011 -2013.

Key findings	Implementation arrangements for honouring requirements for MEA’s

	Lack of legislations for the implementation of MEA’s

	Absence of SOP to outline the processes and how a task is to be implemented.

	Non-existence of national plans for the MEA’s

	Diversion of funds for the implementation of NIP for the Stockholm convention

	Lack of alignment between individual and the organisational strategy

	Failure to adequately conduct education and awareness on MEA’s

	Failure to conduct timely and appropriate reviews on the MEA’s

	More capacity building is needed for the MEA’s

	Lack of in-house and capacity building for the MEA’s

	Adequate management is needed to handle the tasks.

Accountability and reporting relationships

	Lack of commitments noted at the COP

	Information from the COP needs to be disseminated to the stakeholders regularly.

	Lack of coordination amongst stakeholders

	Unclear roles and accountabilities of focal and implementing agencies

	Reports both internal and external needs to be maintained by the department.

	Monitoring of activities in the implementation of the MEA’s needs to be maintained

Overall	The effectiveness of the implementation of the requirements of the multilateral agreements is

Conclusion	weakened by a lack of legislations and policies and the absence of SOP and the national plans

to support the implementation of certain environmental agreements. There is a lack of formal

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	3

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

arrangements between the DOE and other stakeholders responsible for the implementation of

the requirements of the conventions. However despite all the above and the lack in resources,

the DOE and implementing agencies are adequately implementing requirements of multilateral

environmental agreements.

General	The audit recommends that the Department of Environment intensely pursue the review of the

Recommendations necessary legislation and policies and draft standard operating procedure to empower and

ensure consistency in practices undertaken by all stakeholders. Awareness on the conventions

and its requirements should be created amongst all stakeholders. Apart from strengthening

the management of conventions by ensuring all required documentation are maintained,

records management system and reporting system for the conventions are improved, the DOE

need to be adequately resourced to enable it to effectively implement the requirements of the

MEAs

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	4

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.0 INTRODUCTION

This section of the report provides a brief overview on the management of Multilateral

Environmental Agreements in Fiji and the reasons for conducting the audit.

2.1 An overview

2.1.1	Since environmental issues entered the international agenda in the early 1970s, global

environmental politics and policies have been developing rapidly. Global environmental

governance can be defined as ―the sum of organizations, policy instruments, financing

mechanisms, rules, procedures and norms that regulate the processes of global environmental

protection‖.1 Multilateral Environmental Agreements or ―MEAs‖ are one of the most prominent

features that regulate this process.2

2.1.2	MEAs are a subset of the universe of international agreements. What distinguishes them from

other agreements is their focus on environmental issues, their creation of binding international

law, and their inclusion of multiple countries. Multilateral environmental agreements is a broad

term that relates to any of a number of legally binding international instruments (such as

convention. treaty, agreement, charter, final act, pact, accord, covenant, protocol, or

constitution) through which national governments commit to achieving specific environmental

goals3. MEAs are international treaties signed by two or more nation states to deal with

environmental issues crossing national boundaries.

2.1.3	Multilateral environmental agreements are legal instruments with binding effects on countries

that have agreed to become parties to a particular agreement through ratification or accession.4

As a principle of international law, MEAs (as with other international agreements) usually bind

only those States that have agreed to be bound by the MEA. However, an MEA can affect non-

Parties, for example by prohibiting or restricting trade by Parties with non-Parties. For the

countries which have only signed and not as yet ratified, they are nonetheless expected not to

do anything that will affect the aims and purposes of the MEA. They are not declarations of

intention or avowals (which are non-binding); they are rules of law. As such, they are a

powerful tool for the implementation of policies directed at environmental protection and

sustainable development goals. MEAs must conform to international public law (as must all

international instruments of this type). Legally binding and non-legally binding agreements

come in many shapes and forms.5 They can inter alia be of the following types or denominated

as follows:

1 Global Environmental Governance: A Reform Agenda, International Institute for Sustainable Development, 2006,p3

2 Auditing the implementation of Multilateral Environmental Agreements: A Primer for Auditors, p4

3 UNEP Manual on Compliance and Enforcement of MEAs

4 Auditing the implementation of Multilateral Environmental Agreements: A Primer for Auditors, p4

5 Auditing the implementation of Multilateral Environmental Agreements: A Primer for Auditors, p5

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	5

| Legally binding (MEAs) | Non-legally binding |
| --- | --- |
| Treaties | Resolutions |
| Conventions | Decisions |
| Agreements | Declarations |
| Protocols | Recommendations |
| Accords |  |
| Pacts |  |
| Charters |  |
| Amendments |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 2.1: Types of MEAs (legally or non-legally binding)

2.1.4	MEAs may be between two States, in which case they are usually termed ―bilateral.‖ However,

most MEAs are between three or more States, and thus ―multilateral.‖ [For the purposes of this

Primer, MEA includes bilateral agreements]. MEAs are multilateral in the sense that they

involve many nations. However, for the purposes of this Primer an MEA can be any treaty

between two or more nation-states if and when this instrument deals with direct environmental

objectives.6

2.2 Key benefits of an MEA

2.2.1	The key benefits of an MEA are usually environmental, but may also be economic, socio-

political (e.g., empowering the public to become involved), and administrative. The clearest

benefits of any particular MEA usually relate to the specific goals of that MEA.7

2.2.2	In addition to there are some general benefits of ratifying, implementing, complying with, and

enforcing MEAs — and costs associated with not complying. Refer to the following for details:

	Protecting Public Health and the Environment: MEAs have a range of environmental and

public health benefits, the specifics of which vary from MEA to MEA and State to State.

These benefits tend to be both short- and long-term.

	Improving Governance: In addition to providing substantive norms of environmental

protection, many MEAs improve environmental governance, as well as generally promoting

transparency, participatory decision making, accountability, and conflict resolution.

Moreover, MEAs often seek to avoid or limit resource-driven conflicts by promoting

equitable arrangements, for example regarding access to fresh water within an

international watercourse basin.

	International Political Comity and Respect: Most MEAs address environmental and public

health challenges that are shared by many nations. Many nations contribute to the

problem, and many suffer the consequences. Sometimes, they are the same nations;

sometimes, the States causing the harm are different from those most affected.

	Solidarity: States may wish to become a Party to an MEA to support other States in the

environmental challenges they face. In such instances, the particular goals of the MEA

might be noble, worthy, and of great importance to other States (for example in the same

region), but may be a lower domestic priority.

6 Auditing the implementation of Multilateral Environmental Agreements: A Primer for Auditors, p5

7 Auditing the implementation of Multilateral Environmental Agreements: A Primer for Auditors, p5

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	6

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	Financial Assistance: Often, a State needs to be a Party to an MEA in order to access

funding from the MEA Secretariat, multilateral sources and certain bilateral sources.

Moreover, if a State is not complying with an MEA, this could jeopardize existing funding.

	Technical Assistance and Networking: In addition to financial assistance, MEAs often

facilitate technical assistance, for example through technology transfer. Additionally, MEA

Secretariats often build capacity of governmental authorities to implement the MEA by

fostering regional and global networks through which members share experiences.

	Long-term Economic Benefits: Analyses by the OECD, the World Bank, and others indicate

that in many instances it is economically preferable to develop within the context of

environmental regulation. Otherwise, States frequently have had to make large

expenditures to redress environmental and public health consequences of environmental

neglect. Thus, while the priority of many States may be on development, participation in

MEAs can enhance the long-term sustainability of development initiatives.

	Trade: In certain instances, MEAs contain provisions that impose obligations on Parties

vis-à-vis their trade with non-Parties.

	Facilitating Changes in Domestic Environmental Law: While environmental problems may

be evident, a Government or Parliament may be reluctant to develop the necessary laws

and institutions to address the problems.8

2.3 Management of MEAs in Fiji and responsible implementing

agency

2.3.1	Once MEA‘s are ratified they become legally binding and indicate a Government‘s serious

commitment to achieving specific environmental goals. Following the ratification of MEAs,

national governments are required to identify focal and implementing agencies which will be

responsible for administering the implementation of obligations under each agreement.

2.3.2	Fiji as part of the global community has acceded and is a party to 13 MEAs, reflecting its

commitment to environmental protection. The Department of Environment as the focal agency

administers twelve of the thirteen MEAs, whilst the Ministry of Foreign Affairs administers the

United Nations Climate Change Convention (UNCCC).

Reflected in Figure 2.1 are the nine international and three regional agreements administered

by the Department of Environment.

8 Auditing the implementation of Multilateral Environmental Agreements: A Primer for Auditors, p6

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	7

| 1. Convention on Biological Diversity | June 5, 1992 | 25/02/1993 | 29 Dec 1993 |
| --- | --- | --- | --- |
| 2. Cartagena Protocol on Biosafety | May 2 2001 | 05/06/2001 | 11 September 2003 |
| 3. Nagoya Protocol | - | 24/10/2012 | 23/01/2013 |
| 4. Convention on international trade in endangered species of wild fauna and flora (CITES ) | 11/1997 | 30/09/1997 (A) | 29/12/1997 |
| 5. Convention on Migratory Species | - | 01/04/2013 | 01/07/2013 |
| 6. Ramsar Convention on Wetlands | 11/04/2006 | 11/04/2006 | 11/08/2006 |
| 7. Vienna convention on the protection of the ozone layer | 23/10/1989 | 23/10/1989 |  London Amendment (1990) - 09.12.1994 (Ac)  Copenhagen Amendment (1992) - 17.05.2000 (Ac)  Montreal Amendment (1997) - 19.02.2007 (Ac)  Beijing Amendment (1999) - 19.02.2007 (Ac) |
| 8. Montreal Protocol on substances that deplete the ozone layer | 23/10/1989 | 23/10/1989 | 22/01/1990 |
| 9. Stockholm Convention on Persistent Organic Pollutants | 14/06/2001 | 20/06/2001 | 17/05/2004 |
| 10. Waigani Convention | 16/09/1995 | 18/04/1996 | 21/10/2001 |
| 11. Apia Convention | - | 08/09/1989 | 07/12/1989 |
| 12. Noumea Convention |  | 08/09/1989 | 08/10/1989 |

Agreements                	Signed on    	Ratification/

Accession         	Entry into Force

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Figure 2.1: Multilateral environmental agreements Fiji is a party to

Multilateral Environmental

2.3.3	The above table indicate that the first international MEA that was signed by Fiji was the Vienna

Convention on the protection of the ozone layer and the Montreal Protocol which was both

signed on the 23rd of October 1989.

2.4 Reasons for undertaking the audit

2.4.1	As a party to multilateral environmental agreements, Fiji is required to comply with certain

requirements of such Agreements. Poor implementation, monitoring and enforcement of

multilateral environmental agreements requirements imply non-compliance which may have

legal implications for the country.

2.4.2	Furthermore, non-compliances may lead to criticisms from other international governments

which can undermine Fiji‘s credibility and erode the willingness of other governments to take

action on other, unrelated matters such as trade, development, security, or social issues. In

addition, Fiji‘s inability to comply with both national and international reporting requirements

may affect the availability of future funding and hinder the successful implementation of

projects and activities under respective MEAs

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	8

| UNIT | OFFICERS |
| --- | --- |
| Department of Environment- Management |  Director |
| Waste Management Unit |  Principal Environment Officer  Senior Environment Officer  Environment Officers |
| Resource Management Unit |  Senior Environment Officer  Environment Officer  Assistant Project Officer |
| Ozone Depleting Substances Unit |  ODS National Coordinator  ODS Project Inspector  ODS Project Assistants |
| Education and Awareness Unit |  Environment Officer |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

3.0 AUDIT	OBJECTIVES,	SCOPE	AND

METHODOLOGY

This section of the report describes the objective and scope for this audit. It also

discusses the methodology utilised to gather information for the audit.

3.1	Audit objectives and scope

3.1.1	The overall objective of the audit is to assess the efficiency and effectiveness of focal and

implementing agencies in implementing multilateral environmental agreements by examining:

	implementation arrangements in place for honouring requirements of MEA, and

	accountability and reporting relationships including the effectiveness in monitoring

implementation.

3.1.2	The audit focused on the management of multilateral agreements administered by the

Department of Environment over the past three years from 2012.

3.2	Audit methodology

3.2.1	The audit was conducted using the following evidence gathering techniques:

1. Documentary Review

The audit reviewed all multilateral environmental agreements ratified and managed by the

Department of Environment together with related documents.

2. Interviews

Interviews were carried out with the following officers from various Units within DOE.

Table 3.1: Details of interviews conducted

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	9

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

3. Questionnaire

A questionnaire was also answered to capture certain issues that were not in any way

documented

4. Other

Correspondences through emails were also made to clarify certain issues.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	10

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.0 IMPLEMENTATION	ARRANGEMENTS

FOR HONOURING REQUIREMENTS OF

MEA’S

This section of the report seeks to establish the implementation arrangements in place that

define responsibilities amongst key agencies in managing, implementing and enforcing

government’s obligations for each MEA. It also seeks to determine whether the

implementation arrangements have been implemented, implementation is effectively

coordinated across key agencies, and the sufficiency of resources to ensure effective

implementation.

4.0.1	Environmental agreements articulate international approaches to address environmental

challenges. Once a country ratifies or accedes to an agreement, all necessary measures needs

to be taken to ensure compliance to respective MEA obligations.

4.0.2	The UNEP Guidelines on Enforcement and Compliance to MEA‘s defines ―implementation‖ as

all relevant laws, regulations, policies, and other measures and initiatives, adopted or taken to

meet obligations under an environmental agreement.

4.0.3	Whilst the respective MEA Secretariats are responsible for preparing and servicing meetings of

the parties, coordinating with relevant international bodies and overseeing the overall

implementation of MEA obligations, the member countries are responsible for the development

of appropriate legislations, strategies and plans to effectively implement MEA obligations.

General process outlining post ratification activities are outlined in Figure 4.1 below.

Figure 4.1: Post Ratification Process

Multilateral

Environmental

Agreement

Return Home

Domestic

Plans are

designed

Implem

ent Plan

Signed and

Ratified

Country Reports Activities

to MEA Secretariat

Adjust Plan

Results

The following paragraphs discuss findings on implementation arrangements.

4.1 Absence of adequate implementing legislation for MEAs

4.1.1	According to their respective national legal frameworks, states should enact laws and

regulations to enable implementation of multilateral environmental agreements where such

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	11

| MEAs | Specific Legislations | Audit Comments |
| --- | --- | --- |
| Convention on Biological Diversity | No specific legislation | The convention relies on several pieces of legislations that cover different aspects of conservation and sustainable use of biological resources. These legislations include the Endangered and Protected Species Act 2002, Environment Management Act 2005, Fisheries Act Cap 158, Forest Decree 1992, Land Use Decree 2010, and Ozone Depleting Substances Act 1998. |
| Cartagena Protocol on Bio safety | No specific legislation | The convention is legislated through the Biosafety Promulgation 2008, Food Safety Act 2003 and, Customs Act No.11 of 1986 Rev. 2010, Customs Regulations 1986. |
| Convention on international trade in endangered species of wild Fauna and Flora (CITES ) |  Endangered and Protected Species Act 2002 (enforced in 2003)  Endangered and Protected Species Regulations 2003 | The EPS Regulations is in the process of being reviewed. Legislation is currently with Solicitor General‘s Office for the review of fees charged to traders for the registration of companies trading endangered species. |
| Ramsar convention on Wetlands | No specific legislation | The Convention relies on the Environment Management Act 2005 for its implementation. Appropriate legislation is yet to be developed. |
| Vienna convention on the protection of the ozone layer |  Ozone Depleting Substances Act 1998  Ozone Depleting Substances Regulations | The ODS Act 1998 is currently being reviewed. |
| Montreal Protocol- substances that |  |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

measures are necessary for compliance. Laws and regulations should be regularly reviewed in

the context of the relevant international obligations and the national situations9.

4.1.2	Development of appropriate specific legislation is usually required to give the force of law to

environmental agreement obligations to ensure that they are adequately implemented.

4.1.3	There are currently 10 multilateral environmental agreements being implemented by the

Department of Environment. Audit established that only four out of the ten environmental

agreements currently implemented are supported by enabling legislations. Out of the remaining

six MEAs implemented without supporting enabling legislations, three MEAs are implemented

on the provisions of other legislations. Listed in table 4.1 below are MEAs implemented with

relevant supporting legislations.

Table 4.1: MEAs implemented and their supporting legislations

9 UNEP Manual on Compliance and Enforcement of MEA‘s, section 20

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	12

| deplete the ozone layer |  |  |
| --- | --- | --- |
| Stockholm Convention on Persistent Organic Pollutants |  Environment Management Act 2005  Environment Management (Waste Disposal and Recycling) Regulations 2007 | Reliance is also placed on the following pieces of legislation:  Health and Safety at Work Act 1996 – for registration of industrial chemicals  Pesticides Act 1971 – registration of pesticides  Public Health Act 1937 – management of public health  Pharmacy and Poisons Act 1985 – registration, control, distribution and sale of pharmaceuticals |
| Waigani Convention | No specific legislation |  |
| Apia Convention | No specific legislation |  |
| Noumea Convention for the Protection of natural resources and environment of the South Pacific | No specific legislation |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.1.4  	Audit  noted  that  the  absence  of  national  laws  have  hindered  the  effectiveness  of

implementation of Conventions. For instance, the lack of legislation to support implementation

of the Waigani Convention hinders the effective monitoring and enforcement of trans-boundary

movement of hazardous waste.

In addition, reports submitted have also reflected this deficiency. For instance the 2012

RAMSAR national report to the COP 11 meeting in Romania disclosed that the absence of

specific legislation for the RAMSAR convention has duly led to the deterioration in the national

state of Fiji‘s only wetland site.

4.1.5	Audit also noted that principal legislations were also lacking in defining key elements of

managing MEAs. For instance, although the Environment Management Act 2005 and

Environment Management Regulations 2007 are the principal legislations for the Stockholm

Convention, responsibilities of the DOE with regards to POPs management are not clearly

defined. Although the Stockholm convention also requires the development of legal and

administrative arrangements to reduce or eliminate releases from the intentional and

unintentional production and use of POPs chemicals outlined in Annex A – Annex C of the

Convention, audit noted that the banning and control of all chemicals listed in the Stockholm

Convention were not stipulated under the Environment Management Act and Regulations

despite these laws being the governing legislations.

4.1.6	In the absence of specific enabling legislations, principle concepts, obligations, rights and

duties and other institutional arrangements in regards to each Convention will not be clearly

defined thus MEA obligations may not be implemented in a coordinated and cohesive way.

4.2 Absence of standard operating procedures

4.2.1	Standard Operating Procedures (SOP) should exist to support the implementation of programs

and activities required to meet obligations under respective MEAs. Such procedures provide

detailed explanations of how a policy, program or task is to be implemented. The detail in the

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	13

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

SOP standardizes the process and provides step-by-step how-to instructions that enable the

performance of a specific task in a consistent manner.

4.2.2	As the focal point to 10 international and regional environmental agreements, the DOE is

responsible for the effective management and implementation of obligations under the

respective agreements. Activities and programs are undertaken by the six main business units

of the Department, namely:

	the Education and Awareness Unit

	the Resource Management Unit (RMU)

	the Environment Impact Assessment Unit (EIA)

	the Waste Management and Pollution Control Unit (WMU)

	the National Ozone Depleting Substances Unit (NOU) and;

	Corporate Support Services

However, the day to day management of the respective agreements is the responsibility of the

WMU, RMU and NOU as outlined in table 4.2 below.

Table 4.2: Responsible Units for Managing MEA’s within DOE

Business Unit	Relevant Conventions

Resource Management Unit [RMU]		Convention on Biological Diversity

	Cartagena Protocol

	CITES

	Ramsar Convention on Wetlands

Waste Management Unit [WMU]		Stockholm Convention

	Waigani Convention

	Noumea Convention

National Ozone Depleting Substances Unit [NOU]		Montreal Protocol

	Vienna Convention

No allocated Unit		Apia Convention

4.2.3	Based on their respective objectives and targets, different MEAs outline different obligations.

The obligations then require member parties to undertake activities that will support the

achievement of the overall objective of the agreement. Accompanying SOPs are developed to

provide guidance to the Department for the facilitation of day to day management of MEAs.

Audit noted that there were no Standard Operating Procedures in place for eight out of the ten

agreements i.e. CITES, Stockholm, RAMSAR, CBD, Waigani, Apia, Noumea and Cartagena

protocol. Only the Vienna and Montreal Protocols had SOPs providing guidance on the

clearance of imported and exported ODS commodities and equipment containing ODS.

4.2.4	From interviews held, audit gathered that a lack of proper handing over during staff

resignations and the lack of documented procedures have impacted on the ability and

effectiveness of new employees designated in performing assigned tasks.

4.2.5	Interviews with key personnel confirmed that the Department as part of its corporate plan would

develop SOPs relevant to all business units by December 2014.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	14

| Multilateral Environmental Agreement | Obligation to develop plan |  | Strategies/Plans in place | Audit Comment |
| --- | --- | --- | --- | --- |
|  | Yes | No |  |  |
| Montreal Protocol |  |  |  Methyl bromide Phase out Management Plan  CFC Phase out Management Plan  HCFC Phase out Management Plan | The Methyl bromide Phase out Management Plan and CFC Phase out Management Plan has been completed. Department through the NOU is currently implementing the HCFC Phase out Management Plan. |
| Vienna Convention |  |  |  |  |
| Convention on Biological Diversity |  |  |  National Biodiversity | Upon expiry of the NBSAP implementation framework in 2014, |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.6	In the absence of SOPs, work may not be carried out in a consistent and timely manner. New

staffs may not be aware of how to perform certain activities thus affecting the effective

achievement of obligations under respective MEA‘s.

4.3 Existence and adequateness of national plans for

implementing MEAs

4.3.1	National implementation plans (NIPs) should be required in a multilateral environmental

agreement, which should include environmental effects monitoring and evaluation in order to

determine whether a multilateral environmental agreement is resulting in environmental

improvement10.

NIPs are important in integrating MEA obligations into domestic legal, policy and institutional

frameworks. They can be used to identify strategies, policies, programmes, and plans in related

sectors through which specific measures need to be taken in order for the MEA to be effectively

implemented.

4.3.2	The need for developing plans or strategies are usually provided in the respective multilateral

environmental agreements itself. Whilst some agreements do not specify the need to develop

appropriate plans others have specific provisions outlining the need for the member country to

develop and implement them.

4.3.3	The specific process for developing a NIP and the contents of a NIP are usually set by the

particular MEA and the MEA Secretariat. However financial mechanisms such as the

Multilateral Fund and the Global Environment Facility (GEF) that provide funding to nations to

develop country programmes and NIPs may also develop guidelines covering the preparation

of such plans.

4.3.4	The development of NIPs usually follows a consultative, participatory, multi-stakeholder

process. This is usually coordinated by the Department of Environment through the appointed

steering committees. Audit found that fifty percent of the agreements managed by the

Department of Environment did not have appropriate plans/strategies in place to ensure they

are effectively implemented. Refer table 4.3 below for details.

Table 4.3: Policies, Plans and Strategies for the Implementation of MEA’s

10 UNEP Guidelines on Compliance and Enforcement of MEA‘s, section 13(b)

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	15

|  |  |  | Strategy and Action Plan 2007 (NBSAP)  Implementation Framework 2010 - 2014 for the National Biodiversity Strategy and Action Plan | another project is underway for its review. This project is known as the NBSAP Add on Project funded by UNDP |
| --- | --- | --- | --- | --- |
| Cartagena Protocol |  |  | No policy or plan currently exists | The National Bio Safety Framework is currently being drafted and yet to be approved. |
| Convention on International Trade in Endangered Species of wild Fauna and Flora (CITES) |  |  | No specific policy, plan or strategy is in place. | Management of CITES is conducted through EPS Act and Regulations however, strategies have also been incorporated into the NBSAP IF 2010 – 2014 under thematic area 5 for species conservation. |
| Ramsar Convention on Wetlands |  |  | Regional Wetland Action Plan for the Pacific Islands 2011 - 2013 | Strategies and actions are also incorporated into the NBSAP IF 2010 – 2014 under thematic area 7 for Inland Waters. The National Wetland steering committee is in the process of identifying other wetland areas after which appropriate policies and plans will then be developed. |
| Stockholm convention |  |  | National Plan for Implementation of the Stockholm Convention on Persistent Organic Pollutants in Fiji Islands 2006 (NIP) | The NIP for the Stockholm convention outlined action plans for the years 2006. The NIP became out-dated after 2007 and no other strategies and NIP‘s have been developed since then. |
| Waigani Convention |  |  | No specific policy or plan in place to deal with the trans boundary movement of hazardous waste | Despite the NSWMS acknowledging Fiji‘s membership to the Waigani convention, the strategy does not outline specific objectives, activities, roles and indicators required for monitoring and evaluation of implementing the Waigani Convention. |
| Noumea convention |  |  | No specific policy, plan or strategies in place |  |
| Apia Convention |  |  | No specific policy, plan or strategies in place |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.3.5  	Audit also found that the National Implementation Plan for the Stockholm Convention has been

out-dated since 2006. No other policies, plans or strategies were in place to outline activities

required for the effective management of POPs as required by the Stockholm convention.

Furthermore, as required by the Environment Management Act 2005, DOE under the Waste

Management and Pollution Control Unit was required to establish the National Chemical

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	16

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Management Plan based on the National Chemical Profile11. Audit found that no chemical

management plan has been prepared to ensure the sound management and disposal of

chemicals in Fiji.

Interview with the responsible officer noted that implementation of the Stockholm convention

had ceased after the completion of the POPs project in 2006. The absence of an officer to

manage the convention and the failure to review and update the NIP contributed to the failure

to appropriately implement the convention. Audit however, noted that in 2013, the updating of

the NIP has been approved and included as one of UNEP‘s regional project.

4.3.6	Review of the NBSAP Implementation Framework 2010–2014 also noted that the framework

failed to clearly identify indicators for each action, thus there was no basis of identifying the

effectiveness of monitoring and evaluating the implementation of actions indicated under

various thematic areas.

4.3.7	Failure to prepare appropriate national policies, plans or strategies directly impedes on the

successful implementation of MEA obligations.

4.4 Diversion of funds provided for the implementation of the

NIP for the Stockholm Convention

4.4.1	Article 7 of the Stockholm convention requires that each party should develop and endeavour

to implement a plan for the implementation of its obligations under this Convention12 and

review and update, as appropriate, its implementation plan on a periodic basis and in a manner

to be specified by a decision of the Conference of the Parties13.

4.4.2	A national implementation plan for the Stockholm convention was developed and approved by

Cabinet for implementation in 2006. The plan was developed with the financial assistance from

the Global Environment Facility and provided a number of specific action plans with specific

goals and objectives that reflects the requirements of the Stockholm convention.

Implementation of the plan was undertaken from 2003 to 2006.

In 2007 subsequent to the completion of the POPs project, tasks related to the management of

the Stockholm convention were absorbed into the Waste Management and Pollution Control

Unit. No funding was provided for the management of the convention for the years 2007 to

2009; however from 2010 government allocated $80,000 annually for the national

implementation plan of the Stockholm convention.

4.4.3	Audit found that despite the funding provided by government to the DOE for the NIP of the

Stockholm convention, no commitments were made for the review and update of the national

implementation plan. Audit however noted that these funds were used for other purposes not

related to the intentions it was specifically allocated for, as reflected in table 4.4 below.

11 Environment Management Act 2005, section 14(3)(f)

12 Stockholm convention, Article 7(1)(a)

13 Stockholm Convention, Article 7(1)(c)

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	17

| Year | Payment Description | Amount $ | Voucher No |
| --- | --- | --- | --- |
| 2013 | Air fares for Minister & Acting Deputy Secretary to India | 20,745.00 | 031693 |
| 2013 | Provision of Transportation during the Pacific Island Conference | 4,914.45 | 034617 |
| 2013 | Purchase of Air Tickets for Minister – Travel to Nairobi for UNEP seminar | 9,784.00 | 031093 |
| 2012 | Air tickets for Minister and PS travelling to Nairobi, Kenya 17/02 – 27/02/12 | 26,575.90 | 025604 |
| 2012 | UN Sustainable development Conference Per diem allowance – Honnin Kwonsing | 15,926.64 | 027273 |
| 2012 | Air tickets – India Trip: Taina T and Sarah T | 13,419.00 | 029086 |
| 2011 | Air Fare for Fiji Delegation to the Solomon Islands – Pacific Expanded Constituency Meeting | 6706.40 | 023606 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 4.4: Diversion of funds allocated for the NIP for the Stockholm convention

4.4.4	Audit also noted that the Department failed to appropriately monitor and report on the progress

made with regards to the implementation of the convention for each year budget was provided.

4.4.5	Failure to appropriately use funds for its intended purpose indicates a lack of emphasis and

commitment to government‘s contractual obligations.

4.5 Alignment of MEA implementation activities and targets in

organizational plans

4.5.1	Work planning provides a way of coordinating the work that needs to be done with an emphasis

on continuous improvement and innovation. In planning the organisations work, emphasis

should be placed on aligning and documenting its goals and related activities throughout its

organisational plans.

As such work plans at all levels within the organisation should incorporate performance

objectives that identify tasks/activities and expected results in relation to the management of

respective conventions.

4.5.2	Alignment of organisational goals from its strategic plan through to individual work plans are

important to ensure agreement obligations are effectively met. The following diagram illustrates

this alignment.

Figure 4.2: Alignment of IWP with organizational plans

Strategic Plan

Annual Corporate Plan

Business Plan/Annual

Individual Work Plan

Work Plan

• Sets out the

organisations

strategic objectives

• Sets out the targets

and goals of the

organisation on an

yearly basis

• Breaks down the

targets of the

organisation for

each business unit

• Breaks down the

targets for each of

the business unit at

the individual level

of the organisation

4.5.3	Audit review of the agency‘s annual corporate plans found that strategies relating to the

implementation of environmental agreements were not clearly defined for the years 2011 and

2013 despite being indicated as one of the agency‘s output. The 2012 ACP however, clearly

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	18

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

outlines the Department‘s outputs, strategies, KPI‘s, targets and relevant timelines for each of

the agreement managed by the DOE.

4.5.4	Furthermore, despite the identification of the management of regional and international

Conventions as one of the outputs in the agency‘s annual corporate plans, audit noted that

business plans failed to clearly define outputs and activities related to the management of the

Stockholm, Waigani, Noumea and Apia Conventions to ensure they were effectively

implemented.

However, strategies and activities with regards to the implementation of a number of

agreements such as CITES, Ramsar convention, CBD convention, Nagoya and Cartagena

protocols managed by RMU and the Vienna and Montreal Protocol managed by NOU were

aligned to the outputs of the agency‘s corporate plans.

4.5.5	Audit also noted that Individual Work Plans (IWP) did not clearly specify responsibilities

(activities/tasks) to be undertaken by responsible officers in the implementation of the

Stockholm, Waigani and Noumea conventions.

Furthermore, signed copies of IWP‘s were not provided to each officer responsible for

managing the implementation of respective agreements to ensure they were well aware and

accountable for all tasks assigned. Review of employees‘ personal files also noted that IWP‘s

for 2011 and 2013 were not filed.

4.5.6	At the time of audit, the Apia convention was still yet to be allocated to a Unit within the

Department for national implementation. Interview with key officers noted Fiji‘s participation in

regional meetings of the Convention, however there was no reports prepared on the progress

of national implementation of the Convention.

4.5.7	Lack of alignment between individual and group roles and the broader organisational strategy

may lead to uncertainty in role focus and unclear organisational expectations of their

performance.

4.6 Public awareness and education on MEA obligations

4.6.1	Multilateral environmental agreements communicate international governments‘ commitment to

environmental protection. Despite the foremost responsibility falling on governments to

implement the agreement, overall compliance to an MEA is dependent on the combined efforts

of many stakeholders including NGO‘s, industries, local communities and individuals.

As such, to promote compliance, parties could support efforts to foster public awareness about

the rights and obligations under each agreement and create awareness about the measures

needed for their implementation, indicating the potential role of the public in the performance of

a multilateral environmental agreement14.

4.6.2	Although the Department has an Awareness and Education Unit, education and awareness

creation activities on each MEA are developed and conducted by the Units responsible for

each respective MEA in coordination with the Awareness and Education Unit.

14 UNEP Manual on Compliance and Enforcement of MEA‘s, section 31

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	19

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.6.3	Audit noted that the Awareness and Education Unit has in place an ‗‗Integrated Communication

Strategy for the years 2010–2014‖ which integrates all education and awareness components

of the DOE‘s sections/units and focuses on eight target areas, namely:

1. Information dissemination and technology

2. Formal education

3. Community awareness

4. Partnership and networking

5. Capacity building/ training

6. Coordinating and integrating

7. Media outreach

8. Informal education

Annual action plans are then developed from the strategy which outlines the specific activities,

objective, target audience, method, responsibility, timeline and budget for respective target

areas. Audit noted that no action plans were developed for the years 2011 and 2013, however

annual reports prepared for the respective years noted that education and awareness were

conducted for the Vienna convention, Montreal Protocol, Ramsar convention, CITES and CBD.

Education and awareness include trainings and presentations provided to stakeholders,

meetings with local communities, media outreach through television broadcasts, talk back

shows and development and updating of the CHM website.

4.6.4	Furthermore, audit noted that awareness activities were not conducted for a number of

conventions namely the Stockholm, Waigani, Apia and Noumea conventions, for the years

2011 to 2013. These were attributed to lack of policy support and coordination hindering the

effective implementation of each agreement.

4.6.5	Failure to adequately conduct educational and awareness programs on MEAs may directly

impede upon the effective fulfilment of respective MEA obligation.

4.7 Review of National Measures in implementing MEAs

4.7.1	At the institutional level, the Conference of the Parties (COP) represents the primary decision

making body for a given MEA. Implementation however, at the national level is the

responsibility of the focal agency in coordination with other designated implementing agencies

and the assistance of the MEA Secretariat with donor agencies.

4.7.2	As the focal point, the Department is responsible for communications, dissemination of

information, representation at meetings, responding to various requests, collaboration with

other stakeholder groups, monitoring, promoting and facilitating national implementation of

these Conventions.

To ensure a convention is implemented in the most effective, efficient and economical manner

periodic reviews should be conducted on the measures and activities in place in implementing

an agreement.

4.7.3	Audit found that reviews on implementation of the agreements managed by DOE were

adequately conducted for CBD, CITES, Ramsar, Vienna Convention and the Montreal Protocol.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	20

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

These reviews were conducted through annual review meetings between relevant

stakeholders, internal ad hoc meetings by Unit staff and through the meeting and Conference

of Parties.

Audit noted that national review of the remaining five agreements (Stockholm, Waigani,

Cartagena, Apia and Noumea conventions) was lacking and which were attributed to the lack

of implementation on each of the convention, out-dated plans and the lack of coordination

between the relevant implementing agencies.

4.7.4	Failure to conduct timely and appropriate reviews may contribute to the risk of continuously

employing ineffective measures thus impeding on the overall effective, efficient and economical

implementation of respective MEA‘s.

4.8 Lack of in-house and capacity building

4.8.1	Capacity building and the technology transfer should be consistent with the needs and

strategies and priorities of the country concerned for enhancing compliance and assisting such

countries in meeting their obligations under their respective agreements.15

4.8.2	Capacity building at the institutional (or organisational) level focuses on the overall

organisational performances and functioning capabilities. It aims to develop the institution as a

total system including individuals, groups and the organization itself.

4.8.3	The Department of Environment has a total of more than 40 staffs who attend to the various

conventions under their respective Units. This is an additional task to the current duties under

their Units‘ responsibilities as they don‘t have a fulltime officer attending to the work required

under the Conventions. Respective units assigned for the respective Conventions are

illustrated in figure 4.3 below:

Figure 4.3: Units responsible for Conventions

ODS Unit

•Vienna Convention

•Montreal Protocol

Waste & Pollution Unit

•Stockholm Convention

•Waigani convention

•Apia convetion

Resource Management Unit

•Convention on iternational

Trade in Endangered Species of

Wild Flora and Fauna

•Convention on Bilogical Diversity

•Cartegena and Nagoya Protocol

•Convention on wetlands of

International importance -

RAMSAR

4.8.4	The audit gathered responses from staffs responsible for the respective conventions, to

establish extent of capacity building. Refer to the table 4.5 for responses:

15 (UNEP Guidelines, s.33(b)

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	21

| Conventions | Capacity Building |
| --- | --- |
| Ramsar Convention on Wetlands |  In-house awareness programs on the agreements for staff information. |
| Waigani Convention Stockholm Convention |  There were a few regional meetings/workshop on the conventions over the past years; however staffs involved has resigned from the Department.  COPs meetings for the previous years were attended by former management.  Strategic Approach to International Chemicals Management (SAICM), meetings were attended by other stakeholders in particular Min of Labour.  Last year, Senior Environment Officer (waste management) attended an inception workshop for an upcoming regional project including Fiji to assist countries in meeting objectives of the convention and this has also provided capacity building. |
| Vienna Convention on the Protection of the Ozone Layer Montreal Protocol on Substances that Deplete the Ozone Layer |  The staff has been continuously involved in international/ regional technical meetings and workshops related to implementation of Country Programme with respect to the agreements; and  On a national basis, staffs have been sent for trainings to fill in gaps in order for effective implementation of national laws. |
| Convention on Biological Diversity, NAGOYA and Cartagena Protocols |  there has been adequate capacity building in house on MEA‘s however what lacks in this matter is the understanding on how each MEA links to the other and our implementation and operations of work. With the current restructure this understanding reflects better. |
| CITES |  DOE Staffs have been attending CITES enforcement training organized in the Oceania region. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 4.5: Capacity building

4.8.5	Attending workshops has been beneficial in providing knowledge and a platform for exchange

of ideas and experiences with other countries in the implementation of their respective

strategies that could be tailor made to suit Fiji‘s implementations

4.8.6	Commitment by government as a party to the conventions in implementing legal, organizational

and environmental management measures in order to ensure compliance with the

requirements of the convention is seen to be lacking.

4.8.7	The lack of commitment on providing training on continuous basis may lead to staff not being at

par with the current developments relating to the conventions.

4.9 Lack of technical knowledge and skills

4.9.1	Participation of a wide range of stakeholders can be promoted, taking into consideration the

need for developing institutional strengths and decision-making capabilities and upgrading the

technical skills of parties for enhancing compliance and meeting their training and material

requirements16.

4.9.2	Analysis of the questionnaire distributed to DoE staff managing MEAs revealed that staffs are

knowledgeable on the requirements of the multilateral agreements as most of them have

gained a lot of knowledge on the respective agreements from exposures to meetings and

16 UNEP Manual s.33 (c)

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	22

| Business Unit | Staff personnel | Agreements &Projects | Further comments |
| --- | --- | --- | --- |
| Waste Management and Pollution Control (WPC) |  1 SEO – Waste Management  2 EOs  1 vacant EO |  Stockholm Convention  Waigani Convention  Noumea Convention | There is no staff designated for the implementation of the three conventions. At present, the Senior Environment Officer (Waste Management) is responsible for the implementation of the Stockholm and Waigani Conventions. Issues in respect to the Noumea Convention are attended to on an ad hoc basis |
| Resource Management Unit (RMU) |  1 SEO – RMU  1 Environment Officer-Awareness  2 Technical Assistants |  CITES  CBD  Cartagena  Ramsar | The SEO–RMU is responsible for administering the Conventions and assisted by the EO-Awareness and the technical assistants. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

workshops. The staffs attend the regional as well as overseas workshops and meetings in

regards to the respective multilateral agreements.

4.9.3	Audit gathered that whilst trainings are being conducted for the convention on biological

diversity trainings in the other environmental agreements are not being done. Trainings and

workshops are conducted at various intervals based on the necessity of parties in their various

work programs. Staff who attend this training then share the information learnt with the staff in

their sections.

4.9.4	Conduct of training on the agreement would facilitate ensuring compliance to their

requirements.

4.10 Lack of manpower to handle tasks

4.10.1 Adequate human resources must be provided to ensure all tasks related to the management of

environmental conventions are undertaken.

4.10.2 Audit noted that there is no designated staff specifically assigned for the management of

environmental agreements. However in addition to their normal work, DOE staffs are also

required to undertake work related to the implementation of MEAs and ensuring that the

requirements of Environmental agreements are complied with.

4.10.3 It was confirmed from discussions with staff currently administering the MEAs that the lack of

personnel had hindered the effective implementation of requirements of the agreements and

monitoring of progress of implementation. Outlined in the table 4.6 below is a breakdown of the

staff of DOE and their workload.

Table 4.6: Department of Environment Staff

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	23

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

National	Ozone	 1 ODS Project Office

Depleting	 1 ODS Inspector

Substance Unit	 4	ODS	Project

 Montreal Protocol

 Vienna Convention

UNEP funded project

Assistants

 1	vacant	ODS

Project Assistant

4.10.4 An additional 20 staffs have been approved to the Department‘s staff establishment which is

anticipated to alleviate the current work load.

4.10.5 The lack of personnel to manage specific MEAs adversely impact on the effective

implementation and monitoring of the Agreements.

RECOMMENDATIONS

The Department of Environment should ensure that:

	A gap analysis is conducted which includes the examination of all existing legislations supporting the

implementation of respective agreements. Due considerations should be made for the development of

specific legislations or, the review of existing mandates to incorporate provisions relevant to the

effective achievement of obligations under each of the Agreements.

	Appropriate SOPs are developed to serve as an instructional resource that allows employees to carry

out basic tasks in an efficient and effective manner. Communicating procedures that can easily be

followed will ensure the attainment of consistent results contributing to the effective achievement of

MEA obligations.

	Appropriate policies, plans or strategies for each agreement are developed in coordination with relevant

stakeholders. Plans should clearly articulate the strategies, objectives, actions and indicators to allow

monitoring and evaluation of each activity. Together with this, plans should also indicate the agency

responsible for each activity to avoid confusion, overlap and duplication of duties.

	Conventions are implemented where funds are provided, and seek explanations from the line Ministry

as to why funds were diverted.

	Goals and activities relevant to the effective management of MEA‘s are incorporated into all levels of the

organisational plans and clearly communicated at all hierarchical levels.

	Education and awareness programs are well planned and coordinated. Adequate attention should also

be placed on the obligations of the Stockholm, Waigani, Apia and Noumea conventions, whereby,

awareness and education programs should be designed accordingly based on the individual needs of

the respective Conventions.

	Proper review measures are in place for the Stockholm, Waigani, Cartagena, Apia and Noumea

conventions. Reviews should be conducted on a defined periodic basis to ensure agreements are

implemented in the most effective, efficient and economical manner.

	Additional staff are recruited to ensure that the obligations under each agreement is being adhered to,

for enforcement of monitoring and to ensure compliance to the Convention.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	24

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Management Comments

Absences of SOP

SOP for Ramsar, CBD, CITES – It is true that we don’t have SOP’s for the convention because implementation

of these Convention is many fold from policy level to project activities. However where necessary for instance

for CITES we have a SOP for issuance of permits and SOP for uploading information on database in the

Clearing House Mechanism under the CBD. Development of SOP has been on case by case based on necessity.

11 SOPs have been developed so far this year covering CITES and ODS.

Existence and adequateness of NIP’s on MEA’s

The need for National Implementation Plan has been recognized by DoE. NBSAP is an overarching strategy for

all biodiversity related MEA’s. We have the NBSAP Implementation Framework 2010-2014 which serves as the

NIP and work is ongoing for its review.

Yes it was a very early stage after ratification to CBD that Fiji had prepared its NBSAP. Now we are in the

process of reviewing NBSAP and one of the key things that is to be looked at is inclusion of measurable targets

and indicators. This is the same situation everywhere around the globe and that is why CBD has allocated

funding through GEF for NBSAP revision so that lessons learnt are shared and a more workable NBSAP is

formulated as a result of the revision. Fiji had its indicators in the NBSAP however it was confusing the readers

so the hope is that clearly identified indicators to be used. Also work from SoE will be consolidated in terms of

indicators.

We agree and support the recommendations provided after 4.10.6 for Implementation Arrangements for

honouring requirements of MEA's except for the last bullet recommendation which should specify the staff

posts that should be recruited (pg 24). E.g. field, technical etc.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	25

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.0 ACCOUNTABILITY	AND	REPORTING

RELATIONSHIPS

This section of the report seeks to establish accountability and reporting relationships,

and whether key agencies are meeting accountability and reporting requirements for each

MEA. It also seeks to assess whether the effectiveness of implementation is monitored.

5.0.1	The competent body of a multilateral environment agreement could, where authorized to do so,

regularly review the overall implementation of obligations under the multilateral environment

agreement and examine specific difficulties of compliance and consider measures aimed at

improving compliance. Multilateral environmental agreements can include provisions for

reporting, monitoring and verification of the information obtained on compliance17.

5.0.2	Parties may be required to make regular, timely reports on compliance, using an appropriate

common format. Monitoring involves the collection of data and in accordance with the

provisions of a MEA can be used to assess compliance with an agreement, identify compliance

problems and indicate solutions. Verification involves verification of data and technical

information in order to assist in ascertaining whether a party is in compliance, and in the event

of non-compliance, the degree, type, and frequency of non-compliance18.

5.0.3	Accountability is essential to ensuring that promises on environmental protection and

sustainable development produce credible results. The existence of accountability reporting

systems enable evaluations of key policy choices and instruments. Evaluations of key policy

choices and instruments enable government to report and measure their progress towards

environmental protection and sustainable development or to identify whether further key policy

action is required.

5.0.4	Reporting requirements are defined by the terms of each MEA. Information gathered is collated

and submitted as national report to the Secretariats of the respective MEA. These may be

supplemented by independent data (often from NGOs) or some form of inspection. Information

gathered can be used to assess compliance with respect to implementation of commitments for

each MEA, or to monitor breaches. The provision of periodic reports as required under each

MEA in a timely manner is indicative of government meeting its international commitment.

5.1 Monitoring implementation of Conventions

5.1.1	Monitoring involves the collection of data in accordance with the provisions of each respective

MEA and can be used to assess compliance with an agreement, identify compliance problems,

and indicate solutions19.

5.1.2	Monitoring provides a means for ensuring that implementation goes according to plan. Similarly

evaluation enables the determination of whether the Conventions have fulfilled their objectives

or not. Monitoring and evaluation are therefore essential elements for any process.

17 UNEP Guidelines on compliance with and enforcement of MEAs s.13

18 UNEP Guidelines on compliance with and enforcement of MEAs s.14(c)

19 UNEP Guidelines on compliance with and enforcement of MEAs s.14(c)

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	26

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.1.3	The Department of Environment as focal agency is responsible for the collation of data in

coordination with relevant stakeholders. Audit noted that no Memorandum of Understanding

(MOU) is in place between the DoE and the respective agencies except for the Montreal and

Vienna Conventions. The DoE has an MOU with the NGOs and the Fiji Customs Authority for

the two Conventions.

5.1.4	Audit noted that meetings are being conducted with the DoE and the stakeholders via the

various committees formed in respect to the various Conventions. These meetings convened

between the DoE about the stakeholders discuss compliance issues, mechanisms and

procedures regarding the Conventions.

A challenge faced by the DoE is that the Department is not always being involved in the initial

stages of negotiation but once things are formalised then the DOE is being informed to draw up

policies needed for the conventions without being a party to the discussion from the beginning.

The communication lines are not clearly defined thus posing a lot of problems amongst the

stakeholders.

5.1.5	Audit gathered from discussions held with officers responsible that the monitoring of the

implementation of the Conventions is a challenge for the DOE as it is quite huge to monitor and

its scope quite difficult to define. Monitoring the implementation of conventions is also hindered

by a lack of resources and manpower. Audit noted that the current staffing levels are not

sufficient to enable efficient monitoring.

5.1.6	The lack of staffs to conduct monitoring of implementation of the conventions indicate a lack of

consideration of resource capabilities to handle requirements for implementation of

Conventions at the outset by the negotiating parties when agreeing to be a party to the

Conventions.

5.1.7	In addition lack of coordination between relevant stakeholder agencies may result in

inconsistencies in work procedures, overlapping of roles and duplicate use of resources.

5.2 Internal Reporting

5.2.1	Cabinets/Parliaments should be informed regularly on the activities undertaken by the

implementing and focal agencies of respective conventions. Information can be relayed through

reports which can be used to assess in a transparent manner the measures that have been

taken to implement commitments, consider the effectiveness of those measures and deliberate

on areas of improvement.

5.2.2	The DOE normally prepares Cabinet Papers for internal reporting purposes to Government.

The existence of internal reporting process exists for Biodiversity whereby a reporting

mechanism has been developed (national process) plus at intervals the MEAs themselves

require parties to submit national reports which are undertaken through a consultative process.

The other Conventions have yet to establish a reporting process.

5.2.3	The DOE is required to submit for Cabinet‘s endorsement reports describing compliance with

the MEA requirements which are to be forwarded to the respective Convention Secretariats. It

is also required to provide and update to Cabinet through its line Ministry undertakings from

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	27

| Conventions | Submissions to Cabinet | Frequency of reporting |
| --- | --- | --- |
| Ramsar Convention on Wetlands | Yes | Before CoP meeting |
| Waigani Convention Stockholm Convention SAICM | Reports were prepared back in 2006 through the POPs Project Unit and submitted to Cabinet. However, from 2007 till to date, the unit is not aware of any reports prepared and submitted to Cabinet after COPs. | Seldom |
| Vienna Convention and Montreal Protocol | No, only the focal agencies prepare reports as and when the need arises. | Based on national importance which requires policy directions for the country or submission to Cabinet for information purposes. For example, any changes to the Conventions, strategies that needs to be implemented, etc. |
| Convention on Biological Diversity | Yes in the past we have submitted reports on biodiversity and also for various other work programs emanating from the convention | Based on the need or when there is something that needs to be drawn to Cabinet‘s attention such as important national reports, national consultative summaries, meetings etc. |
| CITES | Yes | Before CoP Meetings |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

meetings attended. Table 5.1 reflects responses on whether the monitoring units within DOE

are submitting reports to Cabinet prior to and after attending meetings.

Table 5.1: Submission of reports

5.2.4  	During the course of audit it was also revealed that most of the reports and papers prepared for

submission to Cabinet have been misplaced due to the many relocations of the DoE‘s office

and a lack of storage space to properly store the Department‘s documentary records.

5.2.5	Proper maintenance of documentary records ensure the availability of information which

supports accountability and contributes towards corporate knowledge.

5.3 External Reporting

5.3.1	The conference of the parties of a multilateral environment agreement regularly review the

overall effectiveness of the agreement in meeting its objectives, and consider how the

effectiveness of a multilateral agreement may be improved20.

Parties may be required to make regular, timely reports on compliance, using an appropriate

common format. Simple and brief formats could be designed to ensure consistency, efficiency

and convenience in order to enable reporting on specific obligations21.

5.3.2	The DOE as the focal agency for most of the Conventions is required to submit reports to the

Secretariat of each respective Convention. The reports are discussed at the CoP meetings held

for each Convention.

20 UNEP Guidelines on compliance with and enforcement of MEAs s. 15

21 UNEP Manuals s 14(1)

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	28

| Conventions | Reports submitted to CoP |
| --- | --- |
| Convention on Biological Diversity | th  4 National report submitted on 8/7/10  NBSAP implementation framework – 7/8/12 nd  2 national report – 15/5/01 st  1 national report 7/1/98  NBSAP |
| Cartagena protocol |  Report was due on 11 September 2005 Fiji is yet to submit a report  The meeting of the parties to the protocol (COP-MOP) adopted a reporting format and requested parties to submit reports every 4 years but in the initial 4 year period to submit an interim report after every 2 years after entry into force of the protocol. The first report was due on 11 September 2005 and the first regular national report was due on 11 September 2007 |
| Nagoya Protocol |  Protocol is still new and hasn‘t submitted a report as yet |
| CITES |  Article VIII para 7 says that each party is to submit Annual Report on its CITIES trade containing summary of infomation. The annual reports submitted are for 2007- 2011.  The party is also required to submit Biennial Reports which is yet to be submitted |
| Ramsar |  National report 2008 COP meeting th  National Report for Fiji to the 4 Oceania Regional meeting for RAMSAR |
| Montreal & Vienna Convention |  Country Programme Report submitted to Multilateral Fund Secretariat and Article 7 Report to the Ozone secretariat. This reporting is mandatory that determines the compliance and funding release of countries. Reporting is done on an annual basis on the 1st of May each year and Fiji started reporting as far back as 1986. |
| Stockholm Convention - SAICM |  Not aware of meeting reports prepared by the former Director or by Ministry of Labour as there were no proper handing over of meetings attended and/or reported. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

The reporting requirement and reporting format for reports submitted to CoPs varies amongst

the Conventions because of the nature of information each MEA seeks from the Parties. The

formats of the reports submitted to CoPs for each of the Conventions are standardised and

members are obligated to comply with the reporting requirements. However the reporting

submission timelines are not always being adhered to by the DOE as the lead agency for these

agreements. Listed in Table 5.2 below are reports submitted to the Secretariat of the various

Conventions.

Table 5.2: Reports submitted to the Secretariat of the various conventions

5.3.3	Audit was not able to obtain most of the reports from the DOE due to unavailability of records at

the DOE, thus the other reports were obtained from the Conventions‘ respective websites.

Copies of the report were not always maintained by the Department of Environment and which

were aggravated by the fact that no proper handing over was done when staff moved out of the

Department of Environment.

5.3.4	In addition to reports submitted to CoPs, the Department of Environment being the focal

agency is also required under strategy output 3 of its annual corporate plan (ACP) to prepare

compliance reports on the Conventions and submit to the line Ministry. Audit gathered that

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	29

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

such reports have not been done. Reflected in table 5.3 below are responses provided on

whether compliance reports are submitted.

Table 5.3: Submission of compliance reports

Conventions	  Submission of compliance reports

Convention  on  Biological	None

Diversity

Cartagena protocol	 None

Nagoya Protocol		None

CITES		None

RAMSAR		None

Montreal	&	Vienna	No, as the implementing agency/ Ozone Secretariat/ Multi-lateral

Convention	Fund Secretariat does the non- compliance reporting.

Stockholm Convention	Not aware of any report prepared for non-compliance on the

conventions over the past years.

5.3.5	Failure to prepare consistent and compliance reports will lead to the lack of knowledge as to

the progress on the implementation of the conventions. Failure to prepare and

submit compliance reports will also lead to withholding of funds by secretariats and also non-

compliance to the treaties

5.4 Participation in international and regional meetings

5.4.1	To build and strengthen capacities for enforcement, states should participate in international

meetings, courses and training programs, as well as in regional and global networks to facilitate

sharing information and access to implementation and training materials22. Apart from its

participation, states should ensure that it is well and appropriately represented in these

meetings.

5.4.2	The Conference of the Parties (CoP) is the forum for discussion of the Conventions, and

advances implementation of the Convention through the decisions it takes at its periodic

meetings. All States that are Parties to the Convention are represented at the CoP. Matters for

discussion at the meetings include reviews of implementation of the Conventions, and any

other legal instruments that the CoP adopts. The CoP makes decisions necessary to promote

the effective implementation of the Convention, including institutional and administrative

arrangements. Audit gathered from discussions with the Director of Environment that Fiji has

been an active member in the chairmanship of the CoP meetings.

5.4.3	The meetings of CoPS for most Conventions are scheduled on an annual basis whilst some

Conventions have their CoP meeting every two years. In addition to the COPS meetings, other

meetings are also held during the year. For example the Vienna Convention and the Montreal

Protocol have various meetings before the Meeting of Parties.

5.4.4	Attendees at meetings are required to prepare a report on matters discussed during the

meetings.

22 UNEP Guidelines, s.49e

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	30

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.4.5	Audit gathered that the Department of Environment as the focal agency represents the

Government of Fiji to the CoPs meetings for most of the Conventions except SAICM, which is

attended by Ministry of Labour officials. Listed in Table 5.4 below are the types of meetings

held for each Convention attended by the focal agencies.

Table 5.4: Meetings held for respective Conventions

Convention	Meetings held	Attendees at meetings

RAMSAR	1 regional and 1 international	Senior level management

Waigani Convention

Stockholm

Convention

COPs for the Waigani Convention meet Former Director DOE

every two years.

COPs for the Stockholm Convention meet Former Director DOE attended

every three years. the last meeting of the

Stockholm convention in 2009

SAICM

-

Attended by Ministry of Labour

officials

Vienna Convention	1 International:

and	Montreal	Meeting of Parties [MOP] (1);

Protocol

Minister/ Permanent Secretary/

Deputy Secretary/ Director of

Environment and ODS Project

Office

& Pacific Network Mtg (1).

ODS Project Officer and ODS

 Open- Ended Working Group [OEWG]	Deputy Secretary/ Director of

(1);	Environment and ODS Project

Officer,	and	ODS	Project

assistant

 Executive Committee [ExCom] to the	ODS Project Officer and ODS

Montreal Protocol Meetings- co-opted	Project Assistant

member for 2014 (1);

 South-East Asia and the Pacific	ODS Project Officer and ODS

Network [SEAP] Mtg (1);	Project Assistant

 Joint South Asia [SA]/ South-East Asia	ODS Project Officer and ODS

Project Assistant

2. Regional:

	Pacific Island Countries Network	Project Assistant

Meeting (1)

Convention	on	COP is held at intervals of either 2 years	attended by DOE officers

Biological Diversity

or 4 years.

However they have at least 3-4 different

types of meeting such as technical

meetings, regional meetings

CITES	1 regional and 1 international	Senior level management

5.4.6	Fiji only attended the CoP meeting for the Waigani Convention and did not attend the joint COP

meeting for the Stockholm Convention, Basel Convention and Rotterdam Convention in 2010

and in 2013. Audit confirmed that Fiji last attended the CoP for the Stockholm Convention in

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	31

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2009. Attendances prior to this could not be established due to a lack of records maintained by

the Unit.

5.4.7	In addition audit noted that attendees submitted their reports for meetings attended except for

those attending the Strategic Approach to International Chemicals Management (SAICM23)

meetings. Reflected in table 5.5 below are responses to whether reports were submitted for

attendances at meeting and the dissemination of outcomes of meetings.

Table 5.5: Feedback to questionnaire on whether reports were submitted

Convention	Report submitted

Ramsar  Convention  on	Yes

Wetlands

Waigani Convention

Stockholm Convention

SAICM

Not aware of meeting reports prepared by the former Director or by

Minister of Labour as there were no proper handing over of

meetings attended and/or reported.

Vienna  Convention  and	Yes, reports are prepared and sent to Public Service Commission to

Montreal Protocol	the Permanent Secretary of the Ministry on the outcomes of each

respective meeting.

Convention on Biological	Yes, the report is sent to management for information, PSC and

Diversity	also shared with stakeholders on important matters

CITES	 Yes reports are prepared

The DOE only maintains copies of reports on meetings attended by the DOE staff. Reports on

outcomes from the SAICM meetings attended by the Ministry of Labour officers were not

produced for audit scrutiny. Audit was not able to obtain confirmation on the issue from the

Ministry of Labour despite follow ups with the Principal Technical Officer OHS.

5.4.8	The non-submission of reports is indicative of a lack of accountability by the Ministry of Labour

in communicating to the DoE outcomes of meetings attended that would enable the sharing of

experiences to enhance management and disposal of chemicals.

5.5 Dissemination of outcome of meetings and conference of

parties

5.5.1	Dissemination of information on the deliberations and outcomes of conventions and meetings

should be undertaken to ensure all relevant stakeholders are aware of decisions and outcomes

of such meetings affecting the implementation of MEA‘s24.

5.5.2	Meetings are held with respective stakeholders to deliberate on issues discussed at the

meetings of conference of parties. Stakeholders include Government Ministries and

departments, non-government organisations (NGOs), tertiary institutions, oil companies, and

statutory bodies i.e. Fiji Islands Revenue and Customs Authority (FRCA) and Bio Security

Authority of Fiji (BAF). Stakeholders are then required to proactively implement requirements of

the Convention.

23 The Strategic Approach to International Chemicals Management (SAICM) is a policy framework fostering the sound management of chemicals which was

adopted in Dubai (UAE) on the 6th of February 2006.

24 Good Practices

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	32

| Conventions | Frequency of meetings | Issues discussed | Do the agency conduct meetings to discuss the issues deliberated from the meetings of COP? |
| --- | --- | --- | --- |
| RAMSAR | Biannually |  Ramsar site  Management plan  Information sheet on the Ramsar site | Yes |
| Waigani Convention Stockholm Convention | No meeting has taken place for the past 8 years on the outcome of COPs. | No meeting has taken place for the past 8 years on the outcome of COPs. | No meeting has taken place for the past 8 years on the outcome of COPs. |
| Vienna Convention and Montreal Protocol | During contact group meetings, side- events and bilateral meetings especially for OEWG and MOP. | Normally, a Conference Room Paper[CRP] by concerned party is circulated for discussion during the contact group meeting while the outcomes of side- events that are relevant to the focal agency is included in its respective reports. | Yes, the outcomes are disseminated within the Ministry as well as the respective stakeholders. |
| Convention on Biological Diversity | Biodiversity Stakeholders meet at least 4 times in a year apart from the smaller working groups that meet more often, at least once in 2 weeks (These meetings have different focus but same groups) | The DOE is the Secretariat and makes minutes for all these meetings. Issues of concern on various thematic areas that have been derived from these MEAs such as for CBD on the 7 thematic areas of NBSAP. | Yes, for the CBD there is always a national standpoint, national priorities discussed before and after the COP‘s. COP deliberations, discussions and resolutions play an important role in national meetings. |
| CITES | Quarterly | Thematic 5 and Issues on the Endangered species | Yes |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.5.3	Responses to questionnaire issued regarding regularity of meeting with stakeholders are tabled

in table 5.6 below.

Table 5.6 Dissemination of Information

From the analysis above it can be seen that the only Conventions that has not met with its

stakeholder for the past 8 years is the Stockholm Convention which needs to be strengthened

to ensure that they are made aware of the progress of the implementation of the Conventions.

5.5.4	Non dissemination of outcomes of meetings will result in stakeholders being unaware of the

happenings with the other member countries in regards to the Conventions.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	33

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.6 Maintenance of a database to provide information on

environmental agreements

5.6.1	A database should be created and appropriately maintained to provide an efficient information

network nationwide for the environmental agreements. The database should be coordinated to

enhance its ability to monitor and control and also ease the work in the assessment of the

implementation stages of the Conventions.

5.6.2	The information should include among other things, the number of reports issued, awareness

programs made in respect to the conventions, the level of compliance in respect to the

requirements of the convention, the number of stakeholders and their roles in the

implementation of the conventions. The database should also include the number of meetings

attended, trainings, workshops conducted and the dissemination of outcomes of meeting with

the stakeholders.

5.6.3	The Department of Environment does not have a database on the multilateral agreements that

the Department is the focal agency of.

5.6.4	The absence of a database is a hindrance to the effective sharing of vital information regarding

Conventions between concerned stakeholders. Having a database will ensure the timely

monitoring of the progress of implementation the Conventions.

RECOMMENDATIONS

The Department of Environment should ensure that:

	an effective monitoring strategy to include the frequency of monitoring as well as the roles and

responsibilities of respective officers is developed.

	effective coordination is being maintained to ensure that there is no duplication of work amongst

stakeholders;

	documented copies of the reports sent to the Cabinet, Convention Secretariats, etc; are maintained and filed

in the relevant subject files maintained for each convention for records purposes and for ease of reference,

and for ease of work of new staff assuming roles of reporting on the conventions

	reports are consistently prepared including the compliance reports on the conventions.

	a copy of reports for attendances at meetings is being maintained in the respective subject file maintained

for each Convention for ease of reference. This will also ensure that desk officers for the respective

conventions are aware with the issues being deliberated at the meetings.

	outcomes of meeting are disseminated to all stakeholders so that all concerned parties are aware of the

progress and the new challenges ahead of them in regards to the conventions.

	a database is established for effective sharing of information and for ease of reference.

Management Comments

We agree and support the recommendations.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	34

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.0 CONCLUSION

6.1	Although there are arrangements in place for the implementation of the multilateral

environmental agreements that Fiji is a party to, the effectiveness of implementation of

requirements of certain Conventions are impacted by lacks in certain aspects of the

arrangements in place for honouring MEA and which need to be strengthened. For instance,

the absence of adequate implementing legislations, SOPs and national plans for some

agreements impact the effectiveness of implementation of the Conventions.

Effective implementation is also thwarted by inactions such as failures to update and implement

the national implementation plan despite funding provided by Government [Stockholm

Convention], and failure to adequately review the implementation of a number of agreements.

However, despite the lack of capacity building for a number of the conventions and lack of

manpower to effectively carry out tasks with regards to the implementation of the conventions,

the Department of Environment has made tremendous efforts in implementing relevant MEAs

given its available resources.

6.2	The effectiveness of monitoring of the conventions is adversely affected by a lack of funds and

a lack of resources available to the Department of Environment. The Department needs to

comply with the Conventions reporting requirements and ensure that reports are sent in a

timely manner.

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	35

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

7.0 REFERENCES

1.	Apia Convention on Conservation of Nature in the South Pacific

2.	Biosafety Promulgation 2008

3.	Cartagena Protocol on Biosafety

4.	Convention on Biological Diversity

5.	Convention on International Trade of Endangered Species

6.	Convention on Migratory Species

7.	Customs Act No. 11 1986 Rev. 2010

8.	Customs Regulation 1986

9.	Department of Environment – Annual Report 2013

10.	Department of Environment – Business Plans 2013

11.	Department of Environment Annual Report 2013

12.	Endangered and Protected Species Act 2002

13.	Endangered and Protected Species Regulations 2003

14.	Environment Management (Waste Disposal and Recycling) Regulations 2007

15.	Environment Management Act 2005

16.	Implementation Framework 2010 – 2014 for the National Biodiversity Strategy and Action Plan

2007

17.	Integrated Communication Strategy 2010 – 2014

18.	Manual on compliance with and enforcement of Multilateral Environmental Agreements

19.	Ministry of Local Government, Urban Development, Housing and Environment - Annual

Corporate Plan 2011

20.	Ministry of Local Government, Urban Development, Housing and Environment - Annual

Corporate Plan 2012

21.	Ministry of Local Government, Urban Development, Housing and Environment - Annual

Corporate Plan 2013

22.	Montreal Protocol on substances that deplete the Ozone Layer

23.	National Biodiversity Strategy and Action Plan 2007

24.	National Implementation Plan for the Stockholm convention 2006

25.	National Solid Waste Management Strategy

26.	Noumea Convention for the protection of the Natural Resources and Environment of the South

Pacific Region

27.	Ozone Depleting Substances Act 1998

28.	Ozone Depleting Substances Regulations 2010

29.	Ramsar Convention on Wetlands

30.	Standard Operating Procedures for the clearance of Imported and exported ODS commodities

and equipment containing ODS

31.	Stockholm Convention on Persistent Organic Pollutants

32.	UNEP Guideline on compliance with and enforcement of Multilateral Environmental

Agreements

33.	Vienna Convention on the protection of the Ozone Layer

34.	Waigani Convention

MANAGEMENT OF MULTILATERAL ENVIRONMENTAL AGREEMENTS	36

MANAGEMENT OF RURAL

ELECTRIFICATION

PROGRAM

A Performance Audit Report

of the Office of the Auditor

General of the Republic of

Fiji

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Demand for electricity has increased significantly in the past few years, especially in the rural areas. The power

sector ensures that the entire population has access to electricity through the extension of Fiji Electricity Authority

(FEA) grid network, stand-alone systems by the Department of Energy (DOE), and extensions from government

stations by the Public Works Department (PWD). There is an expectation that by 2011 the country would have

90%national electrification coverage where the urban areas would have 100% access to electricity and the rural

areas 85% access.

The Rural Electrification Unit (REU) within the Department of Energy (DOE) administers and controls the rural

electrification program, a Government initiative aimed at electrifying rural areas. This report assesses the

effectiveness of the REU in managing the implementation of this initiative by examining:

	the management framework of rural electrification program;

	the administration and implementation of rural electrification program; and

	the monitoring and inspection of projects under the REP.

Table of Contents

1.0	EXECUTIVE SUMMARY..........................................................................................................3

2.0	INTRODUCTION.......................................................................................................................5

2.1	Background .......................................................................................................................5

2.2	Reasons for the audit ...........................................................................................................5

3.0	AUDIT OBJECTIVES, SCOPE AND METHODOLOGY ...........................................................7

3.1	Audit objectives and scope ....................................................................................................7

3.2	Audit methodology...............................................................................................................7

4.0	MANAGEMENT FRAMEWORK OF RURAL ELECTRIFICATION PROGRAM .......................9

4.1	Policy and Procedures for the Rural Electrification Program..........................................................9

4.2	Implementing agency .........................................................................................................11

4.3	Human resources..............................................................................................................13

4.4	Planning for Rural Electrification Projects ...............................................................................15

4.4.1	Funding of REU programs ...............................................................................................16

5.0	ADMINISTRATION AND IMPLEMENTATION OF RURAL ELECTRIFICATION PROGRAM18

5.1	Rural Electrification applications ...........................................................................................18

5.2	Diesel generator scheme ....................................................................................................20

5.2.1	Diesel scheme arrangements ...........................................................................................20

5.2.2	Utilisation of diesel schemes ............................................................................................21

5.3	Solar Scheme...................................................................................................................22

5.3.1	Installation of equipment ..................................................................................................23

5.3.2. Installation arrangements – Renewable Energy Service Company (RESCO) ........................	25

5.4	Community Contribution .....................................................................................................27

5.5	Records maintenance ........................................................................................................28

5.5.1	Filing arrangements ........................................................................................................29

5.5.2	Data recording ................................................................................................................29

5.6	Public Awareness Activities .................................................................................................31

5.7	Completion of projects........................................................................................................31

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	1

| AWP | Annual Work Plan |
| --- | --- |
| DOE | Department of Energy |
| FEA | Fiji Electricity Authority |
| GTB | Government Tender Board |
| HR | Human Resource |
| IWP | Individual Work Plan |
| MQR | Minimum Qualification Requirement |
| NGO | Non-Government Organisations |
| OIC | Officer in Charge |
| PSC | Public Service Commission |
| PSIP | Public Sector Investment Program |
| PTO | Principal Technical Officer |
| PV | Photo Voltaic |
| PWD | Public Works Department |
| RE | Rural Electrification |
| REP | Rural Electrification Program |
| RESCO | Renewable Energy Service Companies |
| REU | Rural Electrification Unit |
| SGH | Supervisor Higher Grade |
| SHS | Solar Home Lighting System |
| SOP | Standard Operating Procedures |
| TA | Technical Assistant |
| TNK | Turaga ni koro |
| TOR | Terms of Reference |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.0	MONITORING AND INSPECTION OF PROJECTS UNDER THE REP ................................33

6.1	Monitoring during installation ...............................................................................................33

6.2	Inspection of Projects .........................................................................................................34

6.3	Monitoring resources .........................................................................................................35

6.4	Monitoring and evaluation of rural electrification projects............................................................35

7.0	CONCLUSION ........................................................................................................................37

8.0	REFERENCES ........................................................................................................................38

APPENDIX 1:	GENERATORS INSPECTED AND POWERHOUSES.........................................39

APPENDIX 2: COST OF SOLAR SYSTEMS PER HOUSEHOLD ...................................................	40

APPENDIX 3: INCOMPLETE ENTRIES IN SPREADSHEET ..........................................................	46

APPENDIX 4: COMPLETED PROJECTS ........................................................................................	47

____________________________________________________________________________________________________________________

Acronyms

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	2

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

1.0	EXECUTIVE SUMMARY

Background	Energy is of crucial importance for the socio-economic development of Fiji. Access to energy services

has been identified as a necessary prerequisite for sustainable development, since it can lead to

improvements in household health, education and income levels. Thus it’s important to the public and

government.

The Rural Electrification Program (REP) is a rural empowerment program, where the government

through the Department of Energy, cost share with the recipient rural communities on the funding of

rural electrification projects for their communities.

The programs were intended to support Government Rural Development policy aimed at improving

living standards in the rural areas through electrification, so that disparity of living conditions between

the urban centres and the rural areas can be reduced. It was also aimed at reducing rural urban drift of

rural population

Coverage	The audit on Management of Rural Electrification Program looked into three areas namely

“Management Framework of Rural Electrification Projects”, “Administration and Implementation of

Rural Electrification Projects”, and “Monitoring and Inspection of Projects under the REP”.

The audit examined records for the rural electrification program for the 5 years 2008 to 2012

maintained by the Rural Electrification Unit. Audit also extended its scrutiny to 2013 records for the

current period.

Key findings	Management Framework of Rural Electrification Program

	Framework for the management of rural electrification projects exists and is defined through the

Rural Electrification Policy 1993 and Standard Operating Guidelines. These however need to be

reviewed to incorporate current practices, roles and responsibilities.

	The current structure of the Department of Energy has been in existence for more than 20 years

and has an effect on the effective implementation of the program.

	There is a need for recruitment of more staff and the provision of adequate training for employee

skills enhancement and development.

Administration and Implementation of Rural Electrification Program

	Applications are not always supported by required documentation as required.

	Once installed, use of diesel generator schemes are not always exploited by beneficiaries.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	3

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	There is no approval for variations in parts installed for solar systems and requirements as per the

Policy. Recoveries of monthly fees under the RESCO are not evident.

	Recoveries of community contributions could not be ascertained.

	Records maintenance and security of records is lacking.

Monitoring and Inspection of projects under the REP

	Contradictory reports on inspections

	Improvements noted in monitoring processes include revision to regularity of contractual payment.

	Monitoring activities are hindered by a lack of resources

	Monitoring and evaluation reports were not submitted for audit scrutiny.

Overall	Management of rural electrification program is adequately managed despite resource constraints.

Conclusion	Legal and institutional framework exists to provide guidance on the proper implementation and

management of the rural electrification program even though they may require reviews to keep them

relevant and authoritative.

In addition, deviations in the administrative issues such as adherences to requirement of the

application process, records maintenance, etc.; need to be strengthened to ensure accountability.

General	To ensure effectiveness of management of rural electrification program, audit recommends that the

Recommendation DOE review its current policy and guidelines to incorporate current practices to ensure its relevance

and authoritativeness.

It should also ensure adequate resources are provided to enable efficient and effective program

implementation and monitoring.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	4

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.0 INTRODUCTION

This section of the report provides a brief background of the topic being audited and also

provides reasons for conducting the audit.

2.1 Background

2.1.1	The great demand for electricity by rural areas in the early 1970s arising out of changing lifestyles

and the desire for gaining a better standard of living for the rural population prompted Government

to implement the rural electrification program. The rural electrification program was initially directed

by the 1973 Rural Electrification Policy with the intention of improving the well-being of the rural

population.

2.1.2	The REP is a rural empowerment program, where the government through the Department of

Energy (DOE), cost share with the recipient rural communities on the funding of the REP for their

communities. These programs were intended to support the Government Rural Development policy

aimed at improving living standards in the rural areas through electrification, so that disparity of

living conditions between the urban centres and the rural areas would be reduced. It was also

aimed at reducing rural urban drift of rural population.1

2.1.3	The RE Policy developed in 1973 provided for the implementation of the schemes based on a 2/3

contribution from the government and 1/3 (or 33%) from the local community. Under this

arrangement the government owned the schemes and maintained them. This policy was restricted

to the supply of stand-alone diesel generators with servicing carried out by the DOE for an annual

fee of $100 from the community.

2.1.4	The Rural Electrification Unit (REU), a unit within the DOE was established to spearhead the

implementation of the rural electrification projects aimed at equitable regional distribution of

electricity and increasing rural electricity access to almost 100% by 2014 as per the 1993 RE

policy. As of to date the estimated connectivity to electricity is 90%.

2.2 Reasons for the audit

2.2.1	Energy is of crucial importance for the socio-economic development of Fiji. Access to energy

services has been identified as a necessary prerequisite for sustainable development, since it can

lead to improvements in household health, education and income levels.

2.2.2	Government has invested substantial amount of money in providing electricity throughout the

country. Accessibility of electricity in the rural areas is challenging in terms of the cost involved.

Budget provided to the Rural Electrification Unit and actual expenditure incurred for the REP over

the past 5 years 2008 to 2012 are outlined Table 2.1 below.

1 CP(10)07 – s. 2.0 paragraph 2.2

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	5

| Year | Budgeted Expenditure $ | Actual Expenditure $ | Savings $ |
| --- | --- | --- | --- |
| 2008 | 6,000,000.00 | 5,337,238.85 | 662,761.15 |
| 2009 | 18,887,719.00 | 18,769,062.52 | 118,656.48 |
| 2010 | 5,892,405.00 | 5,723,004.57 | 169,400.43 |
| 2011 | 6,307,991.00 | 5,711,711.82 | 596,279.18 |
| 2012 | 6,963,460.00 | 6,963,035.68 | 424.32 |
| Total | 44,051,575.00 | 42,504,053.44 | 1,547,521.56 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 2.1: Budget and actual expenditure for 2008 to 2012

The  above  table  shows  significant  amount  spent  on  the  alternative  energy  source  and  they

managed to save in the past five years.

2.2.3	A performance audit on the topic has never been conducted. Annual regularity audits conducted

and internal audits by the Ministry of Finance have raised numerous anomalies. Some of the major

anomalies include paying contractors for incomplete projects; improper budgeting for the following

year‟s project; villages and individuals not giving initial payment; procurement done without

involving store man; splitting of payment vouchers for payments for projects; items not recorded in

Fixed Asset Register and Expendable Items Register; cannibalisation of generators; late

installation of generators after purchase; lack of REU database to record completed projects;

tender procedures not followed; contract recommendation not made after each completed phase;

inspection of projects not done after each phase; revision made to initial payment calculation;

wiring on houses not done; and survey not properly carried out; etc.

Thus an audit of this topic would identify improvements for strengthening the management of rural

electrification programme.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	6

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

3.0 AUDIT	OBJECTIVES,	SCOPE	AND

METHODOLOGY

This section of the report describes the objective and scope for this audit. It also discusses the

methodology utilised to gather information for the audit.

3.1	Audit objectives and scope

3.1.1	The objective of the audit is to assess the efficiency and effectiveness of the management of the

rural electrification program by examining:

 the management framework for the rural electrification program;

 the administration and implementation of the rural electrification program; and

 the monitoring and inspection of projects under the REP.

3.1.2	The audit covered records of the rural electrification programs managed by the Rural Electrification

Unit for the years 2010 to 2013.

3.1.3	The audit focused on all the rural electrification schemes managed by the REU that provide

electricity through the following means:

1. Stand-alone diesel schemes

2. Extensions of FEA grid network

3. Renewable energy based schemes i.e. solar power and non-grid electrification systems

3.1.4	The audit did not cover the provisions of electricity through extensions from government stations,

and renewable energy based scheme using hydro power.

3.2	Audit methodology

3.2.1	The audit was conducted using the following evidence gathering techniques.

i.	Interviews

Interviews were carried out with relevant officers of the Department as listed in table 3.1

below.

Table 3.1: Details of officers interviewed

Officer

Director REU

Principal Technical Officer REU

Senior Technical Officer REU

SHS officer in charge

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	7

| Site | Dates |
| --- | --- |
| Waivaka | 24/09/13 |
| Narukunibua | 24/09/13 |
| Nasigatoka | 24/09/13 |
| Namosi village | 25/10/13 |
| Navunibau | 25/10/13 |
| Nawailevu | 01/10/13 |
| Nasarawaqa | 01/10/13 |
| Seaqaqa | 01/10/13 |
| Dreketilailai | 02/10/13 |
| Wairiki | 02/10/13 |
| Saqani secondary | 02/10/13 |
| Labasa REU office | 03/10/13- 4/10/13 |
| Nayaroyaro | 05/10/13 |
| Nasinu | 05/10/13 |
| Viani Primary | 05/10/13 |
| Bagasau | 06/10/13 |
| Vunikura | 06/10/13 |
| Bucalevu | 06/10/13 |
| Waimaqera | 09/10/13 |
| Wairiki | 11/10/13 |

| Document | Source |
| --- | --- |
| Rural Electrification Policy (1993) | Department of Energy |
| Cabinet Papers and Cabinet Decisions | Cabinet Office Department of Energy |
| Applicants file | Department of Energy |
| Contract files | Department of Energy |
| Tender files | Department of Energy |
| Project excel spread sheet | Department of Energy |
| SHS report | Department of Energy |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

ii.	Documentary review

The audit reviewed a number of documents to gather information on rural electrification

projects. The major documents reviewed are outlined in table 3.2 below:

Table 3.2: Details of documents reviewed and source during the audit

iii.	Site visits

Site visits were also undertaken. The areas visited together with the date of visits are

outlined in table 3.3 below.

Table 3.3: Details of site visits

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	8

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.0 MANAGEMENT	FRAMEWORK	OF

RURAL ELECTRIFICATION PROGRAM

This section of the report discusses the sufficiency and effectiveness of the management

framework in providing and planning for rural electrification program by the REU. It looks

into the institutional arrangements in place for implementing the rural electrification projects

and the sufficiency of funding and resourcing to enable effective implementation of the

projects identified.

4.0.1	The Rural Electrification Program is a development program that is influenced by several factors

such as the regulatory and legal framework, involvement of various stakeholders, high dependence

on socio economic factors, bureaucratic red tape and financial constraints. The management of

such programs requires consideration of these factors within the project/program planning

framework in order to achieve successful implementation.

4.0.2	A framework is necessary to define the design, planning, implementation and operations of rural

electrification projects. The framework identifies the involvement of stakeholders, identifying

responsibilities of all parties involved that may ultimately result in communities owning outcomes

4.1 Policy and Procedures for the Rural Electrification Program

4.1.1	The Rural Electrification Policy (REP) developed and approved by Cabinet in 1993 provides the

guidelines for electrifying rural areas2. Under the policy any rural village or settlement is entitled to

request government assistance for electrification.

4.1.2	Reviews of the 1973 Rural Electrification Policy in 1991 led to the development of the Rural

Electrification (RE) Policy 1993. The aims of the RE Policy 1993 was to:

a) electrify all rural villages within a period of approximately eleven years and number of villages

to be electrified each year to be at least 90;

b) have an annual programme of electrification for the above to be approximately $6million per

annum;

c) develop rural electrification primarily for social development but economic development to also

be promoted wherever possible;

d) examine all existing and new types of electrification in the various areas of Fiji to find out their

applicability;

e) grouping areas close to the FEA grid into schemes and electrify through the extension of the

grid;

f)	have consumers contributing 10% of the capital cost of installing an electrification project and

90% of the capital cost of the project to be met by Government;

2

Cabinet Decision No.121 of 23rd March 1993

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	9

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

g) develop a user-pay system in the long term, and to have villages to be fully responsible for the

maintenance, the repair and replacement cost of the electrification scheme after a grace period

of 3 years from the date of the completion of the project;

h) establish a Rural Electrification Unit to administer and control the rural electrification program;

and

i)	have Government subsidising house wiring for 3 villages to be connected to the Bukuya mini

hydro scheme, and to supply surplus electricity from this scheme to nearby villages.

4.1.3	Under the revised policy, the responsibility of planning and implementation of the Government rural

electrification programme was shifted from the PWD to DOE. Contribution required from the local

communities was reduced from 33% to 10% with Government being responsible for maintaining

the schemes only for the first 3 years from installation, and ownership of the schemes being

transferred to the local communities who would be responsible for the operations, maintenance

and replacement of the schemes.

4.1.4	The policy aims at streamlining the provision of electricity services into the rural areas. However

the methods of generation and supply of electricity have been expanded to include a wider range

to choose from. The electrification options available under the 1993 policy framework include:

(a) diesel scheme;

(b) distributed solar scheme;

(c) focal solar scheme;

(d) hydro scheme;

(e) connection to the FEA grid; and

(f) connection to a Government power supply system

4.1.5	The RE Policy 1993 also provides for the establishment of the Rural Electrification Unit (REU) as

well as guidance and instruction for the staff of the REU in facilitating the implementation of the RE

Policy.

4.1.6	Although the RE Policy 1993 has not been reviewed, certain clauses have been amended over the

years to progress the initiative such as the reduction of customers‟ contribution from 10% to 5% of

the total cost of the projects, and corresponding increase in Government‟s contribution from 90% to

95%.

Apart from the RE Policy, the DOE uses a Standard Operating Procedure (SOP) which provides

guideline to the REU officers. The Rural Electrification Unit Guidelines was developed in 2005 and

adopted from 2006 and incorporates the policies that govern rural electrification work and the

standard operational procedures required to be adhered to by all individuals and parties involved in

the implementation of the rural electrification project. The SOP was developed considering all the

existing standard procedures in Government‟s mechanisms that the RE Unit has to adhere to and

how best it can serve its customers. Other guideline includes directives from the Ministry and also

from the Department that include the use of Biofuels and the Minimum Energy Performance

Standards and Labelling.

4.1.7	According to the officer in charge there is a limitation to the policy and SOP in terms of achieving

its goal. The goal of DOE is to have 100% electrification of the Nation by 2016 with 100 projects

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	10

|  | Duties and Responsibilities |
| --- | --- |
| [a] | To administer the funds for rural electrification as allocated by the annual budget of the Government; |
| [b] | To fully inform prospective rural consumers of the opportunities for rural electrification which must include all costs and all benefits of each option |
| [c] | To receive and record applications by the rural consumers for their choice of rural electrification scheme; |
| [d] | To receive deposits for the capital works of rural electrification schemes; |
| [e] | To design, estimate, document and construct the electrification schemes as selected by rural consumers (refer [s] below); |
| [f] | To maintain records - operation, maintenance and accounts of rural electrification schemes; |
| [g] | To provide training for rural consumers to enable them to maintain and repair at the lowest possible cost rural electrification schemes; |
| [h] | To set up a maintenance and repair network throughout rural areas in Fiji; |
| [i] | To collect contributions from rural consumers for replacement of rural electrification schemes; |
| [j] | To manage, invest, disburse and account for funds received for the contributions stated in [i] above; |
| [k] | To arrange for replacements of rural electrification schemes; |
| [l] | To assess the resources and potential for certain types of rural electrification schemes (e.g. hydro, solar) in given areas of Fiji. |
| [m] | To design, construct, operate, maintain and repair without subsidy, electricity supply schemes including Government stations which are outside the areas of supply by the Fiji Electricity Authority; |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

being implemented each year. However, with the existing RE policy not being reviewed and the

program being customer driven, the target is somewhat difficult to achieve.

4.1.8	Although the policy and guidelines do not incorporate the current practices that have evolved since

their development, the framework provides sufficient guidance to the REU in implementing the rural

electrification program.

4.2 Implementing agency

4.2.1	The Rural Electrification Unit within the Ministry of Energy and Rural Electrification administers and

controls the rural electrification program3.

4.2.2	The Rural Electrification Unit was established in 1993 following Cabinet approval 121(4) of 23

March 1993 under the Ministry of Lands, Mineral Resources and Energy and is currently a unit

operating under the Department of Energy.

Although the Department of Energy was responsible for overseeing the implementation of the RE

policy from 1974 to 1993, the Public Works Department was responsible for the technical and

practical activities of the projects until 20054. The Department of Energy took over full responsibility

of the rural electrification project from the beginning of 2005.

4.2.3	In providing for the establishment of the Rural Electrification Unit, the RE Policy 1993 defined the

activities, duties and responsibilities of the Unit which are listed in Table 4.1 below.

Table 4.1: Activities, duties and responsibilities of the Rural Electrification Unit

Cabinet Decision 121(4) of 23rd March 1993

3

4 Department of Energy website

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	11

| [n] | To design and apply appropriate cost covering electricity tariffs at Government stations/load growth centres including the collection of monies received for the sale of electricity to consumers connected to schemes referred to in [m] above; |
| --- | --- |
| [o] | To develop and expand Government station electricity supply systems into load growth centres; |
| [p] | To promulgate information about the activities of the REU to all rural consumers, to advise them about any Government policies which may affect rural electrification and to respond positively to requests, comments and enquiries from rural consumers; |
| [q] | To comply with the requirements of the Electricity Act, Cap 180, and its Regulations; |
| [r] | To be solely accountable for all rural electrification activities to the Minister responsible for the Energy portfolio of the Government - this will include amongst other things, the submission of annual, accounting, audit and performance assessment reports; |
| [s] | To arrange for the execution of the duties of the REU by the most cost effective means either by its own staff or by means of private sector accountants, consultants, contractors or other such organizations. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.2.4	The policy also provides details for the following:

i.	Procedures to be followed by the REU and the villages/ settlements when making an

application for an electricity scheme;

ii.	Arrangements pertaining to local support activities, commissioning, and other requirements

for the construction of schemes [diesel generator and hydro-electric schemes, solar

lighting schemes, FEA schemes, and Centralised Generating Schemes].

iii.	Procedures to be followed by the REU and the villages/ settlements when operating their

electricity schemes;

iv.	Procedures to be followed by the REU and the villages/ settlements for the maintenance of

their electricity schemes;

v.	Procedures to be followed by the REU and the villages/ settlements for sustaining their

electricity schemes;

vi.	Procedures to be followed by the REU in responding to applications by

villages/settlements to extend their electricity schemes; and

vii.	Procedures to be followed when changing schemes to a continuous supply.

4.2.5	Audit noted that since the RE policy came into effect in 1993, technologies have changed and

advanced over the years thereby expanding DOE‟s responsibilities. However, no revisions have

been made to the RE policy 1993 to incorporate the additional duties and responsibilities.

4.2.6	The Unit‟s planning documents and individual work plans were not provided for audit. Thus audit

was unable to assess the effectiveness of the strategies implemented with the requirements of the

1993 policy.

4.2.7	The lack of review with regards to DOE duties and responsibilities may result in certain activities in

the DOE‟s planning documents not being aligned and consistent with the 1993 policy and which

may also be irrelevant.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	12

Grade [SHG]                             	Supervisors High

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.3 Human resources

4.3.1	The Rural Electrification Unit set up within the Ministry of Energy and Rural Electrification to

administer and control the electrification programme requires appropriately qualified persons5.

4.3.2	The revised RE Policy 1993 describes the proposed HR structure and requirements of the RE Unit.

Based on the assumption that the Unit would be established as a statutory body, specialised posts

were identified in the HR structure to enable efficient and effective management of the rural

electrification projects for the different schemes implemented in the various regions. The proposed

specialised positions included those of Manager of REU Regional managers – Vitilevu, Vitilevu-

West, Kadavu, Savusavu, Lau; Senior Project Engineer; Senior Engineer Electrical; Supervisor

Electrical; Technical Officer Electrical; Contracts Officer; Surveyor/ Estimator; Field Officers; and

Stores Officer.

However, audit noted that the proposed post and structure described in the revised policy has not

eventuated. Audit gathered from its interview with the officer in charge at DOE that the proposed

structure stated in the 1993 RE policy did not eventuate due to a lack of funding, thus the

continued existence of the Unit as a government department rather than a statutory body.

With more than 20 years existence, the current DOE structure poses a constraint in terms of it

adapting to changes or new innovations that have taken place in the energy sector both locally and

globally.

4.3.3	The REU as at to date is established as a government unit under the Department of Energy and is

therefore bound by General Orders and all the other relevant rules and regulations guided under

the PSC regulations in terms of its HR establishments. The current work structure is illustrated in

Figure 4.1 below.

Figure 4.1: Current organisation structure of DOE

Director DOE

Principle technical

officer

Supervisors High

Grade [SHG]

Technical Assistants

(6 posts)

Technical Assistants

(4 posts)

4.3.4	The REU is headed by the Principal Technical Officer (PTO) who oversees the overall operations

of the RE Unit.

5

Cabinet Decision No. 121 of 23rd March 1993

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	13

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

The Supervisor Higher Grade supervises the Technical Assistants [TAs] in their field work ensuring

that the works carried out are done in accordance with the required standards and procedures.

The Unit currently has two Supervisors High Grade of which one is responsible for all contracts,

and the other the implementation of projects.

Technical Assistants serve the rural customers and process applications for electricity supply. They

conduct field trips; ascertain scopes of work; design and estimate costs of schemes. The TAs also

provides technical and practical assistance to other sections of the Department.

4.3.5	From the documents provided audit noted that the supervisors and the technical assistant posts

were graded at the same level. Although OIC REU revealed that a tentative HR structure had been

drafted to improve the Unit‟s HR structure and assist in reducing the rate of staff turnover, the draft

tentative HR plan was not provided for audit scrutiny.

4.3.6	As per the person to post listing dated 31st July 2013, the REU currently employs a total of 13 staffs

from the approved staff establishment of 15. Of the two vacant posts, only one has been

advertised. Refer to table 4.2 below for details of staffing for REU.

Table 4.2: Current staffing of REU

Post	Number	of	Number

post	of  post

Post Title         Audit comments

approved

filled

officer (PTO)       	The post have been filled

(SLO)            	The post is vacant and not advertised

grade            	filled

SS05	1	0	Typist	The post have been temporarily filled

ST01	1	1	Principal	Technical

ST03	1	0	Technical	Officer

ES03	2	2	Supervisor	higher

ST05	10	9	Technical assistant	One post vacant and post has been

advertised

Total	15	13

4.3.7	Audit noted that most officers were recruited at the prevailing MQR at the time the post was filled.

Most appointments were based on the officers‟ years of practical experiences with relation to the

work required.

Audit gathered from its discussion with the team leader at the REU that although the current staffs

are able to carry out the work required they would need further training both locally and abroad to

develop their capacities.

4.3.8	Staff developments through appropriate trainings will enhance officers‟ skills that enable them to

carry out their work efficiently and effectively.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	14

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.4 Planning for Rural Electrification Projects

4.4.1	A plan in which the institutional, financial and technical aspects are covered is a precondition for

successful and sustainable rural electrification activity. A plan consisting of a well-coordinated

multiplicity of significant stakeholders from which all the financial and technical aspects are

incorporated would facilitate for an efficient and effective national plan consisting of the

identification of all the relevant resources that is required for the full implementation in the

government objective.

4.4.2	During the planning of RE projects to be undertaken, the total number of projects to be assisted

needs to be determined and a comparative analysis to determine the least cost of implementation

should be carried out.

4.4.3	The Department of Energy is responsible for the overall energy policy and planning, promoting the

development of renewable energy resources and renewable energy service companies

(RESCOS), energy conservation and the coordination of rural electrification activities through the

Rural Electrification Programme.

4.4.4	The rural electrification programme largely, provides a facility that enables rural communities to be

provided or assisted with the provision of electricity. The rural electrification program is drawn on a

yearly basis.

According to REU the programme drawn is based according to a prioritised list and not on a

planned list of a total number of communities that are yet to be electrified.

The prioritised list includes only villagers or communities that have fully paid their contribution to

the DOE. The programme is updated every year and submitted to the Ministry of Finance for

approval. Refer to the figure 4.2 below for the process involved in the approval of the RE

programmes.

Figure 4.2: Process of approving RE programme

DOE	-

prioritised	list

based on full

Payment

Budget

Strategic

Submitted to

MOF for

List

submitted

in the PSIP

to

planning

process

based on the

allocated

budget

Yes

Strategic

Planning

No

Pending application

awaiting

information

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	15

| Year | Amount ($) | Number of village/settlement assisted |
| --- | --- | --- |
| 1994 | 1,000,000 | 19 |
| 1995 | 1,000,000 | 35 |
| 1996 | 1,000,000 | 37 |
| 1997 | 1,000,000 | 31 |
| 1998 | 3,100,000 | 77 |
| 1999 | 3,280,000 | 135 |
| 2000 | 1,500,000 | 34 |
| 2001 | 3,000,000 | 86 |
| 2002 | 5,000,000 | 112 |
| 2003 | 6,000,000 | 140 |
| 2004 | 6,000,000 | 116 |
| 2005 | 6,000,000 | 101 |
| 2006 | 6,000,000 | 95 |
| 2007 | 6,000,000 | 129 |
| 2008 | 6,000,000 | 273 |
| 2009 | 7,000,000 | 654 |
| 2010 | 7,700,000 | 700 |
| 2011 | 3,700,000 | 144 |
| 2012 | 10,000,000 | In progress (~ 220) |
| 2013 | 8,500,000 | Data not provided to audit |
| TOTAL | 84, 280,000 | 3,138 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.4.5	The prioritised list is included in the PSIP submission to the Ministry of Strategic Planning. The

Ministry of Strategic Planning vets the submission to ensure that it is consistent and in line with the

national planning. Once approved by the MSNP it is submitted to the Ministry of Finance for

inclusion in the REU‟s budget.

4.4.1 Funding of REU programs

4.4.1.1 In envisaging the accomplishment of the electrification of the country within a span of 11 years,

Government allocates a budget of $6.0 million per year for the purpose.

However audit noted that actual funding over the years averaged at around $3 million per year.

Provided in Table 4.3 below is a summary of the budgetary allocation over the years from 1994 to

2013.

Table 4.3: Budget allocation for the years 1994 to 2013

Source: 2012-2014 Public Sector Investment Program REU Project Documentation

4.4.1.2 Furthermore DOE confirmed that allocated budget for 2013 was not fully utilised. Even though

projects had been committed, requests made to Ministry of Finance to enable payments were

unsuccessful as funds were not available. Thus outstanding payments for 2013 would be drawn

from the 2014 budget.

4.4.1.3 Inability to pay contractors in a timely manner instil vendor mistrust and contributes to deferment of

completion of projects, and the inability of the Unit in accomplishing its planned outputs.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	16

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

RECOMMENDATIONS

The Department of Energy should:

	review the 1993 Rural Electrification policy and the standard operating procedures to incorporate all current

practices not included in the existing documents. In its review, it should consider reviewing clauses pertaining to

its duties and responsibilities to accommodate the changes in technology that have arisen over time and the

additional activities/responsibilities required to address such changes.

	review the staff structure at the REU that identifies career paths for its officers and promotes staff retention;

	identify the training needs of its staff and send them to appropriate trainings that will enhance their knowledge

and skills; and

	ensure that it utilises funding‟s provided to it in the year appropriated so that it does not impinge on the following

year‟s budget and adversely impact the anticipated activities budgeted for.

Management Comments

No management comments received.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	17

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.0 ADMINISTRATION	AND

IMPLEMENTATION	OF	RURAL

ELECTRIFICATION PROGRAM

This section of the report looks into the efficiency of administering and implementing rural

electrification program. This includes a scrutiny of the administrative processes and the

implementation of the projects identified in accordance with planned requirements.

5.0.1	The Rural Electrification Unit (REU) is responsible for Schemes powered by stand-alone diesel

generators, and FEA Schemes whereby electricity supply is obtained from the Authority‟s national

grid. It also administers the Solar Home Systems (SHS) scheme which is aimed at providing

affordable electricity services to very remote communities that are unlikely to have access to the

national grid and also where fuel supply is limited.

5.0.2	Good coordination, understanding and collaboration amongst stakeholders are important as they

ensure that commissioned projects meet the needs of customers and are also within the minimum

safety standards and regulations of the Fiji Electricity Authority (FEA).

5.1 Rural Electrification applications

5.1.1	Application for assistance to the programme can be made through the standard application

available at the Department which is also disseminated to the 14 provincial and district offices

around the country.6

5.1.2	Interested rural villages, communities and households requiring rural electrification assistance

under the RE programme submit their application to the REU using the appropriate form.

Application forms are available at the various provincial and district offices around the country as

well as on the Department‟s website.

The 1993 Policy offers 3 types of rural electrification schemes which are as follows:

1) a diesel generator with mini-grid system for evening lights and small electrical appliances;

2) renewable energy systems: solar photovoltaic (PV) or small hydro for evening lights; and

3) extension of the FEA grid or government station mini-grid to provide 24 hours per day

service.

The electrification schemes are classified as either major or minor schemes. The major scheme

involves the extension of grids located more than 300 meters from the nearest FEA low voltage

using transformers. Minor schemes include diesel and solar schemes, and extensions to FEA low

voltage line which are located 300 meters from site of installation.

6 REU Guidelines Policy Summary & Standard Operational Procedures- Section 5.0 (a) (A) paragraph 1 page 11

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	18

| Steps | Description |
| --- | --- |
| 1. DOE-receives application | Applications forms for assistance to the programme are disseminated to the 14 provincial and district offices. Applicants are required to fill and submit the form to either of the two DOE offices in Suva or Labasa. |
| 2. Survey, Scheme Estimated cost | Once the application is received by DOE, the DOE officers would then carry out their survey to confirm the most suitable type of scheme and make estimation on the total cost for the project. |
| 3. Inform Community on Contribution | After the cost of the project is identified, the households are informed on their 5% contribution that should be made to the DOE. |
| 4. DOE receives the full contribution | Once the full contribution is received by DOE. The application is confirmed and is added into the list to be supported under the scheme in the next year‟s budget. |
| 5. DOE Tender Process | Once the list is approved by cabinet to be supported. The government tender process is followed. |
| 6. Approve of tender by FPO | FPO does the evaluation and DOE provides the recommendation on the contractor. Contract is signed by DOE and the contractor. |
| 7. Commencement of REP | The RE project is implemented as per the contract and DOE tender specification. |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.1.3	The DOE receives and records applications for rural electrification schemes from interested

applicants. Illustrated in Figure 5.1 below is the process followed when receiving applications.

Figure 5.1: Application Process for a REP scheme

Yes

Hand

delivered

application

Checking of

application

form      by

registry clerk

Application

received

No

Posted

application

Application

is recorded in

Applications

documents

are filed

Pending application

awaiting

information

the database

under the

filing index

system

The application process above is further described in table 5.1 below.

Table 5.1: Description of REP application process

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	19

| Requirements for FEA diesel and Grid extension | Requirements for Solar scheme |
| --- | --- |
|  FEA form filled  Copy Of Title/TNK Letter  Tin Letter  Birth Certificate  Passport Size Photo |  Copy Of Title/TNK Letter  Tin Letter  Birth Certificate  Passport Size Photo |

| Applicants name | Documents not submitted |
| --- | --- |
| Rafaele Naqiomila | TNK letter/stamp, birth certificate, sketch for home location. |
| Filisi Limau | TNK letter/stamp, birth certificate, sketch for home location. |
| Marisila Waqali | TNK letter/stamp, birth certificate, sketch for home location. |
| Alesi Bulivou | No photo, TIN letter, birth certificate |
| Teresia Lewasewa | No sketch of residence location |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.1.4	Applicants are also required to submit evidences of required documents to support their

applications. Documents required to be attached to applications are listed in table 5.2 below.

Table 5.2: Documents required supporting applications

5.1.5  	However, audit verifications of sample applications received noted that some applications did not

have all the required supporting documents such as copies of Title/TNK Letter or birth certificate. In

addition, sketches describing location or address of applicant were also not provided. Refer table

5.3 below for examples.

Table 5.3: Applications without supporting documents

5.1.6	In addition audit noted that REU officers during their inspection found details provided in the

application form that did not correspond with the situation.

5.1.7	The lack of documentation provided or the inaccuracy of details provided in the application forms

imply an obvious weakness in the vetting process and the recording system which also has

impacts on the Unit‟s resources such as time and money.

5.2 Diesel generator scheme

5.2.1 Diesel scheme arrangements

5.2.1.1 Diesel generator is a single device that functionally converts diesel fuel into electricity.

Requirements for installation of diesel schemes include the following major equipment items7:

	Generator house

1. Wooden structured power house

2. Diesel engine driven generator, 240V 1-phase or 415V 3-phase 50 Hz, with starting system,

fuel system and steel base frame;

3. Underground cable distribution incorporating ground level distribution pillars and underground

service cables to buildings.

7 REU Policy 1993 Part B Chapter 1 Sheet 1: Information sheet diesel generator scheme s.1.0: Scope of equipment

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	20

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	House wirings

4. For each individual house, a wiring installation includes;

i.	2 - 18W (2 ft.) fluorescent lights,

ii.	(II) 1-10A power point and

iii.	(III) A meter box with main switch and circuit fuses.

5. For one community hall, a wiring installation including appropriate lighting, 1-10A power point

and a meter box with main switch and circuit fuses.

6. One 200 litre drums of diesel fuel to commission the diesel generator.

These generator systems are also required to be housed in a well-ventilated and shady area.

5.2.1.2 Audit noted during its site inspection that the generator schemes installed had the basic equipment

required which complied with the above requirements. Equipment‟s were also provided with

adequate shelter. Refer to Appendix 1 for illustrations of generators sighted during the site surveys.

5.2.1.3 Compliance with equipment requirements and maintenance promotes longevity of equipment.

5.2.2 Utilisation of diesel schemes

5.2.2.1 New applicants requesting for assistance under the Rural Electrification Policy 1993, and villages/

communities assisted under the program prior to 1993 can opt for electrification through the

following means:

	an upgrade with the existing diesel scheme or

	renewal energy or

	the grid extension

Applicants can only be assisted once

5.2.2.2 According to DOE, diesel generators were once the preferred source of generating electricity in

past years8 for rural villages because of its cheap price. However the prevailing high costs of fossil

fuel costs have impacted much on rural communities using diesel generator operated schemes.

With most of the rural electrification project sites situated in the outer islands and the interiors of

Viti Levu and Vanua Levu, rural communities not only have to pay for the expensive diesel fuel but

also for the transportation costs of carting the diesel fuel from the urban centres to their villages.

Some remote interior villages have to use various modes of transportation just to transport fuel,

that is, by foot, horseback, boat, and/or vehicle to their villages, thus purchasing fuel is quite an

expensive exercise for such communities.

5.2.2.3 From discussions with Turaga ni Koro of villages assisted with diesel generator schemes, audit

noted that not all villages fully utilise their diesel generator system. It was revealed that villages

8 From 1974 to the late 1990s

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	21

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

would operate their generators for only two to three hours a day or only on special community

occasions or village functions. This is mainly attributed to the high costs of fuel.

5.2.2.4 Apart from environmental considerations, Government is promoting the use of renewable energy to

reduce the nation‟s reliance on diesel and other carbon based fuels that are imported.

5.2.2.5 The DOE is currently converting existing diesel generators to run on biofuels or pure coconut oil.

Discussions with DOE revealed that installations of generators with dual oil filters where both diesel

and bio fuel can be used have been installed in villages on outlying islands. Listed in table 5.4

below are 7 villages operating bio fuel generators.

Table 5.4: Villages installed with bio fuel generators

Cooperative Ltd      	Prime Minister

Com Frank Bainimarama      	10/03/2010

Company Ltd       	HE the President

Ratu Epeli Nailatikau        	14/05/2011

Com Frank Bainimarama      	08/09/11

Ltd              	Prime Minister

Com Frank Bainimarama      	16/03/13

Ltd              	Minister for Works

Col. Timoci L. Natuva        	14/08/13

Company Ltd       	Minister for Works

Col. Timoci L. Natuva        	15/08/13

Company Ltd       	Minister for Works

Col. Timoci L. Natuva        	16/08/13

Biofuel Mill	Commissioned By	Date

commissioned

Koro Biofuel

Rotuma Biofuel

Cicia Biofuel Ltd	Prime Minister

Gau Biofuel Company

Rabi Biofuel Company

Vanuabalavu Biofuel

Lakeba Biofuel

Comments

In Operation

In Operation

In Operation

Await Start-Up Capital

Await Start-Up Capital

Await Start-Up Capital

Await Start-Up Capital

5.2.2.6 Since under the current revised policy villages and/or communities are not permitted to request for

an upgrade to other alternative scheme, some villages would not be able to fully utilise their

schemes because of the high cost of fuel thus defeating the objective of the government initiative.

5.3 Solar Scheme

5.3.1	Solar radiation can be used to generate electricity either through photovoltaic (PV) or thermal

technology. The Government through DOE utilizes PV systems technology under the Solar Home

Lighting Systems (SHS) project for providing electricity to rural areas in Fiji.

5.3.2	The Solar PV systems convert sunlight directly into electricity using solar cells. The size of the

solar system and available sunlight determines how much electricity is available for use.

The typical solar home system consists of a panel, a collection of solar cells where the more light

that hits a cell, the more electricity it produces, a battery for storing the energy generated during

the day, a battery charge controller to avoid excessive charging and discharging and fluorescent

lights. Refer to figure 5.2 for Components of a PV solar home system.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	22

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Figure 5.2: Components of a PV solar home system

The following paragraphs discusses observations noted in the solar scheme

5.3.1 Installation of equipment

5.3.1.1 Under the 1993 RE policy the solar scheme should include the following major equipment items for

each individual household:

a] Solar panels installed on a wooden pole with adjustable tilt brackets

b] Two 11W and one 7W fluorescent lights

c] One 12V lead acid battery

d] One battery controller

5.3.1.2 From site visits conducted, audit noted that selected items currently installed varied from

equipment requirements described in the 1993 RE policy. Refer to table 5.5 for variations noted.

Table 5.5: Variations between equipment requirements as per the policy and actual verification

Audit comments	Items required under the 1993

Actual items installed

policy

Verified correct	 solar photovoltaic panel	 1 x 135 Wp solar photovoltaic panel

Verified correct	 1 12V lead acid battery	 1 x 100 Ah deep cycle battery

Verified correct	 1 battery controller		1 x 10 Amps 12 VDC controller/regulator

Not specified in the 1993 RE

policy

Not specified in the 1993 RE

no                     1 x 12 VDC voltage reducer

no                     1 x .5 Watt LED light with switch

policy

Verified correct	 1 x 7 watt light with switch	 1 x 7 watt light with switch

1	additional	from	what

specified in the 1993 RE

2 x 11 watt lights each with

switch

3 x 11 watt lights each with switch

policy

Verified correct	 House wiring	 House wiring

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	23

| 1 x Wp solar photovoltaic panel | 1 x 100 Ah deep cycle battery |
| --- | --- |
| 1x10 amps 12 VDC controller/regulator | 3 x 11 watt lights each with switch |
| 1 x .5 Watt LED light with switch | 1 x 7 watt light with switch |
| 1 x 12 VDC voltage reducer | House wiring |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.3.1.3 Discussions with the officer in charge at DOE confirmed that the Department has been

installing such equipment since 2005 and not as per the requirements of the 1993 RE policy.

Illustrated in figure 5.3 below are the equipment items installed as sighted during the audit inspection.

Figure 5.3: Equipment currently installed

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	24

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.3.1.4 Audit could not ascertain whether variations in equipment requirements as per the Policy and those

installed from 2005 are authorised since endorsements for variations were not provided for audit

verification.

5.3.2. Installation arrangements – Renewable Energy Service Company (RESCO)

5.3.2.1 Under the solar based rural electrification scheme, equipment is owned by Government, but is

installed and maintained by a private company selected through competitive tendering.

5.3.2.2 According to DOE, remote villages and settlements that cannot be connected to the FEA grid and

houses that are located further apart are given the option for solar home lighting system (SHS).

The arrangements under the solar scheme are illustrated in Fig. 5.4 below.

Figure 5.4: Arrangements for solar scheme

(Source; Dornan, M., 2011, Solar-based rural electrification policy design: The Renewable Energy Service Company (RESCO) model in Fiji,

Renewable Energy, 36, 797-803 )

5.3.2.3 The aim of the scheme is to remove the high upfront capital costs associated with solar

technologies and encourages public private sector partnership for maintenance.

5.3.2.4 Each user pre-pays a monthly fee that covers the maintenance and component replacement as

well as the initial capital cost.

Audit noted that a household pays an initial deposit of $50, thereafter „renting‟ the SHS for a

monthly fee of $14, which is paid at the local post office in return for a token that must be entered

into the SHS prepayment meter. This amount is supposed to cover all maintenance costs and 5

percent of the capital cost of SHS, consistent with Fiji‟s Rural Electrification Policy.

The Department then pays the RESCO approximately $10 per month for each household under its

maintenance contract. Payments to the RESCO are made every two months, during which time the

RESCO is expected to visit every household with an SHS once.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	25

| System Type | Period of payment | Amounts per unit | Details |
| --- | --- | --- | --- |
| Type 1 (100 Wp) | Pre-installation | $70.00 | Advance 5 months‟ rent |
|  |  | $84.00 | Refundable security deposit |
|  | Post-installation | $84.00 | Rent to be paid at the beginning of every six months period. First payment due at the end of the first six months from installation date. |
| Type 2 (270 Wp) | Pre-installation | $90.00 | Advance 5 months‟ rent |
|  |  | $68.00 | Refundable security deposit |
|  | Post-installation | $108.00 | Rent to be paid at the beginning of every six months period. First payment due at the end of the first six months from installation date. |

| Funding | Quantity | Capacity per system | Target area | Rental Fees per month | Progress |
| --- | --- | --- | --- | --- | --- |
| Government of Fiji Rural Electrification (Type 1) | 2000 | 100 Wp | Viti Levu and Vanua Levu | $14 | Installation of first batch of 1000 ongoing April – Sept. |
| Pacific Environment Community Fund (Type 2) | 1000 | 270 Wp | Maritime zones (excl. Taveuni and Rotuma) | $18 | Supply of equipment ongoing April - August |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.3.2.5 In addition to the RESCO model, the REU has come up with a new billing and rent payment

structure that was implemented for the new installations made from 2012 onwards. Refer to table

5.6 below for the billing structure extracted from DOE solar system awareness paper.

Table 5.6: Billing and rent payment structure

5.3.2.6 From 2012, the Department of Energy has been implementing two types of SHS as described in

table 5.7 below:

Table 5.7: Types of SHS

5.3.2.7  Scrutiny of documents revealed that the upfront cost of installing each system per household

varied from $2742.67 in 2008, then increased in 2009 to $2944.47 and decreased again to $2700

in 2012 to 2013. Refer to Appendix 2 for details of cost of solar system installations per household.

Reasons for variations in the costs were not provided to audit.

5.3.2.8 Villages/ communities having solar systems are required to pay $14 each month to assist with

funding of maintenance of equipment. However, audit noted that the villagers/ communities have

stopped paying their $14 monthly subscription due to the prepayments machine not working and

certain equipment gone bad and have not been replaced.

5.3.2.9 Without the monthly rentals payments the government would not be able to sustain the projects.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	26

| Village/settlement | No of Houses | Amount Paid | Amount Paid per household | Amount paid per household in excess of $4,000 | Total excess paid per village / community ($) |
| --- | --- | --- | --- | --- | --- |
|  |  | ($) | ($) |  |  |
| 2009 |  |  |  |  |  |
| Bangladesh Settlement | 8 | 32,932.00 | 4,116.50 | 116.50 | 932.00 |
| Qelemumu Primary School | 172 | 710,865.00 | 4,132.94 | 132.94 | 22,865.00 |
| Daku Settlement | 24 | 126,758.00 | 5,281.58 | 1,281.58 | 30,758.00 |
| Vunika Settlement | 235 | 1,348,514.00 | 5,738.36 | 1,738.36 | 408,514.00 |
| Nuknuk/Tabia | 4 | 21,397.00 | 5,349.25 | 1,349.25 | 5,397.00 |
| Maravu/Benau Settlement | 2 | 12,051.00 | 6,025.50 | 2,025.50 | 4,051.00 |
| Vatulele Village | 4 | 21,997.10 | 5,499.28 | 1,499.28 | 5,997.10 |
| Laselevu Junction To Nadovu & Others - Stg3&4 | 1 | 11,978.00 | 11,978.00 | 7,978.00 | 7,978.00 |
| Laselevu Junction To Matainasau Village - Stg1 | 17 | 246,079.00 | 14,475.24 | 10,475.24 | 178,079.00 |
| 2012 |  |  |  |  |  |
| Beleki Settlement - Vitogo | 5 | 21,231.00 | 4,246.20 | 246.20 | 1,231.00 |
| Matanisiga Settlement | 2 | 8,908.00 | 4,454.00 | 454.00 | 908.00 |
| Gaunavou Settlement - Naduri | 2 | 9,218.00 | 4,609.00 | 609.00 | 1,218.00 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.4 Community Contribution

5.4.1	Once the survey has been completed, the community is informed of the contribution that they have

to pay. Upon payment of the contribution the scheme is placed on the Department‟s priority list in

terms of actual construction or assistance to the scheme.9

5.4.2	In order to maintain fairness, consistency, and also ensure that the rural electrification funds are

put to optimum utilization, a ceiling or maximum allocation of $4000 per customer is being used as

a guideline for those aspiring to be supplied with electricity from the FEA power lines. Schemes

having total costs below the maximum allocation of $4000 / customer are considered viable and

customers are required to pay 5% of the total costs with Government funding the remaining 95%.

Schemes having total costs above the maximum allocation of $4000 per customer require

communities to pay the difference whilst the Government would provide the maximum assistance

of $4000 per customer.10

5.4.3	During its verifications, audit could not establish whether customers assisted under schemes

costing more than the maximum allocation had paid the differences in costs as required under the

policy since no records reflecting these were provided for scrutiny. Reflected in table 5.8 below are

examples of customers assisted under the schemes costing more than $4,000 for which

repayments could not be established.

Table 5.8: Customers assisted under the schemes costing more than $4,000

9 REU Guidelines Policy Summary & Standard Operational Procedures- Section 5.0 (a) (A) paragraph 3 page 12

10 REU Guidelines Policy summary & Standard Operational Procedures- Section 2.2 (c) paragraph 3 page 7

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	27

| Nakasa Village And Settlement | 80 | 389,360.00 | 4,867.00 | 867.00 | 69,360.00 |
| --- | --- | --- | --- | --- | --- |
| Navisudina Settlement, Savu, | 1 | 8,275.00 | 8,275.00 | 4,275.00 | 4,275.00 |
| Draladamu Settlement | 4 | 42,279.00 | 10,569.75 | 6,569.75 | 26,279.00 |
| Beleki Settlement - Vitogo | 5 | 21,231.00 | 4,246.20 | 246.20 | 1,231.00 |
| Vatukacevaceva | 92 | 387,876.00 | 4,216.04 | 216.04 | 19,876.00 |
| Koroua | 18 | 81,774.00 | 4,543.00 | 543.00 | 9,774.00 |
| Nakasa Village and Settlements | 80 | 455,940.00 | 5,699.25 | 1,699.25 | 135,940.00 |
| Yawe District School | 10 | 79,130.00 | 7,913.00 | 3,913.00 | 39,130.00 |
| Vuna District School | 12 | 97,800.00 | 8,150.00 | 4,150.00 | 49,800.00 |
| Lumiboso | 13 | 112,095.00 | 8,622.69 | 4,622.69 | 60,095.00 |
| 2013 |  |  |  |  |  |
| Balevuto Settlement, Ba | 9 | 37765 | 4,196.11 | 196.11 | 1,765.00 |
| Jaina Settlement, Tokaimalo, Ra | 13 | 55131.95 | 4,240.92 | 240.92 | 3,131.95 |
| Vuci Irrigation Road, Nausori,Tailevu | 4 | 17355 | 4,338.75 | 338.75 | 1,355.00 |
| Qelewaqa Settlement, Macuata | 11 | 49710.8 | 4,519.16 | 519.16 | 5,710.80 |
| Wairiki Catholic Mission | 34 | 165780 | 4,875.88 | 875.88 | 29,780.00 |
| Natawatawadi Village, Navosa | 21 | 115185 | 5,485.00 | 1,485.00 | 31,185.00 |
| Naloto Settlement, Verata, Tailevu | 4 | 24160 | 6,040.00 | 2,040.00 | 8,160.00 |
| Logavatu Nasau, Mokani, Tailevu | 1 | 6241 | 6,241.00 | 2,241.00 | 2,241.00 |
| Nawaqabena Village, Naitasiri | 35 | 221809 | 6,337.40 | 2,337.40 | 81,809.00 |
| Chandra Wati, Votualevu, Nadi, Ba | 1 | 7065 | 7,065.00 | 3,065.00 | 3,065.00 |
| Calia, Navua, Namosi | 4 | 31476.6 | 7,869.15 | 3,869.15 | 15,476.60 |
| Viani Primary school | 6 | 78392.25 | 13,065.38 | 9,065.38 | 54,392.25 |
| Total | 934 | 5,057,759.70 | 217,281.52 | 81,281.52 | 1,321,759.70 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.4.4	As indicated by the table above, amounts exceeding approved maximum allocation for the above

schemes which have to be repaid by customers totalled $1,321,759.70. The amount if not

reimbursed would incur an unauthorised additional cost to Government.

5.4.5	Sum over-expended has impinged on the authorised budget and could have been utilised for

implementation of other schemes.

5.5 Records maintenance

5.5.1	As part of the Unit‟s filing system, a comprehensive filing index has been created to cater for each

of the scheme. The filing system is intended to contain all information for anyone scheme. Any

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	28

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

written material addressed to the files is to be stored in the relevant files no more than 3 days since

being despatched from the respective officer11.

5.5.2	The most efficient and economical filing system is one that works well for the office and is easily

understood by its users. When establishing a filing system factors to be considered include the

ready identification and retrieval of individual records and files; and the segregation and security of

information requiring special protection.

5.5.1 Filing arrangements

5.5.1.1 The REU file records are arranged by subject. For examples refer the following:

	Contract document files

	Applicants Cannot be Assisted through REP

	Western division surveyed and paid

	Western division surveyed not yet paid

	Central division surveyed and paid

	Central division surveyed and not yet paid

	Central division paid not surveyed

5.5.1.2 Audit noted that the subject files maintained do not provide an adequate audit trail. For example,

contract document files provided for audit verification only contained contract agreements and did

not contain evaluations for successful tenderers, considering that the tenders were of significant

amounts. Audit was not able to ascertain the basis of decisions on the awarding of tenders to

Powerlite Generators Fiji Limited for the supply and installation of solar systems in 2012 for 1,693

houses worth $5,491,500, and in 2013 for 1,233 houses worth $3,638,500. The lack of audit trail

hindered audit verifications.

5.5.1.3 It was also observed that there was no security over files maintained and that they were accessible

to all persons entering the REU section. A scrutiny of the subject files maintained revealed some

subject files did not contain all relevant documents.

5.5.1.4 The current lack of security over records maintained poses a risk over records being manipulated

or getting lost.

5.5.2 Data recording

5.5.2.1 Currently the REU does not maintain a database as required under the SOP but maintains records

of projects in an excel spread sheet. However, items in the spreadsheet are not recorded in a

systematic manner and do not contain all the information pertaining to a project such as contractual

amount, the individual contractors that were awarded the various works required under a project,

detail of total cost identifying the community‟s contribution and governments contribution. Refer to

Appendix 3 for illustration of fields not filled for entries in the Excel spread sheet maintained.

11 REU Guidelines Policy Summary & Standard Operational Procedures- Section 5.0 B paragraph 1 page 12

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	29

| Year | FEA- connected scheme | Diesel Scheme | Solar Scheme | Hydro Scheme | Government Station Extension | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1994 | 5 | 9 | 4 | 1 | 0 | 19 |
| 1995 | 10 | 20 | 4 | 1 | 0 | 35 |
| 1996 | 17 | 17 | 3 | 0 | 0 | 37 |
| 1997 | 16 | 12 | 1 | 0 | 2 | 31 |
| 1998 | 38 | 39 | 0 | 0 | 0 | 77 |
| 1999 | 56 | 75 | 1 | 3 | 0 | 135 |
| 2000 | 19 | 14 | 1 | 0 | 0 | 34 |
| 2001 | 52 | 33 | 0 | 1 | 0 | 86 |
| 2002 | 52 | 58 | 2 | 0 | 0 | 112 |
| 2003 | 60 | 79 | 0 | 0 | 1 | 140 |
| 2004 | 68 | 42 | 6 | 0 | 0 | 116 |
| 2005 | 80 | 11 | 10 | 0 | 0 | 101 |
| 2006 | 55 | 30 | 8 | 0 | 2 | 95 |
| 2007 | 96 | 33 | 0 | 0 | 0 | 129 |
| 2008 | 251 | 15 | 7 | 0 | 0 | 273 |
| 2009 | 495 | 15 | 142 | 0 | 2 | 654 |
| 2010 | 117 | 10 | 402 | 1 | 0 | 530 |
| TOTAL | 1,487 | 512 | 591 | 7 | 7 | 2,604 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.5.2.2 A total of 2,604 schemes have been implemented since the inception of the policy in 1994 to 2010.

A breakdown of number of schemes implemented from 1994 to 2010 is outlined in table 5.9 below.

Table 5.9: Number of schemes implemented from 1994 to 2010

Source: 2012-2014 Public Sector Investment Program REU Project Documentation

The Unit however was unable to provide audit with data for the years 2011 to 2013 due to

misplacement of records, indicating a nonchalant attitude towards record keeping and its

significance. Thus, audit was not able to establish the number of schemes implemented for the

years 2011 to 2013.

5.5.2.3 Audit understood from discussions held with the OIC REU that a submission was made by the

REU for the purchase of a database but which was withdrawn. The GTB did not approve the tender

as the Information Technology and Computing (ITC) Services was not consulted on the intended

purchase. No further information was given to audit on the status of the process on acquiring the

Unit‟s database.

5.5.2.4 The use of a database as a records management tool would benefit the Unit as it maintains high

volumes of records which contain significant information that not only convey how public funds are

expended but also funds that need to be recovered back by government. It also allows for ease of

access to information required.

5.5.2.5 In addition incomplete data provided limits sufficiency of information available to decision makers to

make well informed decisions.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	30

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.6 Public Awareness Activities

5.6.1	The DOE should conduct public information and outreach awareness by public education and

awareness campaigns and upload the requirements and guidelines on the DOE website.

5.6.2	Audit noted that the public information and outreach by REU is inadequate. The only information

DOE has is placed on its website. The villagers/individuals interviewed during the inspection of

REP projects revealed that they were not aware of DOEs Rural Electrification Projects.

5.6.3	Inadequate awareness campaigns on rural electrification activities leave an information gap which

hinders the rural population from taking on the program initiatives.

5.7 Completion of projects

5.7.1	The overall objective of the Rural Electrification Policy 1993 is to provide electricity primarily for

social benefit to all rural residents in Fiji12. It is the intention of government that social benefit of

electricity shall be made available to all rural areas in the shortest time possible. This means that

social benefit of electricity is provided to as many villages and settlements as possible within the

bounds of funds allocated annually by government or aid.13

5.7.2	Audit verifications for projects completed from 2010 to 2013 revealed the following discrepancies:

 there was no list of applicants for the number of houses in the scheme; and

 signed copies of contracts between the DOE and contractors were not in the file. Files only

had unsigned copies.

Attached as Appendix 4 is a list of projects completed without signed contracts or other necessary

documentation as described above.

5.7.3	Explanations provided to audit clarified that former clerks did not maintain the files properly and

records may have gone missing when the Unit was relocating from Nasilivata House to

Government Supplies Yard, Walu Bay.

5.7.4	Audit also noted that amendments to amounts quoted on the signed contracts were not endorsed.

For example, the amount quoted in the contract for the rural electrification of 100 houses for Viria

Village & Settlement in Tailevu of $21,338.19 was crossed off and altered to $106,703.91 and

amendment attributed to “typing error”.

5.7.5	Contracts are documents which once signed are legally binding. Alterations require appropriate

approval.

12 REU Policy 1993 Part A Chapter 2 s.2 paragraph 1

13 REU Policy 1993 Part A Chapter 2 explanatory notes on principles of the policy item 7

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	31

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

RECOMMENDATIONS

The Department of Energy should:

	be more vigilant in its vetting process when receiving applications to ensure that forms are complete in all

respect and that all supporting documents are provided so that applicants are not deprived of receiving

assistance;

	in its review of the RE Policy as recommended under Section 4.0 of the report consider incorporating options

that are viable for rural communities, in view of prevailing or rising costs of fuel;

	ensure that documents sanctioning any changes to requirements of the RE Policy is maintained for evidentiary

audit purposes. The RE Policy needs to be reviewed to incorporate changes with respect to equipment

requirements currently installed;

	ensure that all appropriate maintenance is carried out and prepayment machines replaced if necessary. Follow

up with communities that are not paying their monthly installments should also be carried out;

	ensure that requirements of the policy are adhered to and recoup sums over-expended from customers. In

addition the Accounts Department needs to be proactive in its functions to ensure timely recovery of monies

owed to government over the past 5 years from customers, or imposing surcharge actions against officers

responsible for the incurrence of unauthorised expenditure and the delayed recovery of dues;

	take stock of the Unit‟s files and maintain records to keep track of file movements to minimize misplacement of

files. The Unit should also pursue the purchase of a data base for its records management purposes;

	strengthen its awareness creation activities; and

	maintain contract files properly. All the signed copies of the contract should be filed properly and kept in a

secure place. Each contract should be complete with all the proper documents attached to it such as sketches,

number of applicants and tender specifications.

Management Comments

No management comments received.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	32

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.0	MONITORING AND INSPECTION OF

PROJECTS UNDER THE REP

This section of the report discusses the effectiveness of the REU in monitoring rural

electrification projects and looks into whether projects implemented are monitored and

reported accordingly by the REU.

6.0.1	Monitoring of rural electrification projects is conducted via inspections to the sites where REU

projects are installed. Inspections are conducted during installations of projects as well as

progressively.

6.0.2	Monitoring and evaluation of projects is a means of generating information necessary for making

project improvements throughout its life. It allows the identification of key areas requiring

management‟s attention for improvement.

6.1 Monitoring during installation

6.1.1	There are times when projects will have to be inspected progressively or at various stages of the

work. Officers will have to identify that the right quantum of work specified in the contract is

satisfactorily done before vouching that a percentage of the job is complete, and that the

appropriate payment as per the contract.14

6.1.2	Inspections are done at the following stages of the projects, that is, at 70%, 95% and when the

project is completed. Projects that cost substantial amount are inspected at every stage.

6.1.3	Inspection reports are prepared by officers summarising what they have inspected and what their

recommendations are. The inspection reports are then passed onto Supervisor High Grade and

after their assessment it is passed for comments to the Principal Technical Officer (PTO).

6.1.4	From inspection reports scrutinised audit noted instances where inspection reports issued

contradicted inspection reports submitted for prior inspections. For example, the respective reports

of 3 inspections carried out In Keiyasi & Natawatawadi contradicted each other as follows:

	1st inspection-recommended brands were used as specified in the contract.

	2nd inspection-the inspection report showed unspecified brands were used.

	3rd inspection-was not necessary but was carried out to address the contradicting reports.

6.1.5	The above indicates a lack of guideline to assist the inspectors and provide uniformity of work

approaches and requirements.

14 REU Guidelines Policy Summary & Standard Operational Procedures- Section 5.0 (b) (D) Page 23 paragraph 3 & 4

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	33

| Percentage of work completed | Percentage Paid to Contractor (%) |
| --- | --- |
| Award of contract | 20 |
| Completion of 70% of work | 50 |
| Completion of 30% of remaining work | 10 |
| Tender Specification and Contract Compliance | 10 |
| Retention Component | 10 |
| Total | 100 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.2 Inspection of Projects

6.2.1	Progressive inspection requires REU officers to be familiar with the terms and conditions set out in

the contractual agreements that exist between the Department and the outside company or

contractor in relation to the particular job being inspected.15

6.2.2	Audit noted that the quarterly progress reports from 2010 to 2013 (2nd Quarter) were analysed by

the Unit. Although budgets are provided annually, projects are not always completed in the current

year and are carried forward to the following year.

6.2.3	Previously, advance payments were made to contractors for works to be done prior to any actual

work carried out. Reflected in Table 6.1 is the composition of contractual payments at each stage

of the contract works carried out.

Table 6.1: Composition of payments at each stage of the contract

Under this arrangement, there was a risk that Department would lose the advance payments made

should the contractor wind up or closed down business before any work was actually done

6.2.4	So upon the establishment of the Fiji Procurement Office (FPO), the composition of contract

payments were amended as described in table 6.2 below.

Table 6.2: FPO required composition of payments at each stage

Percentage of work completed (Stages)	Percentage Paid to Contractor

(%)

Completion of 20% of work	20

Completion of 70% of work	50

Completion of 30% of remaining work	10

Tender Specification and Contract Compliance	10

Retention Component	10

Total	100

6.2.5	The current payment schedule now addresses the risks associated with advance payment and

contractor absconding as payments are only made if the work is done in accordance with the terms

of the contract agreement.

15 REU Guidelines Policy summary & standard operational procedures section 5.0 (b) (D) Page 23 paragraph 3

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	34

Expenditure	Actual

Expenditure	Savings

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.3 Monitoring resources

6.3.1	Adequate level of resources should be in place to effectively monitor REU related activities.

6.3.2	Audit noted that the current level of staffs is not adequate to effectively monitor the REP even

despite the merging of the Renewable Energy section with the Rural Electrification Unit.

6.3.3	The REU also does not have a vehicle exclusively for its use but uses the department‟s vehicle.

For inspections in inland terrain, vehicle is requested from the Ministry as the Department does not

have a vehicle that can travel through rugged terrains.

6.3.4	Furthermore audit noted that the amount budgeted for the REU section for the years 2008 to 2012

were not fully utilized. Details of saving are listed in table 6.3 below.

Table 6.3: Savings for years 2008 to 2012

Year	Budgeted

2008	6,000,000	5,337,239	662,761

2009	18,887,719	18,769,063	118,657

2010	5,892,405	5,723,004	169,400

2011	6,307,991	5,711,711	596,279

2012	6,963,460	6,963,036	424

Total	44,051,575	42,504,053	1,547,521

Such savings could have been used for improving monitoring resources.

6.3.5	There is a risk that projects implemented may not be effectively monitored due to the lack of

resources which may impede on the monitoring activities of the Unit.

6.4 Monitoring and evaluation of rural electrification projects

6.4.1	Monitoring and evaluation of projects and contracts allows the identification of key areas requiring

management‟s attention for improvement.

6.4.2	Monitoring and evaluation of Rural Electrification Projects activities is critical in ensuring that the

specifications set in the contract and the guidelines is complied with and that applicable courses of

actions are taken if they are not complied with.

6.4.3	The monitoring and evaluation reports were not produced for scrutiny. The evaluation of the REU‟s

performance was not done, but annual performance was always reported in annual report.

6.4.4	The management of REU has not been able to evaluate its performance in rural electrification; to

identify challenges, track progress and develop corrective measures and this may affect the

achievement of the rural connections set in the corporate plan.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	35

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

RECOMMENDATIONS

The Department should:

	adequately resource the REU with a vehicle and sufficient personnel to fill vacant posts; and

	maintain records of monitoring and evaluations of REU‟s performance.

Management Comments

No management comments received

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	36

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

7.0 CONCLUSION

7.1.1	Although management of the rural electrification program is guided by policies and operating

guidelines, these documents need to be reviewed. Most current practices need to be documented

and included in the policies and guidelines to bolster its authoritativeness. Well documented

practices ensure relevance, compliance and accountability.

7.1.2	Despite a lack of resources, the Unit has been able to administer and implement the rural

electrification program. However maintenance and security over records are lacking. Follow up

action on recoveries of user pay systems and community contributions were not evident.

7.1.3	The effectiveness of monitoring activities is hindered by a lack of resources. The REU monitors

projects implemented under the rural electrification program within the resources available to it.

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	37

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

8.0 REFERENCES

1. Cabinet Decision No. 121 o 23rd March 1993

2. Cabinet Memorandum CP(10)07 of 15th January 2010

3. Cabinet Memorandum CP(11)59 of 25th February 2011

4. Cabinet Memorandum CP(11)292 of 9th September 2011

5. Department of Energy Annual Reports 2006-2007, 2008, 2009

6. Department of Energy Website

7. National Energy Policy 2006

8. REU Guidelines Policy Summary and Standard Operational Procedures 2005

9. Review of the Fiji National Energy Policy Final Inception Report April 2013, Economic Consulting

Associates, SMEC (New Zealand)

10. Rural Electrification Policy 1993

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	38

| Diesel engine driven generator | Diesel generator with starting system |
| --- | --- |
| Switches | Underground cable distribution incorporating ground level distribution pillars |
| Fuel system and steel base frame | Controller |
| Viani Primary: Basic Wooden structured power house not located under a shady area | Nayaroyaro: Basic Wooden structured power house not located under a shady area |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1:	GENERATORS INSPECTED AND

POWERHOUSES

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	39

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 2: COST OF SOLAR SYSTEMS PER

HOUSEHOLD

SHS installed in 2008

Village/Settlement	Province	No of

Applications

Amount Quoted

$

Amount Paid By

DOE

$$

Cost Per

System

Funded

By

Loa	Cakaudrove	43	2,150.00	7,852.66	182.62  GOV

Nanuca	Cakaudrove	6	300.00	16,456.02	2742.67  GOV

Kasavu	Cakaudrove	33	1,650.00	90,508.11	2742.67  GOV

Drekeniwai	Cakaudrove	6	300.00	16,456.02	2742.67  GOV

Viani	Cakaudrove	44	2,200.00	120,677.48	2742.67  GOV

Kanakana	Cakaudrove	67	3,350.00	183,758.89	2742.67  GOV

Valeni	Macuata	10	500.00	27,426.70	2742.67  GOV

TOTAL	209	10,450.00	463,135.88

SHS installed in 2009

Village/Settlement	Province	No of Applications	Amount

Quoted

$

Amount Paid By

DOE

$

Cost Per

System

Funded

By

Nakawakawa	Bua	10	500	27,426.70  2,742.67	GOV

Daria	Bua	5	2500	13,713.35  2,742.67	GOV

Saolo	Bua	12	600	32,912.04  2,742.67	GOV

Nawaisomo	Bua	4	200	10,970.68  2,742.67	GOV

Korokadi Settlement	Bua	22	2,100	60,338.74  2,742.67	GOV

Vunivere	Macuata	21	2,050	57,596.07  2,742.67	GOV

Malawai Settlement	Macuata	30	1,5000	82,280.10  2,742.67	GOV

Muanidevo Settlement	Macuata	15	7500	41,140.05  2,742.67	GOV

Matainadoi	Macuata	12	6000	32,912.04  2,742.67	GOV

Nabiti	Macuata	3	150	8,228.01  2,742.67	GOV

Namuka-I cake	Macuata	4	200	10,970.68  2,742.67	GOV

Nabubu	Macuata	1	50	2,742.67  2,742.67	GOV

Visiqo	3	150	8,228.01  2,742.67	GOV

Total	142	9,1000	389,459.14

SHS installed 2010

Applicants       	Amount Quoted

$         	Amount Paid by

Village/Settlement	Province	No of

DOE

$

Cost Per

System

$

Funded By

Batiri	Macuata	17	850.00	50,055.99	2944.47	GOV

Ucunivatu	Cakaudrove	19	950.00	55,944.93	2944.47	GOV

Navutuvutu	Cakaudrove	21	1,050.00	61,833.87	2944.47	GOV

Dromuninuku	Cakaudrove	56	2,800.00	164,890.32	2944.47	GOV

Nasinu Village	Cakaudrove	37	1,850.00	108,945.39	2944.47	GOV

Nasinu Settlement	Cakaudrove	31	1,550.00	91,278.57	2944.47	GOV

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	40

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Navakacoa	Cakaudrove	35	1,750.00	103,056.45	2944.47	GOV

Vuya	Bua	23	1,150.00	67,722.81	2944.47	GOV

Batiniuciwai	Bua	11	550.00	32,389.17	2944.47	GOV

Yauvula	Bua	4	200.00	11,777.88	2944.47	GOV

Wainivesi	Bua	3	150.00	8,833.41	2944.47	GOV

Taraqiloqilo	Bua	6	300.00	17,666.82	2944.47	GOV

Daria	Bua	1	50.00	2,944.47	2944.47	GOV

Nautoloulou	Bua	6	300.00	17,666.82	2944.47	GOV

Tadema	Bua	1	50.00	2,944.47	2944.47	GOV

Nabelovuso	Bua	1	50.00	2,944.47	2944.47	GOV

Paptea	Rotuma	13	650.00	38,278.11	2944.47	GOV

Eveve, Uanheta	Rotuma	41	2,050.00	120,723.27	2944.47	GOV

Total	403	20,150.00	1,186,621.41

SHS installed 2012

Village/Settlement	Province	No of

Applications

Amount Quoted

$

Amount Paid By

DOE

$

Cost Per

System

Funded

By

Navaga, Magodro	Ba	20	1,680.00	54,000.00	2700.00	GOV

Droca, Nasarawaqa	Bua	2	168.00	5,400.00	2700.00	GOV

Nakalavo	Bua	5	420.00	13,500.00	2700.00	GOV

Namalata	Bua	27	2,268.00	72,900.00	2700.00	GOV

Nasarawaqa Sett	Bua	30	2,520.00	81,000.00	2700.00	GOV

Natokelau, Kubulau	Bua	28	2,352.00	75,600.00	2700.00	GOV

Navunievu	Bua	14	1,176.00	37,800.00	2700.00	GOV

Nawaca / Wailele	Bua	8	672.00	21,600.00	2700.00	GOV

Savusomo, Nasarawaqa	Bua	1	84.00	2,700.00	2700.00	GOV

Sawani	Bua	2	168.00	5,400.00	2700.00	GOV

Soti	Bua	10	840.00	27,000.00	2700.00	GOV

Viligau	Bua	1	84.00	2,700.00	2700.00	GOV

Vuniuto, Nasarawaqa	Bua	6	504.00	16,200.00	2700.00	GOV

Waibunabuna, Lekutu	Bua	23	1,932.00	62,100.00	2700.00	GOV

Bagasau	Cakaudrove	48	4,032.00	129,600.00	2700.00	GOV

Burotu Sett, Taveuni	Cakaudrove	5	420.00	13,500.00	2700.00	GOV

Dawara Village	Cakaudrove	16	1,344.00	43,200.00	2700.00	GOV

Drekeniwai	Cakaudrove	4	336.00	10,800.00	2700.00	GOV

Dreketi village, Taveuni	Cakaudrove	1	84.00	2,700.00	2700.00	GOV

Karoko Village, Tunuloa	Cakaudrove	61	5,124.00	164,700.00	2700.00	GOV

Koroni Sett, Taveuni	Cakaudrove	3	252.00	8,100.00	2700.00	GOV

Lea	Cakaudrove	3	252.00	8,100.00	2700.00	GOV

Malake, Saqani	Cakaudrove	22	1,848.00	59,400.00	2700.00	GOV

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	41

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Nagasauva	Cakaudrove	21	1,764.00	56,700.00	2700.00	GOV

Saqani Settlement	Cakaudrove	10	840.00	27,000.00	2700.00	GOV

Nalele Sett, Taveuni	Cakaudrove	1	84.00	2,700.00	2700.00	GOV

Natokalau Sett, Taveuni	Cakaudrove	3	252.00	8,100.00	2700.00	GOV

Niuwea	Cakaudrove	6	504.00	16,200.00	2700.00	GOV

Salia, Tunuloa	Cakaudrove	44	3,696.00	118,800.00	2700.00	GOV

Sese Saqani	Cakaudrove	49	4,116.00	132,300.00	2700.00	GOV

Udukacu Sett, Taveuni	Cakaudrove	11	924.00	29,700.00	2700.00	GOV

Valeni	Cakaudrove	20	1,680.00	54,000.00	2700.00	GOV

Waimaqera Subdiv.,Taveuni	Cakaudrove	43	3,612.00	116,100.00	2700.00	GOV

Wainigadru Village	Cakaudrove	31	2,604.00	83,700.00	2700.00	GOV

Waitete Sett, Taveuni	Cakaudrove	5	420.00	13,500.00	2700.00	GOV

Ura Estate	Cakaudrove	1	84.00	2,700.00	2700.00	GOV

Waivula, Navatu	Cakaudrove	9	756.00	24,300.00	2700.00	GOV

Caurokodrika	Macuata	23	1,932.00	62,100.00	2700.00	GOV

Cawaro, Udu	Macuata	47	3,948.00	126,900.00	2700.00	GOV

Daku Village, kia Island	Macuata	12	1,008.00	32,400.00	2700.00	GOV

DruaDrua Isl.	Macuata	43	3,612.00	116,100.00	2700.00	GOV

DruaDrua school	Macuata	10	840.00	27,000.00	2700.00	GOV

Kawakawavesi, Seaqaqa	Macuata	27	2,268.00	72,900.00	2700.00	GOV

Matainadoi	Macuata	2	168.00	5,400.00	2700.00	GOV

Muanidevo/Malawai	Macuata	26	2,184.00	70,200.00	2700.00	GOV

Namakomako, Macuata	Macuata	3	252.00	8,100.00	2700.00	GOV

Naqaraniqoli, Dreketi	Macuata	32	2,688.00	86,400.00	2700.00	GOV

Naua, Namuka	Macuata	4	336.00	10,800.00	2700.00	GOV

Navai, Seaqaqa	Macuata	25	2,100.00	67,500.00	2700.00	GOV

Qaranivai	Macuata	22	1,848.00	59,400.00	2700.00	GOV

Vitina, Dogotuki	Macuata	30	2,520.00	81,000.00	2700.00	GOV

Vudibasoga Catholic Pri. Sch	Macuata	9	756.00	24,300.00	2700.00	GOV

Vunikodi, Udu	Macuata	13	1,092.00	35,100.00	2700.00	GOV

Vunivere	Macuata	12	1,008.00	32,400.00	2700.00	GOV

Nabutautau	Navosa	21	1,764.00	56,700.00	2700.00	GOV

Ovalau, Nasau	Ra	30	2,520.00	81,000.00	2700.00	GOV

Naibalebale, Viwa, Yasawa	Ba	48	3,264.00	192,000.00  4000.00	PEC

Dalomo, Yasawa	Ba	25	1,700.00	100,000.00  4000.00	PEC

Teci, Yasawa	Ba	21	1,428.00	84,000.00  4000.00	PEC

Gunu, Yasawa	Ba	68	4,624.00	272,000.00  4000.00	PEC

Yanuya village, Malolo	Ba	33	2,244.00	132,000.00  4000.00	PEC

Natia, Viwa Yasawa	Ba	30	2,040.00	120,000.00  4000.00	PEC

Nalotu, Yawe	Kadavu	53	3,604.00	212,000.00  4000.00	PEC

Naikorokoro, Kadavu	Kadavu	18	1,224.00	72,000.00  4000.00	PEC

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	42

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Kavala Bay Pri School	Kadavu	13	884.00	52,000.00  4000.00	PEC

Naivakarauniniu	Kadavu	28	1,904.00	112,000.00  4000.00	PEC

Rakiraki, Yale	Kadavu	36	2,448.00	144,000.00  4000.00	PEC

Lagalevu, Nakasaleka	Kadavu	18	1,224.00	72,000.00  4000.00	PEC

Matasawalevu, Nakasaleka	Kadavu	34	2,312.00	136,000.00  4000.00	PEC

Soso, Naceva	Kadavu	19	1,292.00	76,000.00  4000.00	PEC

Nauciwai, Nakasaleka	Kadavu	13	884.00	52,000.00  4000.00	PEC

Vutuna, Nairai	Lomaiviti	14	952.00	56,000.00  4000.00	PEC

Waitoga, Nairai	Lomaiviti	32	2,176.00	128,000.00  4000.00	PEC

Somosomo, Sawaieke	Lomaiviti	29	1,972.00	116,000.00  4000.00	PEC

Sawaieke District School, Gau	Lomaiviti	9	612.00	36,000.00

4000.00    PEC

Mua village, Batiki	Lomaiviti	16	1,088.00	64,000.00  4000.00	PEC

Daku , Moturiki	Lomaiviti	26	1,768.00	104,000.00  4000.00	PEC

Uluibau, Moturiki	Lomaiviti	51	3,468.00	204,000.00  4000.00	PEC

Nasauvuki, Moturiki	Lomaiviti	45	3,060.00	180,000.00  4000.00	PEC

Wawa, Moturiki	Lomaiviti	7	476.00	28,000.00  4000.00	PEC

Dakuni, Beqa	Rewa	22	1,496.00	88,000.00  4000.00	PEC

Total	1693	$130,884.00	$5,491,500.00

SHS installed 2013

APPLICANTS     	AMOUNT QUOTED

$         	AMOUNT PAID BY

VILLAGE / SETTLEMENT	PROVINCE	NO OF

DOE

$

COST PER

SYSTEM

$

FUNDED BY

Maloku, Moala	Lau	16	1,088.00	64,000.00	4000.00	PEC

Naceva, Cicia	Lau	40	2,720.00	160,000.00	4000.00	PEC

Malaka, Vanuabalavu	Lau	22	1,496.00	88,000.00	4000.00	PEC

Nukunuku, Lakeba	Lau	37	2,516.00	148,000.00	4000.00	PEC

Salia, Nayau	Lau	57	3,876.00	228,000.00	4000.00	PEC

Lovoni, Qamea	Cakaudrove	13	884.00	52,000.00	4000.00	PEC

Dreketi, Qamea	Cakaudrove	24	1,632.00	96,000.00	4000.00	PEC

Togo Settlement, Qamea	Cakaudrove	21	1,428.00	84,000.00	4000.00	PEC

Qamea                 	Cakaudrove

Korowai Settlement,

8            544.00              32,000.00   4000.00   PEC

Cikobia (Vuninuku/Nalele/

Vatulele/Cikobia District

Macuata          48           3,264.00            129,600.00

GOV

School)

2700.00

Tadravula, Seaqaqa	Macuata	11	748.00	29,700.00	2700.00	GOV

Valelawa, Batiri	Macuata	6	408.00	16,200.00	2700.00	GOV

Lalakoro/Dagau, Seaqaqa	Macuata	59	4,012.00	159,300.00	2700.00	GOV

Vunimako, Seaqaqa	Macuata	17	1,156.00	45,900.00	2700.00	GOV

Navudi, Seaqaqa	Macuata	10	680.00	27,000.00	2700.00	GOV

Savulutu, Seaqaqa	Macuata	16	1,088.00	43,200.00	2700.00	GOV

Korotolutolu, Seaqaqa	Macuata	32	2,176.00	86,400.00	2700.00	GOV

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	43

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Vudibasoga Primary

Macuata          9            612.00              24,300.00   2700.00   GOV

School

Tikilo, Seaqaqa	Macuata	7	476.00	18,900.00	2700.00	GOV

Seaqaqa                 	Macuata

Natekateka Settlement,

9            612.00              24,300.00   2700.00   GOV

Naocobele/Korolailai Sett,

Macuata          15           1,020.00             40,500.00   2700.00   GOV

Nadogo

Vunikodi, Udu	Macuata	4	272.00	10,800.00	2700.00	GOV

Malawai, Dreketi	Macuata	17	1,156.00	45,900.00	2700.00	GOV

Kelikoso, Nadogo	Macuata	4	272.00	10,800.00	2700.00	GOV

Saroni Sett, Nadogo	Macuata	10	680.00	27,000.00	2700.00	GOV

Nasea, Seaqaqa	Macuata	25	1,700.00	67,500.00	2700.00	GOV

Vunimokosoi, Navonu	Cakaudrove	28	1,904.00	75,600.00	2700.00	GOV

Navuci Sett, Navonu	Cakaudrove	18	1,224.00	48,600.00	2700.00	GOV

Dawara, Wailevu	Cakaudrove	2	136.00	5,400.00	2700.00	GOV

Naviavia Settlement,

Cakaudrove         49           3,332.00            132,300.00   2700.00   GOV

Wailevu

Waisali, Wailevu	Cakaudrove	15	1,020.00	40,500.00	2700.00	GOV

Qaralevu sett, Tunuloa	Cakaudrove	9	612.00	24,300.00	2700.00	GOV

Waivula, Navatu	Cakaudrove	2	136.00	5,400.00	2700.00	GOV

Batiniuciwai, Wainunu	Bua	38	2,584.00	102,600.00	2700.00	GOV

Wainunu Sett	Bua	5	340.00	13,500.00	2700.00	GOV

Nakabuta, Wainunu	Bua	8	544.00	21,600.00	2700.00	GOV

Nakawakawa, Wainunu	Bua	5	340.00	13,500.00	2700.00	GOV

Nadua, Wainunu	Bua	2	136.00	5,400.00	2700.00	GOV

Saolo, Wainunu	Bua	11	748.00	29,700.00	2700.00	GOV

Togalevu, Wainunu	Bua	2	136.00	5,400.00	2700.00	GOV

Nacula Estate, Wainunu	Bua	22	1,496.00	59,400.00	2700.00	GOV

Yaqaga, Lekutu	Bua	21	1,428.00	56,700.00	2700.00	GOV

Cavaga, Solevu	Bua	7	476.00	18,900.00	2700.00	GOV

Nasau, Navakasiga	Bua	39	2,652.00	105,300.00	2700.00	GOV

Nasarawaqa village	Bua	64	4,352.00	172,800.00	2700.00	GOV

Rotuma	Rotuma	121	8,228.00	326,700.00	2700.00	GOV

Dala Sett, Taveuni	Cakaudrove	15	1,020.00	40,500.00	2700.00	GOV

Waitabu, Taveuni	Cakaudrove	27	1,836.00	72,900.00	2700.00	GOV

Waimaqera, Taveuni	Cakaudrove	46	3,128.00	124,200.00	2700.00	GOV

Qarawalu, Taveuni	Cakaudrove	37	2,516.00	99,900.00	2700.00	GOV

Mataniwai, Taveuni	Cakaudrove	5	340.00	13,500.00	2700.00	GOV

Delaivuna, Taveuni	Cakaudrove	3	204.00	8,100.00	2700.00	GOV

Navaca, Taveuni	Cakaudrove	2	136.00	5,400.00	2700.00	GOV

Wainiyaku, Taveuni	Cakaudrove	1	68.00	2,700.00	2700.00	GOV

Nabouono, Taveuni	Cakaudrove	1	68.00	2,700.00	2700.00	GOV

Navunitawa, Vaturu	Ba	6	408.00	16,200.00	2700.00	GOV

Bila, Magodro	Ba	4	272.00	10,800.00	2700.00	GOV

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	44

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Navaga, Magodro	Ba	4	272.00	10,800.00	2700.00	GOV

Nayavutoka, Nakorotubu	Ra	28	1,904.00	75,600.00	2700.00	GOV

Namara, Nalawa	Ra	15	1,020.00	40,500.00	2700.00	GOV

Narau settlement, Mataso	Ra	34	2,312.00	91,800.00	2700.00	GOV

TOTAL	1233	$83,844.00	$3,638,500.00

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	45

| Scheme No. | Description | District | No. of applicants | Quoted amount $ | Date quoted | Expiry date | Date paid | Amount paid | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | WESTERN |  |  |  |  |  |  |  |  |
| NA09/10 | MATANISIGA SETTLEMENT | NADI | 2 | 8,908 | 10/21/2010 | 10/21/2011 | 12/7/2011 | 8,908 | Construction completed and commissioned |
| SG11/09 | KOROUA VILLAGE | SIGATOKA |  | 67,374 | 6/6/2010 | 6/6/2011 | 12/12/2011 | 67,374 | Construction completed |
| LU04/10 | BELEKI SETTLEMENT - VITOGO | LAUTOKA | 5 | 21,231 |  |  | 12/12/2011 | 21,231 | Completed and commissioned |
| SG04/06 B-2 | KEIYASI GOVT. STATION - FINAL STAGE | SIGATOKA |  | 265,828 |  |  | 12/12/2011 | 265,828 | Construction in progress |
| RA04/09 | VATUKACEVACE VA VILLAGE | RAKIRAKI | 92 | 313,368 |  |  | 12/12/2011 | 313,368 | Construction in progress |
|  |  |  |  | 676,709 |  |  |  |  |  |
|  | NORTHERN |  |  |  |  |  |  |  |  |
| LAB17/10 | GAUNAVOU SETTLEMENT - NADURI | LABASA | 2 | 9,218 |  |  | 12/7/2011 | 9,218 | Construction completed and commissioned |
| SA01/08 | NAKASA VILLAGE AND SETTLEMENT | SAVUSAV U | 80 | 389,360 |  |  | 12/12/2011 | 389,360 | Way-leave & Survey |
| LAB09/09 | DRALADAMU SETTLEMENT | LABASA | 4 | 42,279.00 |  |  | 12/12/2011 | 42,279 | Wayleave & Survey |
|  |  |  |  | 440,857 |  |  |  |  |  |
|  | CENTRAL |  |  |  |  |  |  |  |  |
| LE01/08 | NAUOUO TO RUKURUKU | OVALAU | 300 | 500,000 |  |  | 6/28/2011 | 500,000 | Construction complete and commissioned |
| SU04/09 | VACOKO REHAB CENTRE - NABORO | SUVA | 20 | 2,466 | 10/5/2009 | 10/5/2010 | 12/7/2011 | 2,466 | Way-leave & Survey |
| KO08/10 | NAKOROLEVU VILLAGE - NAMARA | TAILEVU |  | 1,710 | 8/5/2010 | 8/5/2011 | 12/7/2011 | 1,710 | Construction to start soon |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX	3:	INCOMPLETE	ENTRIES	IN

SPREADSHEET

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	46

| Project | Name of Contractor | Agreement date | Completion date | Amount $ | Audit Comments |
| --- | --- | --- | --- | --- | --- |
| Nawakalevu Settlement – Nadi | Power Electric | 01/06/10 | 30/08/12 | 14,580.00 | No list for the number of houses in the scheme |
| Nawaisomo Village - Kadavu - | Quality Electrical and Refrigeration Services | 06/05/10 | 25/06/12 | 51,942.03 | No list for the number of houses in the scheme |
| Nayaroyaro Village - Macuata | Quality Electrical and Refrigeration Services | 06/05/10 | Page missing | 30,297.54 | The signed agreement by both parties& commencement pages missing. |
| Saliadrau Village - Namosi | Quality Electrical and Refrigeration Services | 06/05/10 | 27/05/10 | 73,464.98 | No list for the number of houses in the scheme |
| Nagado Village - Nadi | Power Electric | 01/06/10 | 31/08/10 | 68,208.77 | No list for the number of houses in the scheme |
| Banisoqosoqo Settlement - Ra | Power Electric | 01/06/10 | 31/08/10 | 19,440.00 | No list for the number of houses in the scheme |
| Delaiwaimale Village, Naitasiri | Power Electric | 01/06/10 | 31/08/10 | 12,037.50 | No list for the number of houses in the scheme |
| Bulia Village - Kadavu | Power Electric | 20/08/09 | 31/01/10 | 67,128.56 | No list for the number of houses in the scheme |
| Nakoronawa Village - Kadavu | Power Electric | 20/08/09 | 31/01/10 | 35,296.49 | No list for the number of houses in the scheme |
| Navunibau Village - Namosi | Quality Electrical and Refrigeration Services | 21/08/09 | 31/10 | 45,532.62 | No list for the number of houses in the scheme |
| Mataqali Vunativi – Yanuya Island | Quality Electrical and Refrigeration Services | 21/08/09 | 31/11 | 33,010.32 | No list for the number of houses in the scheme. The contract was wrongly titled attached to Navunibau Village - Namosi |
| Navunikabi Catholic School | Quality Electrical and Refrigeration Services | 20/08/09 | 31/01/10 | 34,224.31 | No list for the number of houses in the scheme |
| Vunikoro Village - Cakaudrove | Quality Electrical and Refrigeration Services | 06/05/10 | 06/08/10 | 59,082.28 | No list for the number of houses in the scheme |
| Saqani Secondary School - Cakaudrove | Quality Electrical and Refrigeration Services | 06/05/10 | 09/07/10 | 89,972.55 | No list for the number of houses in the scheme |
| Malomalo – Naidiri, Nadroga | Power Electric | 01/06/10 | 31/08/10 | 62,330.63 | No list for the number of houses in the scheme |
| Total |  |  |  | 696,548.58 |  |

| Project | Name of Contractor | Agreement date | Completio n date | Amount $ | Audit Comments |
| --- | --- | --- | --- | --- | --- |
| Bulabula Farming Community – Ba –30 houses | Quality Electrical and Refrigeration Services | 10/11/11 | Not filled | 26,789.72 | Completion date missing. |
| Nameka & Natuva Village- Tailevu – 85 houses | Quality Electrical and Refrigeration Services | 10/11/11 | Not filled | 53,271.79 | Contract copy in file is unsigned by both parties. Filed copy is not the final one |
| Matamaivere Village- Tailevu – 31 houses | Quality Electrical and Refrigeration Services | 10/11/11 | Not filled | 21,338.19 | Contract copy in file is unsigned by both parties. Filed copy is not the final one |
| Namuka & Nakoroivau Village- Tailevu - 110 houses | Quality Electrical and Refrigeration Services | 10/11/11 | Not filled | 64,308.36 | Contract copy in file is unsigned by both parties. Filed copy is not the final one |
| Viria Village & Settlement - Tailevu – 100 houses | Quality Electrical and Refrigeration Services | 10/11/11 | 31/12/11 | 106,703.91 | The amount stated in the signed contract is $21,338.19, it was crossed and it‟s written typing error, |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 4: COMPLETED PROJECTS

Year 2010

Year 2011

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	47

|  |  |  |  |  | figure changed. |
| --- | --- | --- | --- | --- | --- |
| Installation of Generators – 10 sets | CBS Power Solutions Ltd | 18/02/11 | 30/04/11 | 22,271.85 | File properly maintained. |
| Nauouo to Rukuruku Villages – Ovalau - 100 houses | Letrik Ltd | 10/11/11 | 30/03/12 | 125,737.75 | File properly maintained. |
| Nawaka Tramline – Nadi - 20 houses | Letrik Ltd | 10/11/11 | 30/01/12 | 16,326.12 | File properly maintained. |
| Total |  |  |  | 562,363.36 |  |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

MANAGEMENT OF RURAL ELECTRIFICATION PROGRAM	48

PUBLIC DEBT

MANAGEMENT

A performance audit report of the Office of the

Auditor General of the Republic of Fiji

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Rising debt levels present problems for Government especially since servicing of such debts have significant impacts

on government expenditure. The proper management of public debt is crucial in ensuring sustainability of public debt.

This report discusses findings from an assessment of the effectiveness of public debt management in ensuring

sustainability of public debt.

Table of Contents

1.0 EXECUTIVE SUMMARY........................................................................................................................	4

2.0 INTRODUCTION ....................................................................................................................................	6

2.1	Background..................................................................................................................................................6

2.2	Legislation....................................................................................................................................................7

2.3	Administering agency ...................................................................................................................................7

2.4	Other agencies influencing determination of borrowing needs .....................................................................8

2.5	Reasons for undertaking the audit..............................................................................................................10

3.0 AUDIT OBJECTIVES, SCOPE, & METHODOLOGY ...........................................................................	11

3.1	Audit objectives..........................................................................................................................................11

3.2	Audit scope.................................................................................................................................................11

3.3	Audit methodology ......................................................................................................................................11

4.0 DETERMINATION OF PUBLIC BORROWING NEEDS.......................................................................	13

4.1	Process of determining borrowing need .....................................................................................................13

4.2	Reliability of budget deficit estimation.........................................................................................................17

4.3	System for determining debts due ..............................................................................................................18

4.4	Estimation of contingencies ........................................................................................................................19

5.0 PUBLIC DEBT REPORTING................................................................................................................	22

5.1	Statutory reporting requirements of public debt ..........................................................................................22

5.2	Government debt reports............................................................................................................................24

5.3	Reporting of contingent liabilities ................................................................................................................26

5.4	Mechanism for implementing agencies to regularly report to Ministry of Finance ......................................29

6.0 CONCLUSION .....................................................................................................................................	32

7.0 REFERENCES.....................................................................................................................................	33

APPENDIX 1.0	CHARGES ON ACCOUNT OF PUBLIC DEBT 2009-2012.........................................34

PUBLIC DEBT MANAGEMENT	2

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Acronyms

CPA	Cooperative Performance Audit

CSB	Cabinet Sub Committee to Budget

CS-DRMS	Commonwealth Secretariat – Debt Recording Management System

DCFMU	Debt & Cash Flow Management Unit

FJDs	Fiji Dollars

FRCA	Fiji Revenue and Customs Authority

FSC	Fiji Sports Council

MCFF	Monthly Cash Flow Forecast

MoF	Ministry of Finance

PASAI	Pacific Association of Supreme Audit Institution

PSIP	Public Sector Investment Program

RBF	Reserve Bank of Fiji

MSPNDs	Ministry of Strategic Planning, National Development & Statistics

PUBLIC DEBT MANAGEMENT	3

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

1.0	EXECUTIVE SUMMARY

Background:	The main determinant for borrowings has been the financing of Government’s annual deficit, since government

revenue has not been able to cover all of government’s expenditure, particularly capital expenditure. Over the

past 5 years, Government borrowings have increased steadily from $3.1billion in 2009 to $3.8billion in 2013. The

increasing trends in public debt highlight the importance of public debt management to ensure sustainability of

public debt.

Coverage:	The audit on “Public Debt Management” focused on two areas namely, “the determination of public

borrowing needs”, and “public debt reporting”.

Public debt management in government is a collaborative effort amongst all government entities and relevant

key stakeholders, with the Ministry of Finance as the key agency responsible overall. The audit centers on the

Ministry of Finance as the focal ministry responsible for administering borrowings on behalf of Government.

Key findings: 1) Determination of public borrowing needs

	Government’s borrowing needs is determined through the structured annual budget process that involves a

significant amount of information and coordination amongst relevant government entities. A conservative

approach to budgeting is adopted as evidenced in the disparities reflected between projected deficits and

actual deficits, and which distorts the planned projection of government’s borrowing needs.

	Over the past 5 years Government borrowings have increased steadily from $3.1billion in 2009 to $3.8billion

in 2013. However, declining trends or percentage decreases were noted in actual borrowings as a

percentage of GDP from 2010 to 2012, and which are less than the fiscal targets forecasted.

	The Debt and Cash Flow Management Unit (DCFMU) has adequately provided information pertaining to debt

servicing requirements and for which sufficient provisions have been provided for in the annual budget of

government. However, in 2009 and 2012 actual debt servicing for domestic borrowing paid exceeded

budgetary provisions. Actual debt servicing for short term borrowing also exceeded budgeted provided in

2010.

	Considerations on the potential impacts of contingent liabilities to the economy are factored in the budget

process. Provisions have been set aside in the annual budget over the past 5 years 2009 to 2013 to cater for

meeting obligations for contingent liabilities. During the 5 years 2009 to 2013, Government has only had to

meet contingent liability of the Fiji Sports Council and the Fiji Sugar Cane Growers Council.

2) Public debt reporting

	Public debt and contingent liabilities of Government have been adequately reported in the whole of

government’s annual financial statements. Financial disclosures of public debt and contingent liabilities are

deemed accurate and reliable as they have been subjected to thorough scrutiny.

	There are sufficient disclosures in the Government Debt Reports and Contingent Liability Reports.

PUBLIC DEBT MANAGEMENT	4

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Overall audit conclusion	Government’s borrowing need is determined in view of the current to medium term and is

sustainable. The process in place to determine borrowing needs and its debt servicing requirements,

and the provision of funds to meet contingent liabilities are sufficient to ensure sustainability in the

current and medium term. However, with public debt and contingent liabilities of government steadily

increasing over the years, Government may have to reconsider debt management strategies to

ensure long term sustainability.

General recommendation Although public debt is currently maintained within the projected annual fiscal targets, the Ministry

should consider employing strategies that will enable it to achieve the ideal rule of thumb target of

40% of GDP to ensure sustainability in the long term.

PUBLIC DEBT MANAGEMENT	5

Auditing Public Debt Management – A Practical Guide, IDI 2001

Guidelines for Public Debt Management – IMF and World Bank 2001

Guidelines for Public Debt Management – IMF and World Bank, 2001

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.0 INTRODUCTION

This section of the report provides a brief overview of arrangements in place for acquiring

government borrowing as well as provides reasons for the conduct of the audit.

2.1 Background

2.1.1	Government debt, also known as public debt and national debt is the debt owed by a central government,

and is one method of financing government operations1.	Government usually borrows by issuing

securities, government bonds, and treasury bills, as well as borrowing directly from international

organisations.

Since government draws its income from much of the population, government debt is an indirect debt of the

taxpayers and can be categorised as internal debt. Public borrowing and debt can expand the production

and consumption choices of current and future generations, allowing governments to increase investments

and distribute the tax burden more fairly between current and future generations2. However, public

borrowing and debt entail significant risks if they are not managed properly.

2.1.2	Sovereign debt on the other hand usually refers to government debt that has been issued in foreign

currency. Sovereign debt management is the process of establishing and executing a strategy for

managing the government’s debt in order to meet any other sovereign debt management goals the

government may have set3.

2.1.3	A government’s debt portfolio is usually the largest financial portfolio in the country, which often contains

complex and risky financial structures, and can generate substantial risk to the government’s balance sheet

and to the country’s financial stability4.

2.1.4	Declining revenues and/or increased government spending/expenditure contribute towards public debt.

2.1.5	Public debt impacts on the overall economy and can seriously undermine the financial condition of a

government. Therefore it is important to have in place robust public debt management strategies that

include sound risk management practices, to achieve long term sustainability and financial stability.

2.1.6	Government borrows funds either through external sources i.e. from overseas countries as well internally

through the local financial markets.

The Fiji Government’s debt position as at 31st December 2013 stood at $3.83 billion comprising of $2.74

billion domestic debt and $1.08 billion external debt.

1 Wikipedia

2

3

4

PUBLIC DEBT MANAGEMENT	6

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.2 Legislation

2.2.1	Part 9 of the Financial Management Act 2004 empowers the Minister for Finance, on behalf of the State to:

 borrow money by way of loans, overdrafts or advances in order to fund budget deficits or for other

purposes authorised by the House of Representatives5;

 enter into a hedging arrangement, provided it is in accordance with a prescribed debt strategy

policy6; and

 guarantee the financial liabilities of a statutory authority or majority government owned company,

where authorised by the House of Representatives7.

Any pay out of a guarantee by Government is taken as a loan to the state entity whose liability was

guaranteed.

2.2.2	In the absence of a Parliament, powers to approve the borrowing of monies to fund budget deficits and the

guaranteeing of loans is vested with the Cabinet.

2.3 Administering agency

2.3.1	The Ministry of Finance assumes the lead role in the drafting of fiscal and monetary policies in coordination

with the Ministry of Strategic Planning, National Development, & Statistics (MSPNDS) and the Reserve

Bank of Fiji (RBF) respectively. Policies are formulated at macro level and proposed to Cabinet for

approval.

2.3.2	The two key Units within the Ministry of Finance that are responsible for the drafting of policies and the

management of public debt are the Budget Division’s Budget Policy Monitoring & Analysis Unit, and the

Financial Asset Management Division’s Debt & Cash Flow Management Unit (DCFMU), as illustrated in

figure 2.1 below.

5 Financial Management Act 2004 s.59

6 Financial Management Act 2004 s.60

7 Financial Management Act 2004 s.61

PUBLIC DEBT MANAGEMENT	7

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Figure 2.1: Organisation Structure of the Ministry of Finance

MOF

Administration

Financial Asset Management

Budget                                        Government Printer

Revenue Policy, Forecasting and Analysis

Budget Policy Monitoring and Analysis

Overseas Development Assistance

Expenditure Management and Analysis

Debt & Cash Flow Management

Asset Management

Financial Policy Assurance

Financial Management Information System

Treasury

2.3.3	The Budget Division adopts the approved policies in the budget process. Fiscal policies influence the level

of borrowing depending on which stance government wants for the economy. For example, if the Fiji

Government wants to boost economic growth, it would opt for an expansionary fiscal policy, thus requiring

more borrowing to improve infrastructure and other sectors. The magnitude of expenditure has an impact

on the net budget deficits which determine the level of government borrowing.

2.3.4	The DCFMU is responsible for the management of all Government domestic and foreign debt by identifying

lending agencies, securing loans by negotiation, documentation of all loan agreements, monitoring and

reporting on the various aspects of the loan and servicing all obligations of the loan on the due date. For

domestic debt, this involves the management of the domestic bond and Treasury Bills tenders using the

RBF as an agent and servicing all obligations through the registry on the due date. In addition, the DCFMU

is responsible for the overall management of cash, investment of surplus cash, recording of contingent

liabilities through guarantees and for project finance for statutory bodies as well as management of

government’s arrears of revenue and lending fund account.

2.4 Other agencies influencing determination of borrowing needs

2.4.1	The determination of a government borrowing need is a complex function that requires a significant amount

of information and coordination among government agencies in the budget process. A complete, thorough

budgeting process results in a more accurate budget8 which would lead to an accurate estimate of

borrowing.

8 Investorwords.com

PUBLIC DEBT MANAGEMENT	8

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.4.2	The central key agencies of Government that are influential in the formulation of macro-economic policies

include the Ministry of Finance (MoF), the Ministry of Strategic Planning, National Development and

Statistics (MSPNDS); the Fiji Revenue and Customs Authority (FRCA); and the Reserve Bank of Fiji (RBF)

The above central agencies are mostly involved in Phase 1 of the budget process cycle and play a vital role

in the planning phase as reflected in Figure 2.2 below.

Figure 2.2: Fiji Government Budget Process Cycle

2.4.3	The MOF takes the lead role in the budget process via the functions of the Budget Division. The MSPNDS

contributes to the development of fiscal policies and capital budgeting process whilst the FRCA contributes

to the fiscal - revenue policies and revenue budgeting. The RBF is responsible for developing the monetary

policies considered in the budget process. Figure 2.4 below illustrates a summary of the relationship

between macroeconomic policies and government borrowings.

Figure 2.3: Summary process of relationship between Macroeconomic policies and government borrowing

2.4.4	The other Ministries and Departments are also instrumental in the Budget formulation process and in

determining the budget outcome, i.e. a surplus or deficit budget.

PUBLIC DEBT MANAGEMENT	9

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

2.5 Reasons for undertaking the audit

2.5.1	The members of the Pacific Association of Supreme Audit Institutions (PASAI), at its annual congress

meeting in 2012 identified rising public debt as an issue of common interest in the member countries, and

endorsed the topic “Public Debt Management” for a regional cooperative performance audit.

2.5.2	In the past 5 years Fiji has been operating under a deficit budget, implying that Fiji is dependent on loans or

borrowings to finance its annual budgets.

The Fiji Government’s reliance on borrowings to finance its normal operations over the years makes it vital

to carry out a performance audit on public debt management.

PUBLIC DEBT MANAGEMENT	10

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

3.0 AUDIT	OBJECTIVES,	SCOPE,	&

METHODOLOGY

This section of the report describes the objective and scope of the audit. It also discusses the

methodology utilised to gather information for the audit.

3.1 Audit objectives

3.1.1	The objective of the audit is to ascertain whether government borrowing needs were determined in view of

long term sustainability and financial stability by examining:

i.	the process of determining borrowing needs; and

ii.	the reporting arrangements of public debt and loan guarantees.

3.1.2	In examining the process of determining borrowing needs, the audit sought to establish the effectiveness of

the budget system in ensuring that borrowing needs are determined in view to economy and sustainability.

Audit aspired to ascertain whether actual borrowings made by government in prior years were based on

correct and complete estimates of borrowings needs. It also sought to ascertain whether contingent

liabilities were adequately considered and factored into the annual budget estimates of government.

3.1.3	With respect to reporting arrangements, the audit sought to establish the effectiveness and efficiency of the

reporting system in properly recording and reporting public debt and contingent liabilities through the

production of complete, accurate and timely reports which are prepared in accordance with relevant

reporting regulations, standards, and requirements.

3.2 Audit scope

3.2.1	The audit focused on the Ministry of Finance as the agency responsible for administrating borrowing on

behalf of Government

3.2.2	The audit reviewed records maintained with respect to borrowings and the contingent liabilities of

government for the past four years, 2009 to 2013. Records of years prior to 2009 were examined where

deemed necessary.

3.3	Audit methodology

3.3.1	The audit was conducted in accordance with International Standards of Supreme Audit Institutions (ISSAI)

guidelines 3000 - 3100.

PUBLIC DEBT MANAGEMENT	11

| Organisation | Unit | Position |
| --- | --- | --- |
| Ministry of Finance | Budget | Deputy Secretary Budget, Principal Economist Budget |
| Ministry of Finance | DCFMU | Director Debt, Principal Accountant Debt and officials |
| Ministry of Strategic Planning, National Development and Statistics | Macro Unit | Acting Chief Economic Planning Officer |
| Fiji Revenue and Customs Authority | Corporate Service & Policy | Principal Revenue & Policy |
| Reserve Bank of Fiji | Economics | Chief Manager Economics |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

3.3.2	To accomplish the audit objectives the audit team gathered evidence using the following techniques:

i.	Documentary reviews

The audit team reviewed all necessary documents relevant to the audit topic. Documents reviewed

included the Financial Management Act 2004; Ministry of Finance Circulars on Budget strategies;

Annual Budgets of Government with its respective Budget Address Speeches and Supplements;

Ministry of Finance Annual Corporate Plans and Annual Reports; Annual Financial Statements for the

whole of Government; and Government of Fiji Debt Report; etc.

ii.	Interviews

Interviews were carried out with relevant personnel of the various key stakeholder agencies. Person

interviewed are listed in table 3.1 below.

Table 3.1: List of persons interviewed

iii.  	Analytical review

Analytical reviews of debt management data maintained by the Debit Management and Cash Flow

Unit were conducted.

iv.	Walk through tests and re-performance

Walk through tests were carried out to verify systems in operation. Debt records were examined

and re-performances of calculations of sampled transactions were carried out to verify accuracy

and completeness of recording.

v.	Internet research

Internet research regarding issues pertaining to government borrowings and audits carried out on

the topic were conducted.

vi.	Electronic Communication

Communications via e-mails between the audit team and relevant officers in key stakeholder

agencies were made to obtain as well as reaffirm information.

PUBLIC DEBT MANAGEMENT	12

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

4.0 DETERMINATION OF PUBLIC BORROWING

NEEDS

This section of the report discusses findings on the assessment of government’s capacity to produce

and communicate promptly to debt managers the budget figures for the period; and all major

contingencies that will be realised during the period.

4.0.1	Part 2 of the Financial Management Act 2005 specifies the principles of responsible financial management,

which should be considered in managing the financial affairs of the State, amongst which includes

managing of revenue and expenditure in such a way as to achieve prudent levels of debt.

4.0.2	Assessing the sustainability of public debt is an important task of macroeconomic policy. It is recognised

that debt management strategies must be coordinated with monetary, fiscal and exchange rate policies to

ensure long term macroeconomic stability.

4.1 Process of determining borrowing need

4.1.1	The Minister must table a strategic policy statement in the House of Representative on or before the 30th

of June in each financial year9. The strategic policy statement must include amongst other things a

statement of the Government’s financial targets or limits for the next financial year and for the following two

financial years, relating to the budget result as a proportion of gross domestic product; government debt as

a proportion of gross domestic product; government debt servicing as a proportion of gross domestic

product, and contingent liabilities as a proportion of gross domestic product.

4.1.2	The strategic policy statement (SPS) prepared by the Ministry of Finance and submitted to Cabinet, sets

out Government’s broad medium-term objectives and fiscal targets, and forms the basis on which the

following annual budget is prepared. The fiscal targets set relate to the intended budget result

(deficit/surplus); the level of government debt; the level of government debt servicing; and the level of

contingent liabilities. All four targets are expressed as a percentage of gross domestic product (GDP) as it

provides an indicator of the sustainability of the government's fiscal intentions in relation to the size of the

economy as a whole, that is, the higher the percentage the greater the size/impact the public debt has on

the economy. The medium term which covers three years, i.e. the following year and the two subsequent

financial years, also include the actual/projected results for the previous two financial years for purposes of

comparison and trend analysis.

4.1.3	Over the 4 years 2009 to 2012 the Ministry of Finance has, upon Cabinet’s endorsement of the SPS,

effectively disseminated the Budget Strategy to all government entities via issuance of a Circular as listed

in table 4.1 below informing government entities of the strategy and broad guidelines for the formulation of

the Government’s Annual Budget.

9 Financial Management Act 2004 s.12

PUBLIC DEBT MANAGEMENT	13

|  | 2009 | 2010 | 2011 | 2012 (Revised) | 2013 (Target) | 2014 (Target) |
| --- | --- | --- | --- | --- | --- | --- |
| Total revenue | 1,415.9 | 1,535.90 | 1,745.67 | 1,813.01 | 1,980.49 | 2,143.56 |
| % of GDP | 24% | 26.0% | 26.3% | 25.6% | 26.0% | 26.1% |
| Total Expenditure | 1,644.7 | 1,665.62 | 1,961.72 | 2,025.7 | 2,170.9 | 2,307.8 |
| % of GDP | 28% | 28.2% | 29.6% | 28.6% | 28.5% | 28.1% |
| Net deficit | (228.9) | (129.72) | (216.05) | (212.65) | (190.43) | (164.26) |
| % of GDP | -3.8% | -2.2% | -3.3% | -3.0% | -2.5% | -2.0% |
| Debt stock | 3,376.2 | 3,382.9 | 3,575.9 | 3,788.55 | 3,978.98 | 4,143.24 |
| % of GDP | 56.6% | 57.2% | 54.0% | 53.4% | 52.2% | 50.4% |
| Operating expenditure | 4,712.42 | 1,320.13 | 1,423.32 | 1,458.48 | 1,541.35 | 1,615.47 |
| as % of Total | 24% | 26.0% | 26.3% | 25.6% | 26.0% | 26.1% |
| Capital Expenditure | 1,252.67 | 345.48 | 538.39 | 567.19 | 629.57 | 692.34 |
| as % of Total | 24% | 26.0% | 26.3% | 25.6% | 26.0% | 26.1% |
| GDP Market prices | 5,965.10 | 5,914.61 | 6,627.54 | 7,088.42 | 7,617.26 | 8,212.86 |
| GDP growth rate | -3.0 | 0.6 | 2.7 | 3.0 | 4.0 | 5.0 |

| MoF Circular No. | Date | Subject |
| --- | --- | --- |
| 10/2008 | 2/7/2008 | 2009 Budget Strategy |
| 9/2009 | 6/7/2009 | 2010 Budget Strategy |
| 12/2010 | 10/9/2010 | 2011 Budget Strategy |
| 8/2011 | 4/7/2011 | 2012 Budget Strategy and Baseline Budget |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 4.1: Ministry of Finance Circulars on Budget Strategy issued for years 2009 to 2012

Source: Ministry of Finance Circulars

The Budget Strategy describes the revenue, expenditure and policy measures to be adopted by

Government in attaining its broad fiscal policy objectives. To ensure the sustainability of Government’s debt

position, the Budget Strategy sets annual targets for Government’s debt levels. Government’s fiscal

strategy are developed for the medium term and focus on gradual budget deficits to attain a sustainable

debt level while simultaneously allocating adequate resources to raise growth, investment and essential

public services.

Since the allocation of resources is a critical input to the achievement of government’s growth targets, the

Budget Strategy include fiscal frameworks developed to enable the attainment of Government’s annual

targeted growth rates. For example, the fiscal framework included in the 2012 Budget Strategy as

illustrated in table 4.2 below sets the net deficit target at 3% of GDP for the 2012 Budget with gradual

reductions to 2.5% in 2013 and 2% by 2014, with anticipated results in declining debt levels from around

53.4% of GDP in 2012 to 50.4% within the medium term.

Table 4.2: 2012-2014 Fiscal frame work

Source: 2012 Budget Strategy - Ministry of Finance and Reserve Bank of Fiji

4.1.4	Following the dissemination of the Budget Strategy by the Ministry of Finance, Ministries and Departments

submit their operating expenditure proposals to the Ministry of Finance (MoF) Budget Division, and their

capital expenditure proposals to the Ministry of Strategic Planning, National Development and Statistics

(MSPNDS) within the stipulated timelines. Ministries with projects to be funded through direct payments

ensure that the total direct payments are within the approved expenditure envelope size for the Ministry.

PUBLIC DEBT MANAGEMENT	14

| Projections as per budget strategy | 2012 | 2011 | 2010 | 2009 |
| --- | --- | --- | --- | --- |
| Net deficit % of GDP | 3 | 3 | 3 | 2 |
| Debt to GDP ratio | 54 | 55.3 |  | 46.1 |
| Operating capital expenditure mix | 70:30 | 76:24 | 77:23 | 79:21 |
| Projections as per budget estimate | 2012 | 2011 | 2010 | 2009 |
| Net deficit % of GDP | 1.9 | 3.5 | 3.5 | 3 |
| Debt to GDP ratio | 53.4 | 54.5 | 56.2 | 55.8 |
| Operating capital expenditure mix | 73:28 | 72:28 | 80:20 | 80:20 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Consultations on the budget proposals are then held between central agencies and the MoF, the MSPNDS,

and the Public Service Commission (PSC). Further consultations are held at the ministerial level with the

Cabinet Sub Committee on the Budget (CSB), following which the Budget is finalized and tabled in Cabinet,

prior to being announced in November.

4.1.5	Audit noted that forecasted ratios as per the budget estimate over the 4 years 2009 to 2012 have been

forecasted in view of the budget strategies circulated. Refer table 4.3 below for details.

Table 4.3: Projected targets as per budget strategy and budget estimate

Source: Ministry of Finance circulars on budget strategy 2009-2012 and Budget Estimates 2009-2012 and Ministry of Finance Annual Debt Reports 2009-2012

The forecasted net deficit of 1.9% of GDP as per the 2012 budget estimate is well within the budget

strategy projection of 3.0% of GDP and the IMF’s recommended target of 2percent10, whilst forecasted net

deficits of 3.5% of GDP for 2010 and 2011 were slightly above the projections as per the budget strategy of

3.0% of GDP.

A downward trend was noted in forecasts of debt to GDP ratios. However, despite declining forecasted

debt ratio levels from 55.3% of GDP in 2011 to 53.4% in the 2012 budget, debt levels are still considered

unsustainable in view of the international “rule of thumb” which requires debt to be within 40% of GDP

thresh-hold.

A little more flexibility was noted in the forecasting of the operating to capital expenditure ratios in the

annual budget over the 4 years. Although the forecasted operating capital expenditure mix in the 2012

budget was more than the projected budget strategy ratio, it is much lesser than forecasted as per the

budgets for years 2009 and 2010, which is reflective of government’s efforts towards preventing the need to

borrow to finance recurrent expenditure and freeing up additional resources for capital expenditure and

debt repayment.

4.1.6	The budget estimate is supported by an annual Budget Funding Program (BFP) which provides an estimate

of total expenditure and revenue. The budget results (surplus/deficit) arising out of projected revenue and

expenditure together with projected debt repayments provide the basis for borrowing need, that is, a deficit

budget result would require borrowings by Government. The BFP also identifies sources of borrowings that

will finance the forecasted deficit. Reflected in table 4.4 are the forecasted budget results from the BFP and

the proposed sources of funding the budget results for the 5 years 2009 to 2013.

10 2012 Budget address page 2

PUBLIC DEBT MANAGEMENT	15

| Source of Loans | 2013 $ | 2012 $ | 2011 $ | 2010 $ | 2009 $ |
| --- | --- | --- | --- | --- | --- |
| OVERSEAS LOANS: Direct payment – International Bank Loan |  |  |  |  |  |
| ADB Loan No. 1530 FRUP III | 0 | 0 | 8,000,000 | 0 | 0 |
| ADB Loan No. 2541 Flood Recovery Loan | 15,000,000 | 0 | 0 | 0 | 0 |
| ADB Loan No. 2603 Supp. Suva Nausori | 13,000,000 | 15,000,000 | 10,000,000 | 0 | 0 |
| ADB Loan No. 2514 Supp. FRUP III | 10,000,000 | 18,000,000 | 22,000,000 | 0 | 0 |
| EXIM China Low Cost Housing Project | 13,000,000 | 10,000,000 | 10,000,000 | 0 | 0 |
| EXIM China Fiji Public Rental Housing Project | 6,000,000 | 6,000,000 | 6,000,000 | 0 | 0 |
| EXIM Malaysia Roads Rehabilitation Project | 40,000,000 | 45,000,000 | 30,000,000 | 0 | 0 |
| EXIM China Roads Improvement Project Sigatoka/ Serea | 22,000,000 | 22,000,000 | 8,000,000 | 0 | 0 |
| EXIM China Roads Improvement Project Buca/Moto | 24,000,000 | 24,000,000 | 9,000,000 | 0 | 0 |
| EXIM China Roads Nabouwalu – Dreketi Road Upgrading Project | 80,000,000 | 0 | 0 | 0 | 0 |
| EXIM Bank of Malaysia Nakasi – Nausori Widening | 15,000,000 | 0 | 0 | 0 | 0 |

| Description | 2013 $ | 2012 $ | 2011 $ | 2010 $ | 2009 $ |
| --- | --- | --- | --- | --- | --- |
| Expenditure | 2,327,385,300 | 2,077,929,300 | 1,961,718,300 | 1,706,597,500 | 1,715,225,400 |
| Revenue | 2,108,408,900 | 1,942,807,000 | 1,745,672,300 | 1,486,514,800 | 1,522,389,100 |
| Net deficit | 218,976,400 | 135,122,300 | 216,046,100 | 220,082,700 | 192,836,300 |
| Debt repayments | 179,997,000 | 203,314,500 | 518,755,400 | 276,806,700 | 329,644,500 |
| Gross deficit | 398,973,400 | 338,436,800 | 734,801,500 | 496,889,382 | 522,480,800 |
| Gross deficit to be financed from: |  |  |  |  |  |
| Overseas loans | 255,000,000 | 142,500,000 | 603,000,000 | 0 | 0 |
| Domestic loans | 143,973,400 | 195,936,800 | 131,801,500 | 496,889,400 | 522,480,800 |
|  | 398,973,400 | 338,436,800 | 734,801,500 | 496,889,400 | 522,480,800 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 4.4: Budget Funding Program

Source: original Budget Estimates 2009 - 2013

The audit noted that financing of gross deficits have been adequately identified. Annual deficits forecasted

for the years 2009 and 2010 were anticipated to be financed entirely through domestic loans. A significant

proportion of gross deficit for the years 2011 and 2013 were forecasted to be financed through overseas

borrowings, whilst 58% of deficit for 2012 was anticipated to be financed through domestic loans. The

forecasted budget deficit trend over the 5 years reflect a significant increase from 2010 to 2011 and

downward trend in 2012, and is attributed to the substantial provisions for debt repayments in 2011 which

included prepayments of 3 loans due in 2030 totaling $8.7million, and the repayment of bonds totaling

$500,000,000 in the international bond market.

4.1.7	To facilitate the deficit budget results the Debt Management and Cash Flow Unit (DCFMU) prepares and

submits to the Budget Division a Loan Funding Program (LFP) which identifies borrowing providers and the

amount to be drawn down from each provider, either domestically or externally. Listed in table 4.5 below

are annual anticipated borrowings as per the Loan Funding Program.

Table 4.5: Loan Funding Program

PUBLIC DEBT MANAGEMENT	16

| EXIM Bank of Malaysia Nadi – Denarau Road Widening | 15,000,000 | 0 | 0 | 0 | 0 |
| --- | --- | --- | --- | --- | --- |
| Total direct payments | 253,000,000 | 140,000,000 | 103,000,000 | 0 | 0 |
| Other overseas loans |  |  |  |  |  |
| ADB Loans – reimbursement to Government | 2,000,000 | 2,500,000 | 0 | 0 | 0 |
| International Bond Market | 0 | 0 | 500,000,000 | 0 | 0 |
| Total overseas loans | 255,000,000 | 142,500,000 | 603,000,000 | 0 | 0 |
| DOMESTIC LOANS |  |  |  |  |  |
| Fiji Development Loans | 143,973,400 | 195,936,800 | 131,801,500 | 496,889,400 | 522,480,800 |
| Total domestic loans | 143,973,400 | 195,936,800 | 131,801,500 | 496,889,400 | 522,480,800 |
| TOTAL | 398,973,400 | 338,436,800 | 734,801,500 | 496,889,400 | 522,480,800 |

|  | 2012 | 2011 | 2010 | 2009 |
| --- | --- | --- | --- | --- |
| Gross deficit | 334,436,800 | 734,801,500 | 496,889,400 | 522,480,800 |
| Financed by: |  |  |  |  |
| Overseas loans | 142,500,000 | 603,000,000 |  |  |
| Domestic loans | 195,936,800 | 131,801,500 | 496,889,400 | 522,480,800 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Source: Budget Estimates 2009 - 2013

The audit noted that whilst anticipated funding from domestic sources declined over the five year period,

anticipated sources of and total direct payments from overseas sources increased significantly, indicating a

dependence on overseas borrowings to fund its budget deficit. Of the projected borrowings for 2013, four

new loans were anticipated whilst eight were drawdowns of existing loans.

4.1.8	The structured budget process has enabled Government in determining its borrowing needs, and

adequately identifying sources of funds to meet its loan obligations in a sustainable manner for the current

and medium term.

4.2 Reliability of budget deficit estimation

4.2.1	The Minister must also table in the House of Representative and the Senate budget papers for an annual

budget for the next financial year on or before the 30th of November in each financial year11. The budget

papers for a financial year must comprise inter alia one or more budget statements, of which one is to

include the estimated budget result for the budget year (as surplus or budget deficit).

4.2.2	The estimated budget result determines the extent of government borrowings for any one year. Thus

Government provides for borrowings when a budget deficit is estimated since forecasted revenues are

insufficient to cover forecasted expenditure of Government for such periods.

4.2.3	A comparison of actual borrowings drawn down against forecasted borrowings to finance gross deficit as

per the budget estimate noted that actual borrowings were not reflective of forecasts made in the budget

estimate, with overall savings in budgets noted ranging from $33,924,297 (or 7%) in 2010 and

$142,245,965 (or 42.5%) in 2012, indicating a conservative budget approach. For details refer Table 4.2

below.

Table 4.6: Actual borrowings vs. estimated borrowings to fund budget deficit

11 Financial Management Act 2004 s.13

PUBLIC DEBT MANAGEMENT	17

| Actual borrowings |  |  |  |  |
| --- | --- | --- | --- | --- |
| Overseas loans | 91,587 | 569,043,119 | 10,231,002 | 1,149,982 |
| Domestic loans | 192,099,248 | 81,470,524 | 452,734,100 | 404,239,758 |
| Total borrowings | 192,190,835 | 650,513,643 | 462,965,103 | 405,389,740 |
| Variance in actual borrowings against estimated borrowings | (142,245,965) | (84,287,857 | (33,924,297) | (117,091,060) |
| Percentage variance | 42.5% | 11% | 7% | 22.4% |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Source: Ministry of Finance Budget Estimates 2009-2012

Actual borrowings drawn from domestic sources in 2009 and 2010 were less than forecasted by

$118,241,042 (or 22.6%) and $44,155,300 (or 8.9%) respectively. In addition loans of $1,149,982 and

$10,231,002 were drawn down from overseas borrowings despite forecasts in the budget estimates that

gross deficit would be financed entirely by domestic loans for the years 2009 and 2010.

4.2.4	The audit noted that actual borrowings incurred to finance anticipated deficits for 2011 and 2012 were less

than forecasted borrowings by 11% and 42.5% respectively, indicating overstated budget results. It was

noted that actual overseas borrowings recognized in the consolidated fund in 2012 were significantly less

than forecasted by $142,408,413 (or 99.9%) and is attributed to non-inclusions of direct cash disbursed to

contractors, non-cash loans and other loan payables (interest and commitment fee) due even though they

were provided for in the budget and are being serviced by government. Direct cash disbursements to

contractors and related transactions incurred, these are $137,460,945 in 2012, $51,718,514 in 2010 and

$24,326,851 in 2009, which are disclosed as notes in the whole of Government’s accounts.

4.2.5	Misstatements of budget results impact on estimation of borrowing needs of Government, that is, growing

public debt and its servicing costs could lead to severe debt burden to the economy in future if not

managed properly.

4.3 System for determining debts due

4.3.1	The Debt Management & Cash Flow Unit (DCFMU) is responsible for producing the Government’s Head 52

forecasts for principal repayments of loans and interest payments on loans for inclusion in the annual

Budget Estimate.

4.3.2	The DCFMU uses the Commonwealth System–Debt Repayment Management System (CS-DRMS) to

record and report all government debt related data. Amounts to be repaid are determined from the External

Debt Repayment Schedule generated from the CS-DRMS as well as from the amortisation schedule as per

the Loan Agreements.

4.3.3	A comparison of actual expenditures against forecasted expenditures for charges on account of public debt

over the four years 2009 to 2012 revealed significant variances. Refer to Appendix 1.0 for details of interest

and principal repayments provided under Head 52 and the actual debt servicing paid out for years 2009 to

2012.

As can be noted from table in Appendix 1, significant savings were recorded for principal repayments for

overseas borrowings in 2009 by 68.9%, in 2010 by 58.5%, and in 2012 by 19.1%. Substantial savings were

PUBLIC DEBT MANAGEMENT	18

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

also noted for interest payments for treasury bills by 34.2%, 58.37% and 78.7% over the same period

respectively.

Also domestic loan interest payments for 2009 and principal repayments for domestic loans for 2012

exceeded forecasted expenditures by $8,620,307 (or 5.5%) and $45,020,000 (or 24.56%) respectively.

4.3.4	Forecasted overall debt servicing in 2012 decreased by $320,022,000 from 2011. However actual overall

debt servicing for 2012 exceeded forecasts and is attributed to redemptions of domestic borrowing

exceeding forecasts by $45,020,000 (or 24.56%).

4.4 Estimation of contingencies

4.4.1	One of the five principles of responsible financial management is to manage contingent liability in a prudent

manner12. The Minister must table a strategic policy statement in the House of Representative on or

before the 30th of June in each financial year13, which must include amongst other things a statement of the

Government’s financial targets or limits for the next financial year and for the following two financial years,

relating to contingent liabilities as a proportion of gross domestic product.

A register of contingent liabilities must be maintained and must include information with respect to the

description of the contingent liability; its value (if it can be reliably measured); the way in which the

contingency arose; details of any action required to minimise the potential loss; and details of progress in

managing the risk14.

4.4.2	As part of the budget formulation process, Strategic Policy Statements (SPS) prepared by the Ministry of

Finance and submitted to Cabinet (in the absence of Parliament) by the 30th of June of the preceding

financial year include the fiscal targets relating to levels of contingent liabilities for the coming year, and the

two following financial years. The actual/projected results for the previous two financial years are also

included for purposes of comparison and trend analysis.

Fiscal targets for government contingent liability portfolios for 2011 to 2014 have been set to be contained

at below 35% of GDP15 as per each respective year’s ACP.

4.4.3	The audit also noted that the Annual Budget Strategy disseminated by the Ministry of Finance to all

government entities identifies contingent liabilities as one of the significant risks to Fiji’s economy. It

discloses that the Ministry finds the increasing size of contingent liabilities and government guarantees of

significant concern, as it represents potential claims that have not materialised but could prompt immediate

financial obligation from Government16. Reflected in table 4.7 below are the contingent liabilities of

Government’s for the five years 2009 to 2012.

12 Part 2 s.5(d) Financial Management Act 2004

13 Financial Management Act 2004 s.12

14 Finance Instruction 2010 s.56

15 Ministry of Finance Annual Corporate Plans 2011, 2012, 2013, 2014

16 Finance circular No. 8/2011 para. 4.2(vi)

PUBLIC DEBT MANAGEMENT	19

| Year | Budget Provision $ |
| --- | --- |
| 2009 | 915,800 |
| 2010 | 915,800 |
| 2011 | 1,802,000 |
| 2012 | 1,000,000 |
| 2013 | 1,000,000 |

|  | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- |
| Total contingent liabilities | 1,963,068,505 | 1,791,461,261 | 1,931,795,891 | 2,155,254,122 |
| Contingent liability to GDP (%) | 34.3% | 29.4% | 28.7% | 28.8% |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 4.7: Contingent liabilities

Source: Schedule 5 to Whole of Government Financial Statements for years 2009 to 2012

Although minor fluctuations were noted in the fiscal targets of contingent liabilities expressed as a

percentage of GDP over the three years 2010 to 2012, contingent liability has increased steadily by 7.8% to

11.5% in 2011 and 2012 respectively.

4.4.4	In recognising the potential risks to government’s financial position should agencies default on their

repayment obligations, provisions for contingent liabilities have been made in the annual budget estimate.

Provisions in the annual budget estimate, as provided by the DCFMU for the last five years 2009 to 2013

are reflected in Table 4.8 below.

Table 4.8: Provision for contingents in Budget Estimate

Funds in the Budget Estimate are to cater for any contingent liability, and are not provided specifically for

explicit or implicit guarantees. Implicit guarantees is assurance given by Government on the financial

liability of an entity in respect of a loan or otherwise in the domestic market as well as externally, as

approved by Cabinet. Explicit guarantees are assurances given by Government without deeds of guarantee

with the other entity such as guarantees of member contributions in the Fiji National Provident Fund,

customer deposits in the National Bank of Fiji, and subscriptions held with international Agencies’

Securities accounts.

However, Government has only utilised funds provided in the 2010 annual Budget totalling $500,000. The

inability of the Fiji Sports Council in meeting their loan obligations with the ANZ Bank led government to

meet the default.

4.4.5	Furthermore section 6.3 of the Government Guarantee Policy 2013 requires the Ministry of Finance to

create a Sinking Fund where all proceeds from guarantee fees are to be deposited. Proceeds deposited in

the sinking fund are to be used to support payment of guaranteed loans in the event of defaults. However

this has yet to eventuate.

4.4.6	Expressing fiscal target levels of contingent liabilities as a percentage of gross domestic products (GDP)

provides an indicator of the sustainability of the Government's fiscal intentions in relation to the size of the

economy as a whole. The higher the percentage the greater the size/impact the public sector has on the

economy.

PUBLIC DEBT MANAGEMENT	20

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

RECOMMENDATIONS

The Ministry of Finance should:

	Introduce strategies that will reduce the total debt to GDP ratio and maintain it below the 40% threshold as

required for developing economies such as Fiji.

	be more prudent and thorough and in its assessment of submissions from stakeholders during the budget

formulation as outcomes of all submissions from stakeholders determine the budget deficit, and consequently

government borrowing needs.

	ensure that the budget system focuses more on reducing the variance between estimated and actual budget so

that fiscal deficit is kept at minimal level.

	make adequate provisions during the budget process for its debt servicing costs.

Management Comments

The current debt strategy implemented by the Ministry of Finance is to maintain the debt level to GDP ratio below 50% and

eventually target 45% in the medium term. However, debt levels are rarely technical decisions implemented by the Ministry

but politically driven by the Government of the day to cater for deficit funding. It should be noted that Debt to GDP is not the

only indicator to assess debt sustainability. There are other indicators that need to be considered such as Debt to Total

Exports, Debt to Foreign Reserves, Debt to Total Government Revenue etc.

Prudent and thorough assessments of submissions from stakeholders during the budget formulation are undertaken by the

Budget Division of the ministry. Thus, the under-utilization of total expenditure estimates of government during a year are

mainly due to the failure of Ministries & Departments in fully utilizing their respective budgets allocated for the year.

Furthermore, it is to be noted that Table 4.6 is incorrect as it excludes direct payments in 2012. The overseas borrowing

estimates are based on the respective line Ministries estimations on expected completion of projects and funding requirement

within a year; however variances are incurred due to delays in project execution owing to unforeseen circumstances which

are beyond the ministry’s control.

Proper consultations are always conducted by the Ministry during the budget formulation. The government currently

espoused policies which are focused on infrastructure developments, as well as undertake reforms that requires budget to

cater for expenditure forecasts as required by ministries/departments. The Ministry will ensure that ministries and

departments expedite utilization of budgets allocated to them.

Further OAG Comments

Figures reflected in Table 4.6 are extracts from the Annual Budget Estimate of Government for the years 2010 to 2012.

Direct disbursements are not included as they have not been received by Government and subsequently not included in the

Government’s financial statement but are disclosed only as notes to the accounts as explained in paragraph 4.2.4 of the

report.

PUBLIC DEBT MANAGEMENT	21

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.0 PUBLIC DEBT REPORTING

This section of the report discusses findings on whether public debt information have been reported as

required, and whether the reports are subject to external audits.

5.0.1	Reporting transparently in accordance with relevant accounting and statistical standards is one of the

principles of responsible financial management.17

5.0.2	Clear and explicit legal reporting requirements such as financial statements, budgetary reports, and public

debt reports, should exist to hold public debt managers accountable to senior debt officials and ministers

charged with governance and to the Cabinet (in the absence of Parliament).

5.1 Statutory reporting requirements of public debt

5.1.1	The Minister must table in the House of Representatives a mid-year fiscal statement for the first 6 months

of each financial year18 which must include a statement for the whole of government, specifying:

	the total revenue and total expenditure, and the surplus or deficit, for the period of 6 months,

compared with the revenue and expenditure, and the surplus or deficit, for the corresponding

period of the previous financial year19;

	the projected total revenue and total expenditure, and the projected surplus or deficit, for the

financial year, compared with the actual revenue and expenditure, and surplus or deficit for the

previous year20.

The Minister must also table a whole of government (WoG) annual report for each financial year within 9

months after the end of each year, and which must include21:

	the whole of government financial statements;

	the annual appropriation statement; and

	the annual budget statement.

The Chief Executive Officer of the Ministry of Finance is responsible for the preparation of the whole of

government annual report and the statements required to be included in them22.

5.1.2	The audit observed that the Ministry of Finance has met its statutory reporting requirements for the years

2009 to 2012. The WoG annual report for financial years 2009 to 2012 submitted for audit includes

amongst other things a statement of assets and liabilities, including details of cash balances, investment,

17 Financial Management Act 17 of 2004 s.5(e)

18 Financial Management Act 17 of 2004 s. 44(1)

19 Financial Management Act 17 of 2004 s. 44(3) & (5)(a)

20 Financial Management Act 17 of 2004 s. 44(3); & (5)(b)

21 Financial Management Act 17 of 2004 s. 45(1)(2)(3)

22 Financial Management Act 17 of 2004 s. 45(4)

PUBLIC DEBT MANAGEMENT	22

| Year | Date audit opinion issued | Date WoG statement signed by PSF |
| --- | --- | --- |
| 2009 | th 20 September 2010 | th 17 September 2010 |
| 2010 | th 19 October 2011 | th 12 October 2011 |
| 2011 | th 19 September 2012 | th 12 September 2012 |
| 2012 | th 17 September 2013 | September 2013 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

sinking funds and borrowings; and a statement of contingent liabilities as required under section 46(1)(b) of

the Financial Management Act 17 of 2004.

The WoG financial statements signed by the Permanent Secretary for Finance (PSF) has been submitted

to the Office of the Auditor General for audit within 9 months after the end of each respective financial year

as required. The WoG financial statements for the years ended 2009 to 2012 also contain the audit opinion

issued by the Office of the Auditor General as required under section 46(2) of the Financial Management

Act 17 of 2004. The Auditor General issued opinions on the WoG financial statements on the following

dates as reflected in table 5.1 below.

Table 5.1: Dates of signing WoG statements and issuance of audit pinions

Source: Whole of Government Financial Statements for 2009, 2010, 2011, 2012

Issue of the audit opinion on the WoG financial statements for year ending 2010 was delayed due to

“implosions” in the Ministry of Finance’s Financial Management Information System (FMIS).

5.1.3	The annual appropriation statement is also included in the WoG annual report for the financial years ending

2009 to 2012. As required under section 47 (1) of the FMA 2004, the annual appropriation statements

disclosed:

	the actual revenue and expenditure, and surplus or deficit, for the financial year;

	the corresponding revenue estimates and appropriations for the financial year; and

	details of reportable authorisations relating to the financial year.

5.1.4	Also included in the WoG annual reports for the years 2009 to 2012 is the annual budget statement.

Disclosures in the respective annual budget statements were in accordance with section 48 (1) of the FMA

2004, and:

	showed the revenue, expenditure, and surplus or deficit, for each of the 2 previous financial years;

	showed the estimated revenue, expenditure, and surplus or deficit, for the financial year;

	showed the projected revenue, expenditure, and surplus or deficit, for the next 2 financial years;

	provided a disaggregation of revenue, estimated revenue, and projected revenue by economic

type;

	provided a disaggregation of expenditure, estimated expenditure, and projected expenditure by

economic type;

	included a statement comparing for each type of financial target, or limit specified in the most

recently tabled strategic policy statement that target or limit any revisions specified in the budget

statement, and the actual results.

5.1.5	The data disclosed are complete, reliable, accurate and consistent as they have been audited by the Office

of the Auditor General and certified with accompanying opinion as reflected in table 5.1 above.

PUBLIC DEBT MANAGEMENT	23

| Year | Date published |
| --- | --- |
| 2009 | undisclosed |
| 2010 | May 2011 |
| 2011 | January 2012 |
| 2012 | January 2013 |
| 2013 | January 2014 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.2 Government debt reports

5.2.1	The Minister of Finance is responsible for managing the financial affairs of the Government as a whole in

accordance with the requirements of the Financial Management Act and with due regard to the principles of

responsible financial management23. One of the principles of responsible financial management is to report

transparently in accordance with relevant accounting standards and statistical standards24.

The Debt Management & Cash Flow Unit (DMCFU) is required to present the annual debt report to Cabinet

by March of each year25.

5.2.2	The Debt Management & Cash Flow Unit of the MOF uses the CS-DRMS to record and report all the

government debt related data. The CS-DRMS system enables the Unit in formulating the quarterly and

annual government debt reports.

The CS-DRMS is an integrated tool for recording, monitoring, analysing and reporting public debt which is

constantly evolving to match the ways in which debt management is reshaping itself. The CS-DRMS helps

MOF in minimizing risks within their debt portfolios and achieves savings through lower debt servicing

payments while assisting the government in bringing the debt burden to manageable levels through the

analysis of the impact of debt relief and restructuring.

However, the current version of the CS-DRMS used by MOF has not been updated from the 2006 version.

As a result, the full potential of the CS-DRMS could not be used. The audit noted the following international

debt report limitations:

1. Reporting on internationally accepted practices such as IMF’s Special Data Dissemination Standard

(SDDS), Quarterly External Debt Statistics (QEDS) and World Bank’s Debtor Reporting System (DRS)

2. Report writing tool for developing country specific reports Commonwealth Secretariat Debt Recording

and Management System (CS-DRMS)

5.2.3	Government Debt Reports are prepared by the DMCFU on a quarterly and annual basis. Quarterly reports

are submitted to the Debt and Cash Flow Policy Committee on the 10th day of the month following the

quarter for their internal deliberations. Annual government debt reports for the 5 years 2009 to 2013

prepared and submitted to Cabinet were published on the dates referred to in table 5.2 below.

Table 5.2: Date of publishing debt reports

Source: Government Debt Reports 2009-2013

23 Financial Management Act 17 of 2004 s.6

24 Financial Management Act 17 of 2004 s. 5(e)

25 Ministry of Finance Annual Corporate Plans 2012,2013

PUBLIC DEBT MANAGEMENT	24

|  | 2009 | 2010 | 2011 | 2012 | 2013 |
| --- | --- | --- | --- | --- | --- |
| Government debt | 3,132.2 | 3,383.2 | 3,566.5 | 3,679.5 | 3,825.3 |
| Domestic | 2,605.0 | 2,834.7 | 2,734.4 | 2,744.0 | 2,744.2 |
| External | 527.2 | 548.5 | 832.1 | 935.5 | 1,081.1 |
| Total Debt % of GDP | 55.8% | 56.2% | 54.5% | 53.4% | 49.1% |
| Domestic to total debt | 83.2% | 83.8% | 76.7% | 74.6% | 71.7% |
| External to total debt | 16.8% | 16.2% | 23.3% | 25.4% | 28.3% |

| Debt instrument | 2009 | 2010 | 2011 | 2012 | 2013 |
| --- | --- | --- | --- | --- | --- |
| Bonds | 2,505.0 | 2,759.0 | 2,663.0 | 2,622.0 | 2,635.0 |
| T-bills | 99.9 | 75.4 | 71.1 | 112.4 | 102.6 |
| Loan |  |  |  | 9.5 | 6.3 |
| Total domestic debt | 2,605.0 | 2,834.7 | 2,734.4 | 2,744.0 | 2,744.2 |
| % of GDP | 46.4% | 47.1% | 41.8% | 39.8% | 35.2% |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

The above annual Government debt reports and those for the years 2007 and 2008 are available to the

public on the Ministry of Finance’s website.

5.2.4	Comparisons of Government debt reports prepared for the years 2009 to 2013 revealed transparency and

consistency in disclosures of government’s debt portfolio.

The debt reports disclosed information pertaining to Government’s debt position, Government’s domestic

debt, and Government’s external debt. Other disclosures included debt servicing forecasts, Government

guarantee exposures, major highlights in the year; opportunities, and a summary on the performance of

government’s debt portfolio for each year.

5.2.5	Total debt stock is classified as either external or domestic borrowings (i.e. residency), with debt ratio

expressed as a percentage of GDP. Residency classification of debt is also expressed as a percentage of

total debt. Comparative data is provided over a 5 year period. Refer to table 5.3 for disclosures in the

Government’s Debt Report for 2013.

Table 5.3: Total debt stock for the years 2009 to 2013

Source: Government Debt Report for year ending December 2013, MoF

It is noted from the above table that increase in government debt over the five years period is attributed

mainly to increased external borrowings. However total debt to GDP ratio has decreased gradually from

55.8% in 2009 to 49.1% at the end of 2013 indicating that the economy is growing faster than its borrowing

activities.

5.2.6	Domestic debt is further classified by instruments. Refer to table 5.4 below for details.

Table 5.4: Domestic debt stock by instrument for the years 2009 to 2013 (million)

Source: Government Debt Report for year ending December 2013, MoF

The debt report also discloses information of composition of debt holder for each classification of debt

instrument. Details are provided in table 5.5 below.

PUBLIC DEBT MANAGEMENT	25

| Debt instrument | Total debt holdings as at 31.12.13 $million | Non bank financial institutions | Commercial banks | Reserv e Bank | Others | Government |
| --- | --- | --- | --- | --- | --- | --- |
| Bonds | 2,635.3 | 93% | 2% | 3% | 2% |  |
| T-bills | 102.6 | 63% | 37% |  |  |  |
| Loan(government guarantee realised) | 6.3 |  |  |  |  | 100 |
| Total domestic debt | 2,743.6 |  |  |  |  |  |

| Debt instrument | 2010 | 2011 | 2012 | 2013 |
| --- | --- | --- | --- | --- |
| External DOD Central Government | 548.5 | 832.1 | 935.5 | 1,081.1 |
| Total External debt Service of which | 41.3 | 331.5 | 65.6 | 69.3 |
| Principal payment | 17.6 | 285 | 19.3 | 19.7 |
| Interest payments | 23.7 | 46.5 | 46.3 | 49.6 |
| External debt to GDP ratio | 9.4% | 12.1% | 13.6% | 13.9% |
| External debt Service as % age of export of goods | 2.6% | 17.3% | 3.0% | 3.1% |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 5.5: Domestic debt by holder category 2013

Source: Government Debt Report for year ending December 2013, MoF

Loans under domestic borrowing are the amount realised by Government for a government guaranteed

loan by the Fiji Sugar Cane Growers Council.

Domestic debt servicing is presented graphically and shows trends in debt servicing costs but does not

attach a dollar value to it.

5.2.7	The debt report presents information on external debts by disbursed outstanding debt at year end. Refer

table 5.6 below.

Table 5.6: Government External Disbursed Outstanding Amount 2010 to 2013(million)

Source: Government Debt Report for year ending December 2013, MoF

The increase in debt servicing in 2011 is attributed to the settlement of the global Bond of US$150 million, a

trend that is expected to continue until the redemption of the second global bond in 2016.

The debt report also provides a breakdown of annual external loan disbursements by lenders.

Composition of external debt is presented in the debt report by creditor categories as well as by economic

sectors.

5.2.8	There is a risk that users of the report may not have been consistently informed of key aspects of public

debt over the years

5.3 Reporting of contingent liabilities

5.3.1	The whole of government financial statements required to be included in the whole of government annual

report for a financial year must include for financial years where the Minister is satisfied that relevant

reliable accrual information is not available, amongst other things, a statement of contingent liabilities26.

26 Financial Management Act 17 of 2004 s.46(1)(b)(iii)

PUBLIC DEBT MANAGEMENT	26

| Year | Report Date |
| --- | --- |
| 2010 | June 2011 |
| 2011 | June 2012 |
| 2012 | April 2013 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.3.2	Although the Ministry’s corporate planning documents do not provide for the submission of report on

contingent liabilities, the DCFMU prepares the Contingent Liability Reports each year.

5.3.3	Audit verifications established that the reports presents trends in government guarantees provided over a

five year period. It also provides brief analysis of the types of guarantees provided to each entity and how

funds are utilised. The report also discloses risk and challenges to government, and proposed strategies

and recommendations to be undertaken by government in order to strengthen the supervision and

monitoring of risks associated with guaranteed entities.

5.3.4	Our audit however found that there is no defined timeline as to when the reports are to be produced by the

Unit. No evidence of the timeline was indicated in the Ministry’s ACP. As a result there were variations in

the time the reports were finalised. Refer to the following table for the time the reports were prepared by the

Unit over the last three years. Reflected in table 5.7 below are reports published on contingent liabilities for

the years 2010 to 2012.

Table 5.7: Government Contingent liability reports for 2010-2012

5.3.5  	The audit noted that the Government Contingent Liability Report is submitted to the Minister of Finance and

made available within the Ministry but is not made available on the Ministry’s website as in the case of

Government Debt Report.

5.3.6	Review of the past five years contingent liability reports found that there were differences in the amount of

contingent liability reported for specific years. Refer to the table 5.8 for details.

PUBLIC DEBT MANAGEMENT	27

| Entities | 2010 Government Contingent Liability Report ( $ million) |  |  | 2011 Government Contingent Liability Report ($ million) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2008 | 2009 | 2010 | 2009 | 2010 | 2011 |
| Fiji Development Bank | 347.1 | 358.7 | 237.2 | 358.7 | 322.9 | 257.2 |
| Fiji Electricity Authority | 235.8 | 354.3 | 356.6 | 354.3 | 346.5 | 353.9 |
| Fiji Hardwood Corporation | 12.6 | 13.2 | 17.1 | 13.2 | 17.2 | 16.6 |
| Fiji Pine Limited | 11.9 | 8.1 | 6.2 | 8.1 | 8.4 | 13.7 |
| Fiji Sugar Corporation | 65.2 | 140.3 | 127 | 140.3 | 121.9 | 116.4 |
| Housing Authority | 90.2 | 87 | 96.1 | 87 | 86 | 82.6 |
| Pacific Fishing Company Limited | 3.4 | 2.8 | 0 | 2.8 | 5.4 | 5.4 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

Table 5.8: Differences in contingent liability

Entities

2012 Government Contingent

Liability Report ($ million)

2013 Government

Contingent Liability Report

($million)

2010	2011	2012	2011	2012	2013

Fiji Development Bank	322.9	257.2	250	257.2	250	190

Fiji Electricity Authority	346.5	353.9	323.5	353.9	323.5	297.9

Fiji Hardwood Corporation	17.2	16.6	15.9	16.6	16	15.3

Fiji Pine Limited	8.4	13.7	16.9	13.7	17.1	13.5

Fiji Sugar Corporation	121.9	116.4	117.9	116.4	111.8	156

Housing Authority	86	82	105.4	82.6	105.5	79.8

Limited          	5.4

Pacific Fishing Company

5.4     3.2     5.4     1.4     2.8

Source Ministry of Finance Contingent Liability Report

It can be gathered from the table that incorrect amounts of contingent liabilities were reported in 2010 and

2012 for the indicated agencies.

5.3.7	The differences in recording of the amount reflected in the table above indicate that no proper checks were

conducted by the Debt and Cash Flow Management Unit prior to the report being finalised. In addition, the

absence of defined timeline in the preparation of the contingent liability report suggests that there is no

urgency in determination of the amount and as such evaluations of potential risks of the liability to

government finances are not conducted in a timely manner.

Furthermore, the non-publishing of the contingent liability report by the Ministry in its website reflects lack of

transparency in reporting such key information.

PUBLIC DEBT MANAGEMENT	28

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

5.4 Mechanism for implementing agencies to regularly report to

Ministry of Finance

5.4.1	The Ministry of Finance should have a mechanism in place that requires implementing agencies to report

on their servicing of debt which the government has guaranteed.

5.4.2	Section 6 of the government guarantee supplementary agreements sets out the requirements of the types

of information to be provided by a guaranteed entity concerning the guarantees issued. The following

requirements are set out under section 6.0 of the agreement:

Within 30 workings days for the period ending 30th June and 31st December each year while this

Agreement is in force, the Authority shall provide a comprehensive report to the Minister on the operation of

the guarantee finance for the half-year. Each report must detail:

a.	All borrowing proposals which might involve a guarantee from Government;

b.	Provision of Progressive Repayments or Prepayments;

c.	Statement of Finance Performance;

d.	Statement of Annual Financial Position;

e.	Security of Guarantee- Debenture on the guaranteed entity;

f.	Statement of Cash flow;

g.	A documentary on the current and future soundness of the entity;

h.	Business and Corporate plan;

i.	Reform Plans; and

j.	Early notification (3 month prior) of any such or foreseeable circumstances which could jeopardise

the performance of the Authority in debt servicing or other loan covenants.

Section 7.01 of the contractual agreements also provides the actions to be taken by government in case of

breach of its clauses.

5.4.3	The audit noted that the requirements for reporting as per the contractual agreement facilitate the

preparation of the annual Contingent Liability report by the DCFMU. Therefore it is vital that the government

guaranteed entity provides all information as per section 6 of the government guaranteed agreement on a

timely basis.

5.4.4	An audit carried out on the reporting requirements noted several anomalies. Refer to the following for

further details of the anomalies identified.

	Whilst the requirements are clearly set out in the guarantee agreement for the guaranteed entity to

submit information relating to government guarantee, observations found that the supply of

information from the entities were not forthcoming. The audit noted that each year the Ministry of

Finance has to formally write to the various guaranteed entities to remind them to provide the

required information. As a result the Debt Management Unit found it difficult to validate information

relating to guarantees, in particular the amount to be reported under Schedule 5 of the WoG

Annual Financial Statement of the Statement of Contingent Liabilities.

PUBLIC DEBT MANAGEMENT	29

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

	The guarantee agreement requires entities to provide the Ministry of Finance with information or

details concerning security of guarantee; current and future soundness of the entity and details of

any foreseeable circumstances, which could jeopardise the performance of the entity in debt

servicing or other loan, covenants. However, the agreement does not specify the format and the

specific supporting details for this information.

	The guarantee agreement also requires that the guaranteed entity to send in reports including the

Statement of Financial Performance, Statement of Cash Flows and Statement of Annual Financial

Positions. These reports are required to be provided on an half yearly basis suggesting the reports

are unaudited.

5.4.5	The findings indicate that there is difficulty in enforcing the contractual requirements of reporting by

agencies whose loans government have guaranteed.	In addition, the requirement of submission of

unaudited financial statement may have an impact on the Ministry making an accurate evaluation of the

financial performances of these agencies to meet loan obligations which government is guaranteeing.

RECOMMENDATIONS

The Ministry of Finance should:

	work towards upgrading the version of the CS-DRMS.

	work towards developing a format which will standardize the format of the debt report.

	make the Government Contingent Liability report available on its website for public information and for transparency

purposes.

	set a fixed timeline for the submission of the Contingent Liability report.

	enforce the penalty clause of the contractual agreement if agencies do not comply with the reporting requirements.

	specify the format to which information relating to security of guarantee, documentary evidence on the current and

future soundness of the entity and the information requiring early notification of any such foreseeable circumstances

which would jeopardise the performance of the company in debt servicing and other loan covenants.

Management Comments

The CS-DRMS has been upgraded in May, 2014 by the Commonwealth Secretariat Consultant from Version 1.1.2 to

Version 1.3.

The Debt report has been structured to consistently provide reliable information to users on the government debt portfolio.

The Debt unit strives to continuously improve its reporting and with the help of technical assistance will include more

financial indicators to ensure long-term debt sustainability within the debt report.

The Ministry will make the Contingent Liability Report available on the website upon endorsement by Cabinet.

PUBLIC DEBT MANAGEMENT	30

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

The Contingent Liability report is produced after the receipt of updates from the respective guaranteed entities. The

timeliness of the report is contingent on timely submission from the respective entities. The Ministry will incorporate an

appropriate timeline for submission of Contingent Liability Report into its Annual Corporate Plan after consultation with

management.

The issues of enforcement should be viewed from a holistic perspective, some entities are in dire straits and imposing

penalties will further exacerbate the entities problems. It should be noted that these companies have got social obligations to

fulfill and more than 200,000 people depend on it directly and indirectly. However government is steadfast in implementing

the penalties once all the entities are performing to expectations and the planned reforms are duly implemented.

The Ministry conducts financial analysis on guaranteed entities which includes information relating to securities and current

and future soundness. The Ministry conducts regular site visits which includes detailed discussion with management on its

plans to repay debt on timely basis and strategic decisions relating to improving the overall business performance.

PUBLIC DEBT MANAGEMENT	31

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

6.0 CONCLUSION

6.1	Government borrowing needs have been determined in view ultimately of long term sustainability and

financial stability. Borrowing needs of government are identified through its structured annual budgetary

process and its quantum determined by the magnitude of the annual budget deficit. Borrowing needs have

been forecasted or planned as close as possible to annual budget strategies developed by Government to

ensure public debt is kept at sustainable levels over the medium term. However there are inefficiencies in

the budgetary process. Impairments noted in the estimation of government borrowing needs are attributed

to the conservative approach to determining the annual budget. Debt servicing requirements have been

adequately met over the four years except for overspending of provisions for domestic borrowings principal

and interest payments in 2012 and 2009 respectively, and short term financing in 2010 and 2012.

Provisions to meet contingent liabilities have been adequately provided for in the annual budget, as

Government has been able to meet its debt servicing commitments on occasions when government

guarantees have been called on. Although actual government borrowings are above expected international

fiscal targets of 40% of GDP, they are still within the Government’s annual forecasted fiscal targets, and

have also decreased gradually over the years.

6.2	Public debt and contingent liabilities of government are adequately reported as required under the Financial

Management Act 2004. The accuracy and reliability of the reporting of public debt and contingent liability is

enhanced by the auditing of records of borrowings. However since Government adopts cash basis of

accounting, only borrowings received in cash are included in the consolidated fund account of government.

Direct disbursements to contractors, non-cash loans and other payables due are not included but disclosed

only as footnotes in the financial statements of government.

6.3	The CSDRMS is an effective system of recording public debt and producing information pertaining to debt

servicing requirements that is utilised by the DCFMU. However it is yet to realise its optimal potential of

automating production of the debt reports. Annual debt reports have been prepared with sufficient

disclosures of information and indicators on public debt and contingent liabilities and their sustainability.

PUBLIC DEBT MANAGEMENT	32

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

7.0 REFERENCES

1.	DEMPA. Debt Records and Reporting. Debt Management Performance Assessment Tool. 3-4 December

2008

2.	Dr. Enrique Cosio-Pascal. UNITAR e-Learning Course on, Audit of Public Debt: Introduction and

Institutional Framework. 2009

3.	International Monetary Fund and the World Bank. Guidelines for Public Debt Management, 2003

4.	International Monetary Fund, Republic of Fiji 2012 – Country Report No. 13/370. 2013

5.	Mahendra Reddy. Assessing Sustainability of Fiji’s Public Debt: A Cointegration Analysis Approach.

University of the South Pacific. 2006

6.	Ministry of Finance. Annual Corporate Plan. Suva, Fiji: 2010-2014

7.	Ministry of Finance. Annual Debt Report. Suva, Fiji: 2009-2013

8.	Ministry of Finance. Debt Management Strategies. Suva, Fiji: 2013

9.	Ministry of Finance. Debt Policy – Medium Term Strategy in the Budget Supplement.The Government

Printer. 2013

10.	Ministry of Finance. Economic and Fiscal Update: Supplement to the 2013 Budget Address. The

Government Printer. 2012

11.	Ministry of Finance. Government Contingent Liability Report. Suva, Fiji: 2010-2013

12.	Republic of Fiji. Financial Management Act 2004. Suva, Fiji. Fiji Government Printer.

13.	T.K.Jataraman and Chee-Keong Choong. Public Debt and Economic Growth in the South Pacific Islands: A

Case Study of Fiji. The University of the South Pacific and Universiti Tunku Abdul Rahman. 2006

14.	The International Standards of Supreme Audit Institutions. Guidance on Definition and Disclosure of Public

Debt. 2006

15.	The International Standards of Supreme Audit Institutions. Guidance for Conducting a Public Debt Audit –

The Use of Substantive Tests in Financial Audits. 2007

PUBLIC DEBT MANAGEMENT	33

| 2012 | Estimate | Actual | Variance Savings/overspent $ | Percentage variance Savings/(overspent) % |
| --- | --- | --- | --- | --- |
| Interest payments |  |  |  |  |
| Overseas | 51,437,500 | 49,322,771 | 2,114,729 | 4.1 |
| Domestic | 211,662,900 | 210,534,849 | 1,128,051 | 0.53 |
| Treasury bills | 4,000,000 | 850,851 | 3,149,149 | 78.7 |
|  | 267,100,400 | 260,708,471 | 6,391,929 | 2.39 |
| Principal repayments |  |  |  |  |
| Overseas | 20,066,500 | 16,215,884 | 3,850,616 | 19.18 |
| Domestic | 183,248,000 | 233,268,000 | (45,020,000) | (24.56) |
|  | 203,314,500 | 249,483,884 | (41,169,384) | (20.24) |
| Miscellaneous & short term financing | 1,150,000 | 152,448 | 997,552 | 86.74 |
| Total debt servicing | 477,564,900 | 510,344,803 | (33,779,903) | (7.07) |
| 2011 | Estimate | Actual | Variance |  |
| Interest payments |  |  |  |  |
| Overseas | 45,048,700 | 43,104,766 | 1,943,934 | 4.31 |
| Domestic | 220,373,400 | 213,248,464 | 7,124,936 | 3.23 |
| Treasury bills | 5,000,000 | 2,081,244 | 2,918,756 | 58.37 |
|  | 270,422,100 | 258,434,474 | 11,987,626 | 4.43 |
| Principal repayments |  |  |  |  |
| Overseas | 305,375,400 | 291,113,603 | 14,261,797 | 4.67 |
| Domestic | 213,380,000 | 213,380,000 | 0 | 100 |
|  | 518,755,400 | 504,493,603 | 14,261,797 | 2.74 |
| Miscellaneous & short term financing | 8,409,400 | 7,293,820 | 1,115,580 | 13.26 |
| Total debt servicing | 797,586,900 | 770,221,897 | 27,365,003 | 3.43 |
| 2010 | Estimate | Actual | Variance |  |
| Interest payments |  |  |  |  |
| Overseas | 28,222,600 | 22,901,709 | 5,321,891 | 18.85 |
| Domestic | 190,911,800 | 190,736,707 | 175,093 | 0.09 |
| Treasury bills | 4,500,000 | 4,295,960 | 204,040 | 4.53 |
|  | 223,634,400 | 217,934,376 | 5,701,024 | 2.54 |
| Principal repayments |  |  |  |  |
| Overseas | 79,169,100 | 32,850,575 | 46,317,525 | 58.50 |
| Domestic | 199,340,500 | 198,540,500 | 800,000 | 0.40 |
|  | 278,509,600 | 231,391,075 | 47,117,525 | 16.91 |
| Miscellaneous & short term financing | 5,837,000 | 6,018,208 | (181,208) | (3.10) |
| Total debt servicing | 507,981,000 | 455,343,659 | 52,637,341 | 10.36 |
| 2009 | Estimate | Actual | Variance |  |
| Interest payments |  |  |  |  |
| Overseas | 27,266,000 | 24,358,748 | 4,720,445 | 17.31 |
| Domestic | 156,666,700 | 165,287,007 | (8,620,307) | (5.5) |
| Treasury bills | 3,000,000 | 1,971,651 | 1,028,349 | 34.27 |
|  | 186,932,700 | 191,617,406 | (2,871,513) | (1.53) |
| Principal repayments |  |  |  |  |
| Overseas | 74,339,500 | 21,263,254 | 51,263,053 | 68.95 |
| Domestic | 255,305,000 | 245,405,000 | 9,900,000 | 3.87 |
|  | 329,644,500 | 266,668,254 | 61,163,053 | 18.55 |
| Miscellaneous & short term financing | 6,445,400 | 4,862,792 | 1,582,608 | 24.55 |
| Total debt servicing | 523,022,600 | 463,148,452 | 59,874,148 | 11.44 |

REPORT OF THE AUDITOR GENERAL OF THE REPUBLIC OF FIJI	DECEMBER 2014

APPENDIX 1.0	CHARGES ON ACCOUNT OF PUBLIC DEBT

2009-2012

PUBLIC DEBT MANAGEMENT	34